## Instructions
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
Reporting Form Instructions
Dates Reports are Due
DPH systems submit this report to the State twice a year:
|  | DY 6 (6-month) | 2011-03-02
|  | DY 6 (year-end) | 2011-05-15
|  | DY 7 (6-month) | 2012-03-31
|  | DY 7 (year-end) | 2012-09-30
|  | DY 8 (6-month) | 2013-03-31
|  | DY 8 (year-end) | 2013-09-30
|  | DY 9 (6-month) | 2014-03-31
|  | DY 9 (year-end) | 2014-09-30
|  | DY 10 (6-month) | 2015-03-31
|  | DY 10 (year-end) | 2015-09-30
Use of This Reporting Form
All DPH systems must use this reporting form template for reports starting May 15, 2011.
For the year-end report, DPH systems will include the year-end narrative, the year-end report, and reattach the
previously submitted 6-month report.
DPH systems should follow the instructions at the top of each tab for completing the form. DPH systems should
complete information for items marked "*" for each project tab and milestone being reported.

## Total Payment Amount
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
* | DPH SYSTEM: | Ventura County Medical Center
* | REPORTING YEAR: | DY 6
* | DATE OF SUBMISSION: | 2011-05-15
Total Payment Amount
This table sums the eligible incentive funding amounts. Please see the following pages for the specifics.
* | Instructions for DPH systems: Please input the DPH System Name, Reporting DY & Date. Everything else on this
tab will automatically populate.
Category 1 Projects - Incentive Funding Amounts
Expand Primary Care Capacity
Increase Training of Primary Care Workforce |  |  | 0
Implement and Utilize Disease Management Registry Functionality
Enhance Interpretation Services and Culturally Competent Care |  |  | 0
Collect Accurate Race, Ethnicity, and Language (REAL) Data to Reduce Disparities
Enhance Urgent Medical Advice
Introduce Telemedicine
Enhance Coding and Documentation for Quality Data
Develop Risk Stratification Capabilities/Functionalities
Expand Capacity to Provide Specialty Care Access in the Primary Care Setting
Expand Specialty Care Capacity
Enhance Performance Improvement and Reporting Capacity |  |  | 0
TOTAL CATEGORY 1 INCENTIVE PAYMENT: |  |  | 0
Category 2 Projects
Expand Medical Homes
Expand Chronic Care Management Models |  |  | 0
Redesign Primary Care
Redesign to Improve Patient Experience
Redesign for Cost Containment
Integrate Physical and Behavioral Health Care |  |  | 0
Increase Specialty Care Access/Redesign Referral Process
Establish/Expand a Patient Care Navigation Program
Apply Process Improvement Methodology to Improve Quality/Efficiency
Improve Patient Flow in the Emergency Department/Rapid Medical Evaluation
Use Palliative Care Programs |  |  | 0
Conduct Medication Management
Implement/Expand Care Transitions Programs
Implement Real-Time Hospital-Acquired Infections (HAIs) System
TOTAL CATEGORY 2 INCENTIVE PAYMENT: |  |  | 0
Category 3 Domains
Patient/Care Giver Experience (required)
Care Coordination (required)
Preventive Health (required)
At-Risk Populations (required)
TOTAL CATEGORY 3 INCENTIVE PAYMENT: |  |  | 0
Category 4 Interventions
Severe Sepsis Detection and Management (required) |  |  | 0
Central Line Associated Blood Stream Infection Prevention (required) |  |  | 0
Surgical Site Infection Prevention |  |  | 0
Hospital-Acquired Pressure Ulcer Prevention |  |  | 0
Stroke Management
Venous Thromboembolism (VTE) Prevention and Treatment
Falls with Injury Prevention
TOTAL CATEGORY 4 INCENTIVE PAYMENT: |  |  | 0
TOTAL INCENTIVE PAYMENT |  |  | 0

## Year-End Narrative
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  | Ventura County Medical Center
REPORTING YEAR: |  | DY 6
DATE OF SUBMISSION: |  | 2011-05-15
Year-End Narrative
This narrative summarizes the DSRIP activities performed in the reporting demonstration year.
* | Instructions for DPH systems: Please complete the narrative for year-end reports. The narrative must include
a description of progress made, lessons learned, challenges faced, other pertinent findings and participation in
shared learning.
Summary of Demonstration Year Activities
Category 1
Summary of DPH System's Participation in Shared Learning
Category 2
Summary of DPH System's Participation in Shared Learning
Category 4

## Category 1 Summary
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
Category 1 Summary Page
This table is the summary of data reported for the DPH system. Please see the following pages for the specifics.
* | Instructions for DPH systems: Do not complete, this tab will automatically populate.
The black boxes indicate Milestone achievements, either "yes/no", or the actual achievement # or %.
The blue boxes show progress made toward the Milestone ("Achievement Value") of 1.0, 0.75. 0.5, 0.25 or 0.
The red boxes indicate Total Sums.
Category 1 Projects
Expand Primary Care Capacity
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Increase Training of Primary Care Workforce
| Process Milestone: ________________________________ |  | Develop a plan for expansion of the Family Medicine Residency program | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 3964625
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 3964625
| Incentive Funding Already Received in DY: |  |  | 3964625
| Incentive Payment Amount: |  |  | 0
Implement and Utilize Disease Management Registry Functionality
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Enhance Interpretation Services and Culturally Competent Care
| Process Milestone: ________________________________ |  | Collaborate with HCIN to install technology (dual phones and video conferencing) for interpretation at VCMC | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  | Designate one trilingual (English, Spanish, Mixteco) translator and train/certify as a health care interpreter, to provide direct interpretation services to OB patients in VCMC. | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 7929250
| Total Sum of Achievement Values: |  |  | 2
| Total Number of Milestones: |  |  | 2
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 7929250
| Incentive Funding Already Received in DY: |  |  | 7929250
| Incentive Payment Amount: |  |  | 0
Collect Accurate Race, Ethnicity, and Language (REAL) Data to Reduce Disparities
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Enhance Urgent Medical Advice
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Introduce Telemedicine
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Enhance Coding and Documentation for Quality Data
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Develop Risk Stratification Capabilities/Functionalities
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Expand Capacity to Provide Specialty Care Access in the Primary Care Setting
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Expand Specialty Care Capacity
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Enhance Performance Improvement and Reporting Capacity
| Process Milestone: ________________________________ |  | Restructure the Performance Improvement (PI) Department to manage data, improve trajectory and improve activities (Lean) across the Helath Care Agency. | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 3964625
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 3964625
| Incentive Funding Already Received in DY: |  |  | 3964625
| Incentive Payment Amount: |  |  | 0

## Category 2 Summary
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
Category 2 Summary Page
This table is the summary of data reported for the DPH system. Please see the following pages for the specifics.
* | Instructions for DPH systems: Do not complete, this tab will automatically populate.
The black boxes indicate Milestone achievements, either "yes/no", or the actual achievement # or %.
The blue boxes show progress made toward the Milestone ("Achievement Value") of 1.0, 0.75. 0.5, 0.25 or 0.
The red boxes indicate Total Sums.
Category 2 Projects
Expand Medical Homes
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Expand Chronic Care Management Models
| Process Milestone: ________________________________ |  | Develop a plan for a comprehensive care management program related to diabetes care | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 3171700
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 3171700
| Incentive Funding Already Received in DY: |  |  | 3171700
| Incentive Payment Amount: |  |  | 0
Redesign Primary Care
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Redesign to Improve Patient Experience
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Redesign for Cost Containment
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Integrate Physical and Behavioral Health Care
| Process Milestone: ________________________________ |  | Co-locate a primary care clinic to include adult and pediatric behavioral health services | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  | Provide training for and adopt an evidence based treatment practice utilizing the IMPACT Collaboartive Trratment Model (Prevention and Early Intervention [PEI] for depression, anxiety, or traumatic stress disorders | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 6343400
| Total Sum of Achievement Values: |  |  | 2
| Total Number of Milestones: |  |  | 2
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 6343400
| Incentive Funding Already Received in DY: |  |  | 6343400
| Incentive Payment Amount: |  |  | 0
Increase Specialty Care Access/Redesign Referral Process
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Establish/Expand a Patient Care Navigation Program
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Apply Process Improvement Methodology to Improve Quality/Efficiency
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Improve Patient Flow in the Emergency Department/Rapid Medical Evaluation
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Use Palliative Care Programs
| Process Milestone: ________________________________ |  | Develop plan for Palliative Care Team | Yes
|  | Achievement Value |  | 1
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Process Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| Improvement Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 6343400
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 6343400
| Incentive Funding Already Received in DY: |  |  | 6343400
| Incentive Payment Amount: |  |  | 0
Conduct Medication Management
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Implement/Expand Care Transitions Programs
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Implement Real-Time Hospital-Acquired Infections (HAIs) System
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:

## Category 3 Summary
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
Category 3 Summary Page
This table is the summary of data reported for the DPH system. Please see the following pages for the specifics.
* | Instructions for DPH systems: Do not complete, this tab will automatically populate.
The black boxes indicate Milestone achievements, either "yes/no", or the actual achievement # or %.
The blue boxes show progress made toward the Milestone ("Achievement Value") of 1.0, 0.75. 0.5, 0.25 or 0.
The red boxes indicate Total Sums.
Category 3 Domains
#REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
Numerator: Number of patients in population expiring during current month hospitalization with sepsis, severe sepsis or septic shock and/or an infection and organ dysfunction. Denominator: Number of patients identified in the population that month with sepsis, severe sepsis or septic shock and/or an infection and organ dysfunction.
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
#REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
#REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
#REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
#REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:

## Category 4 Summary
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
Category 4 Summary Page
This table is the summary of data reported for the DPH system. Please see the following pages for the specifics.
* | Instructions for DPH systems: Do not complete, this tab will automatically populate.
The black boxes indicate Milestone achievements, either "yes/no", or the actual achievement # or %.
The blue boxes show progress made toward the Milestone ("Achievement Value") of 1.0, 0.75. 0.5, 0.25 or 0.
The red boxes indicate Total Sums.
Category 4 Interventions
Severe Sepsis Detection and Management (required)
| Compliance with Sepsis Resuscitation bundle (%) |  |  | N/A
Achievement Value
| Sepis Mortality (%) |  |  | N/A
Numerator: Number of patients in population expiring during current month hospitalization with sepsis, severe sepsis or septic shock and/or an infection and organ dysfunction. Denominator: Number of patients identified in the population that month with sepsis, severe sepsis or septic shock and/or an infection and organ dysfunction.
Achievement Value
| Optional Milestone: ________________________________ |  | Designate multidisciplinary team to improve Sever Sepsis Detection and Management | Yes
|  | Achievement Value |  | 1
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 695750
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 695750
| Incentive Funding Already Received in DY: |  |  | 695750
| Incentive Payment Amount: |  |  | 0
Central Line Associated Blood Stream Infection Prevention (required)
| Compliance with Central Line Insertion Practices (CLIP) (%) |  |  | N/A
Achievement Value
| Central Line Bloodstream Infection (Rate per 1,000 patient days) |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  | Designate a multidisciplinary Central Line Associated Bloodstream Infection (CLABSI) Team | Yes
|  | Achievement Value |  | 1
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 695750
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 695750
| Incentive Funding Already Received in DY: |  |  | 695750
| Incentive Payment Amount: |  |  | 0
Surgical Site Infection Prevention
| Rate of surgical site infection for Class 1 and 2 wounds (%) |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  | Develop a process to track and report SSI related to procedures reportable to the State of California | Yes
|  | Achievement Value |  | 1
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 695750
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 695750
| Incentive Funding Already Received in DY: |  |  | 695750
| Incentive Payment Amount: |  |  | 0
Hospital-Acquired Pressure Ulcer Prevention
| Prevalence of Stage II, III, IV or unstagable pressure ulcers (%) |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  | Join a collaborative related to decreasing the occurrence of hospital acquired pressure ulcers (HAPU) | Yes
|  | Achievement Value |  | 1
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| Optional Milestone: ________________________________ |  |  | N/A
Achievement Value
| DY Total Computable Incentive Amount: |  |  | 695750
| Total Sum of Achievement Values: |  |  | 1
| Total Number of Milestones: |  |  | 1
| Achievement Value Percentage: |  |  | 100%
| Eligible Incentive Funding Amount: |  |  | 695750
| Incentive Funding Already Received in DY: |  |  | 695750
| Incentive Payment Amount: |  |  | 0
Stroke Management
` | #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
` | #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Venous Thromboembolism (VTE) Prevention and Treatment
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:
Falls with Injury Prevention
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| #REF! |  |  | #REF!
|  | Achievement Value |  | #REF!
| DY Total Computable Incentive Amount: |  |  | #REF!
| Total Sum of Achievement Values: |  |  | #REF!
| Total Number of Milestones: |  |  | 0
Achievement Value Percentage:
Eligible Incentive Funding Amount:
| Incentive Funding Already Received in DY: |  |  | #REF!
Incentive Payment Amount:

## Training Primary Care Workforce
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 1: Increase Training of Primary Care Workforce
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Increase Training of Primary Care Workforce
| DY Total Computable Incentive Amount: |  |  | * | 3964625
| Incentive Funding Already Received in DY: |  |  | * | 3964625
| Process Milestone: ________________________________ |  | Develop a plan for expansion of the Family Medicine Residency Program
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
Plan developed for expansion of Residency program was completed. Submitted Residency complement expansion request to the National Resident Matching Program to increase the number of Residents from 14 to 16. Submission was completed in January 2011. In March 2011, match process completed with a full complement of 16 Residents to begin in June 2011.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | yes
|  | Achievement Value |  |  | 1
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## Interpretation Services
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 1: Enhance Interpretation Services and Culturally Competent Care
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Enhance Interpretation Services and Culturally Competent Care
| DY Total Computable Incentive Amount: |  |  | * | 7929250
| Incentive Funding Already Received in DY: |  |  | * | 7929250
Collaborate with HCIN to install technology (dual phones and video conferencing) for interpretation at VCMC
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
Acquired and opertationalized 5 HCIN terminals in the hospital in varying locations. Installation and activation was completed in February 2011. Hospitalwide training was completed in April 2011.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Designate one trilingual (English, Spanish, Mixteco) translator and train/certify as a health care interpreter, to provide direct interpretation services to OB patients in VCMC
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
One trilingual translator was hired and trained to provide translation services within the hospital in January 2011. Translator began providing translation services in OB for 40 hours/week in February 2011 and is doing outreach in other areas of the hospital as well providing translation.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## Perf Improvement & Reporting
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 1: Enhance Performance Improvement and Reporting Capacity
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Enhance Performance Improvement and Reporting Capacity
| DY Total Computable Incentive Amount: |  |  | * | 3964625
| Incentive Funding Already Received in DY: |  |  | * | 3964625
Restructure the Performance Improvement (PI) Department to manage data, improve trajectory and improvement activities (Lean) across the Helath Care Agency.
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
Organizational restructure of Performance Improvement (PI) Department was implemented by having this department report directly to the Nurse Executive with a formal linkage to the Medical Staff Committees. By implementing this change, medical staff is involved in the PI process allowing for better endorsement of the PI projects. Policy and Procedure was updated to reflect the full integration of PI throughout the Health Care Agency. PI Manager was hired in November 2010 and completed Lean Training in March 2011. In March 2011, the first Kaizen using Lean principles which was to decrease patients that leave without being seen in the Emergency Department was completed.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## Chronic Care Management
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 2: Expand Chronic Care Management Models
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Expand Chronic Care Management Models
| DY Total Computable Incentive Amount: |  |  | * | 3171700
| Incentive Funding Already Received in DY: |  |  | * | 3171700
Develop a plan for a comprehensive care management program related to diabetes care
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
Plan was developed by the Medical Director of Ambulatory Care Specialty Services and Diabetes Care Team to provide comprehensive care management related to diabetic care. Location obtained for care provision was in a space at South Las Islas Clinic. Staff were recruited and hired. This process was completed in January 2011. Physician Assistant in this clinic has completed Diabetic Educator certification in March of 2011. Wound Care training specific to diabetic patient was completed in April 2011 and currently being provided at the center by the facility's physician assistant.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## Integrate Physical Behavioral
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 2: Integrate Physical and Behavioral Health Care
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Integrate Physical and Behavioral Health Care
| DY Total Computable Incentive Amount: |  |  | * | 6343400
| Incentive Funding Already Received in DY: |  |  | * | 6343400
Co-locate a primary care clinic to include adult and pediatric behavioral health services
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
Formal integration of two primary care clinics with co-locatedBehavioral Health services in two locations: Simi Valley and Fillmore occurred in November of 2010. Simi Valley is in east Ventura County and Fillmore is in the Santa Clara Valley which is a rural location in north eastern Ventura County. Two additional locations are in the planning phase. Architectural drawings were completed in April 2011 for the build out of a co-located clinic in Thousand Oaks. The integration of care allows for referral between primary care and behavioral health in either direction to approach the patient's holistic needs in a collaborative fashion.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Provide training for and adopt an evidence-based treatment practice utilizing the IMPACT Collaboartive Trratment Model (Prevention and Early Intervention [PEI] for depression, anxiety, or traumatic stress disorders.
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
Training occurred for Medical Directors, primary care clinic champion along with the assigned PE&I Licensed Clinical Social Workers in the IMPACT Model. This training addressed how the providers interact and provide care to patients in need of focused support in the areas of depression, anxiety, or traumatic stress disorders. Licensed Clinical Social Workers were placed in eight (8) Ambulatory Care Clinics with integrated care initiated; practices continue to expand through May 2011.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## Use Palliative Care Programs
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 2: Use Palliative Care Programs
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Use Palliative Care Programs
| DY Total Computable Incentive Amount: |  |  | * | 6343400
| Incentive Funding Already Received in DY: |  |  | * | 6343400
Develop plan for Palliative Care Team
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
The Palliative Care Team plan was developed to consist of the identified and certified Physicians (2), along with a Registered Nurse, Licensed Clinical Social Worker and a Psychologist. The team was established in January 2011. The two physicians received their letters from the Board that they passed in January 2011 and certified to have "Added Qualifications in Hospice and Palliative Medicine from 2010-2020.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Process Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Improvement Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## Sepsis
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
Category 4: Severe Sepsis Detection and Management (required)
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please type in all of your DY milestones for the project below and report data
in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Severe Sepsis Detection and Management
| DY Total Computable Incentive Amount: |  |  | * | 695750
| Incentive Funding Already Received in DY: |  |  | * | 695750
Compliance with Sepsis Resuscitation bundle (%)
| Numerator |  |  | *
| Denominator |  |  | *
|  | % Compliance |  |  | N/A
| DY Target (from the DPH system plan) |  |  | *
Achievement Value
Sepis Mortality (%)
| Numerator |  |  | *
| Denominator |  |  | *
|  | % Mortality |  |  | N/A
| DY Target (from the DPH system plan) |  |  | *
Achievement Value
Designate multidisciplinary team to improve Severe Sepsis Detection and Management
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
A Physician Champion was named to head the Sepsis Taskforce. He has developed a team that consists of Registered Nurses, Respiratory Care Therapists, Clinical Lab Manager, Dietary Manager and other physicians from ICU, Emergency Department and Med/Surg units. This team has reviewed patients data from the past 6 months with diagnosis of Sepsis or Septic Shock. The team continues to develop our Sepsis detection and management process, meeting monthly or more often as needed. Education to the ED staff related to timing of care occurred in April 201. Development of the team and plan for improvement related to Sepsis care is ongoing.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## CLABSI
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
Category 4: Central Line Associated Blood Stream Infection (CLABSI) (required)
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please type in all of your DY milestones for the project below and report data
in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Central Line Associated Blood Stream Infection
| DY Total Computable Incentive Amount: |  |  | * | 695750
| Incentive Funding Already Received in DY: |  |  | * | 695750
Compliance with Central Line Insertion Practices (CLIP) (%)
| Numerator |  |  | *
| Denominator |  |  | *
|  | % Compliance |  |  | N/A
| DY Target (from the DPH system plan) |  |  | *
Achievement Value
Central Line Bloodstream Infection (Rate per 1,000 patient days)
| Numerator |  |  | *
| Denominator |  |  | *
|  | Infection Rate |  |  | N/A
| DY Target (from the DPH system plan) |  |  | *
Achievement Value
Designate a nultidisciplnary Central Line Associated Bloodstream Infection (CLABSI) Team.
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
A multi-disciplinary team was formed in November 2010 that consists of a Physician Champion, Registered Nurses, Infection Control Officer, Laboratory Manager, and other Physicians. The team developed a plan for data collection process and will provide educational training for staff and physicians during DY7.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## SSI
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 4: Surgical Site Infection Prevention
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Surgical Site Infection Prevention
| DY Total Computable Incentive Amount: |  |  | * | 695750
| Incentive Funding Already Received in DY: |  |  | * | 695750
Rate of surgical site infection for Class 1 and 2 wounds (%)
| Numerator |  |  | * | Yes
| Denominator |  |  | *
|  | % Infection Rate |  |  | N/A
| DY Target (from the DPH system plan) |  |  | *
Achievement Value
Develop a process to track and report SSI related to procedures reportable to the State of California
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
Infection Control Officer or designee has developed a process which allows for reportable information that are transmitted to the State of California periodically. This process includes data submission from medical records, data input from surgical services and education of staff and physicians to reduce the number of SSI. This process was refined and staff educated on process in January 2011.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## HAPU
CA 1115 Waiver - Delivery System Reform Incentive Payments (DSRIP)
DPH SYSTEM: |  |  | Ventura County Medical Center
REPORTING YEAR: |  |  | DY 6
DATE OF SUBMISSION: |  |  | 2011-05-15
|  |  | REPORTING ON THIS PROJECT: | * | Yes
Category 4: Hospital-Acquired Pressure Ulcer Prevention
Below is the data reported for the DPH system.
* | Instructions for DPH systems: Please select above whether you are reporting on this project. If 'yes',
please type in all of your DY milestones for the project below and report data in the indicated boxes (*).
* |  | The yellow boxes indicate where the DPH system should input data
The black boxes indicate Milestones and will automatically populate and flow to summary sheets
The blue boxes show progress made toward the Milestone ("Achievement Value") and will automatically
populate and flow to summary sheets
Hospital-Acquired Pressure Ulcer Prevention
| DY Total Computable Incentive Amount: |  |  | * | 695750
| Incentive Funding Already Received in DY: |  |  | * | 695750
Prevalence of Stage II, III, IV or unstagable pressure ulcers (%)
| Numerator |  |  | *
| Denominator |  |  | *
|  | Prevalence (%) |  |  | N/A
| DY Target (from the DPH system plan) |  |  | *
Achievement Value
Join a collaborative related to decreasing the occurrence of hospital acquired pressure ulcers (HAPU)
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | * | Yes
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | Yes
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | * | Yes
VCMC was chosen by Kaiser Foundation to participate in a HAPU educational process. This allowed VCMC to establish a HAPU team, which occurred in December 2010. This team consists of Registered Nurses, Dieticians, Physical Therapists and Physicians. In April 2011, one VCMC RN completed a Wound Certification course and passed the test. She is now part of the HAPU team.
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | * | Yes
|  | Achievement Value |  |  | 1
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value
Optional Milestone: ________________________________
(insert milestone)
| Numerator (if N/A, use "yes/no" form below; if absolute number, enter here) |  |  | *
| Denominator (if absolute number, enter "1") |  |  | *
|  | Achievement |  |  | N/A
If "yes/no" as to whether the milestone has been achieved, select "yes" or "no" from the dropdown
| menu, and (if "yes") provide an in-depth description of how the milestone was achieved: |  |  | *
| DY Target (from the DPH system plan) or enter "yes" if "yes/no" type of milestone |  |  | *
Achievement Value

## Sheet1 (hidden)
Yes
No

## Sheet4 (hidden)
Alameda County Medical Center
Arrowhead Regional Medical Center
Contra Costa Regional Medical Center and Health Centers
Kern Medical Center
Los Angeles County Department of Health Services
Natividad Medical Center
Riverside County Regional Medical Center
Santa Clara Valley Medical Center
San Francisco General Hospital & Trauma Center
San Joaquin General Hospital
San Mateo Medical Center
The University of California, Davis Medical Center
The University of California, Irvine Medical Center
UCLA Health System
The University of California, San Diego Health System
The University of California, San Francisco Medical Center
Ventura County Medical Center

## Sheet5 (hidden)
DY 6
DY 7
DY 8
DY 9
DY 10

## Sheet48 (hidden)
Manually (sample)
Registry
Data warehouse
Practice management system
Electronic medical record (EMR)