

**Programmatic Transition Plan**

Coordinated Care Initiative Beneficiary Protections

September 28, 2012

Submitted by the Department of Health Care Services

In Fulfillment of Requirements of   
Senate Bill 1008 (Committee on Budget and Fiscal Review, Chapter 33, Statutes of 2012, Welfare and Institutions Code §14182.17 (d) (10) (B))

**TABLE OF CONTENTS**

**Executive Summary** 3

**Introduction** 4

Coordinated Care Initiative 4

Health Plan Selection, Readiness, Contracts, and Oversight 7

State Administrative Background 9

Transition Plan Components 10

**Part A – Access and Quality of Service** 11

**Part B – Operational Steps, Timelines and Key Milestones for   
Beneficiary Protection Provisions of CCI** 13

(1) Ensure timely and appropriate communication with beneficiaries 13

(2) Initial Assessment Process 15

(3) Primary Care Physician Assignment 16

(4) Care Coordination16

(5) Network Readiness 18

(6) Medical and Social Needs 20

(7) Grievance and Appeals Process 20

(8) Monitor Health Plan Performance and Accountability Through Performance   
Measures, Quality Requirements, Joint Reports, and Utilization Results 21

(9) Local Stakeholder Advisory Groups Established by Health Plans 21

Key Milestones and Timeline 24

**Part C – Process for Addressing Consumer Complaints** 29

**Part D – Stakeholder Agreement** 31

APPENDICES

* Appendix A CCI Timeline 34
* Appendix B Health Plan Monitoring and Oversight 35
* Appendix C Consumer Complaints 36
* Appendix D Legislative Reporting Requirements 38
* Appendix E Beneficiary Protections Statute 40
* Appendix F Acronyms 47

**EXECUTIVE SUMMARY**

Governor Brown signed Senate Bill (SB) 1008 (Committee on Budget and Fiscal Review, Chapter 33, Statutes of 2012) and SB 1036 (Committee on Budget and Fiscal Review, Chapter 45, Statutes of 2012), as part of the Budget Act of 2012, which enacted the Coordinated Care Initiative (CCI), effective as early as March 1, 2013.   
SB 1008 requires the Department of Health Care Services (DHCS) to submit a written programmatic Transition Plan for implementation of the beneficiary protection provisions of the CCI to the relevant fiscal and policy committees of the Legislature no later than 90 days after enactment.

The law directs DHCS to coordinate with the California Department of Social Services (CDSS), the California Department of Aging (CDA), and the Department of Managed Health Care (DMHC), and to convene at least two public stakeholder meetings to obtain input that guides the development of the Transition Plan. Stakeholders include beneficiaries, providers, advocates, counties, managed care health plans and representatives of the Legislature. DHCS hosted two stakeholder meetings regarding this CCI Transition Plan. Stakeholders had an opportunity to review the draft Transition Plan and submit comments before a final version was sent to the Legislature.

As required by SB 1008, this Transition Plan provides:

1. A description of how access and quality of service shall be maintained during and immediately after implementation of the CCI in order to prevent unnecessary disruption of services to beneficiaries.
2. B. Explanations of the operational steps, timelines, and key milestones for determining when and how the components of Welfare and Institutions (W&I) Code §14182.17 (d), paragraphs (1) to (9), inclusive, shall be implemented. These paragraphs represent the core beneficiary protection provisions of the CCI.
3. The process for addressing consumer complaints, including the roles and responsibilities of the departments and health plans and how those roles and responsibilities will be coordinated. The process outlines required response times and the method for tracking the disposition of complaint cases. The process will include the use of an ombudsman, liaison, and 24-hour hotline dedicated to assisting Medi-Cal beneficiaries in navigating among the departments and health plans to help ensure timely resolution of complaints. DHCS anticipates a more comprehensive report on the process of posting this information in the next Legislative report.
4. A description of how stakeholders were included in the various phases of the planning process to formulate the Transition Plan, and how their feedback shall be taken into consideration after transition activities begin.

**INTRODUCTION**

**Coordinated Care Initiative**

In January 2012, Governor Brown announced his CCI, with the goals of enhancing health outcomes and beneficiary satisfaction for low-income seniors and persons with disabilities (SPDs), while achieving substantial savings from rebalancing service delivery away from institutional care and into the home and community. Working in partnership with the Legislature and stakeholders, the Governor enacted the CCI though SB 1008 and SB 1036.

The three major components of the CCI addressed in this report are[[1]](#footnote-2):

* A three-year demonstration project (Demonstration) for dual eligible Medi-Cal and Medicare beneficiaries to combine the full continuum of acute, primary, institutional, and home- and community-based services (HCBS) into a single benefit package, delivered through an organized service delivery system.
* Mandatory Medi-Cal managed care enrollment for dual eligible beneficiaries.
* The inclusion of long-term services and supports (LTSS) as Medi-Cal managed care benefits for SPD beneficiaries who are eligible for Medi-Cal only, and for SPD beneficiaries eligible for both Medicare and Medi-Cal (dual eligibles).

The CCI is effective in eight counties beginning as early as March 1, 2013, pending federal approval. SB 1008 also expresses the intent that these provisions be implemented statewide within three years of initial implementation. The eight counties for 2013 implementation are: Alameda, Los Angeles, Orange, Riverside, San Bernardino, San Diego, San Mateo, and Santa Clara.

Dual eligible and Medi-Cal-only SPDs are among the state’s highest-need populations. They tend to have many chronic health conditions and need a complex range of services from many providers. Because programmatic and financial responsibilities currently reside in multiple areas, the current system is fragmented and difficult to navigate. This fragmentation leads to beneficiary confusion, poor care coordination, inappropriate utilization, and unnecessary costs.

The CCI includes the following goals, as specified in SB 1008:

1. Coordinate Medi-Cal and Medicare benefits across health care settings and improve the continuity of care across acute care, long-term care, behavioral health, including mental health and substance use disorder services, and HCBS settings using a person-centered approach.
2. Coordinate access to acute and long-term care services for dual eligible beneficiaries.
3. Maximize the ability of dual eligible beneficiaries to remain in their homes and communities with appropriate services and supports in lieu of institutional care.
4. Increase the availability of and access to HCBS services.
5. Coordinate access to necessary and appropriate behavioral health services, including mental health and substance use disorder services.
6. Improve the quality of care for dual eligible beneficiaries.
7. Promote a system that is both sustainable and person- and family-centered by providing dual eligible beneficiaries with timely access to appropriate, coordinated health care services and community resources that enable them to attain or maintain personal health goals.

The CCI will use a capitated payment model to provide both Medicare and Medi-Cal benefits through the State’s existing network of Medi-Cal managed care health plans. These plans also have experience delivering Medicare services in managed care settings. The health plans will be responsible for delivering a full continuum of Medicare and Medi-Cal services, including medical care, behavioral health services, and LTSS, including HCBS services such as In-Home Supportive Services (IHSS), Community-Based Adult Services (CBAS), and Multipurpose Senior Services Program (MSSP), in addition to care in nursing facilities when needed. DHCS is developing assessment and care coordination standards which will be made public when finalized, and which will address the coordination of CBAS, IHSS, MSSP, and other services for dual eligible beneficiaries.

Consistent with DHCS’ approach to CCI program development, DHCS considers all stakeholder input on these standards. Moreover, DHCS is also identifying necessary health plan reporting requirements relating to care coordination, utilization management, service coordination, and appeals and grievances to ensure that DHCS will oversee and monitor compliance with these standards.

The CCI will protect and improve the nation’s largest personal care services program, IHSS, which serves over 430,000 individuals. IHSS is a prized program rooted in consumers’ right to self-direct their care by hiring, firing and managing their IHSS providers.  Throughout the stakeholder process for CCI, beneficiaries emphasized the critical role IHSS plays in their ability to have a high quality of life in the community.

Additionally, they emphasized the need to self-direct their care. The CCI seeks to enhance the IHSS program's ability to help people avoid unnecessary hospital and nursing home admissions, to better support beneficiaries in coordinating their care, and to preserve the right to self-direct their care. Under CCI, IHSS continues to be an entitlement program and serves as the core for HCBS. County social workers will continue to determine IHSS hours. The current fair hearing process for IHSS will remain in effect in the initial years of the Demonstration. The principles of consumer direction and continuity of care are, and will remain, key aspects of the beneficiary protections.

For the Demonstration, the State will use a passive enrollment process through which dual eligible beneficiaries may choose to opt out of the Demonstration. Pending approval by the Centers for Medicare and Medicaid (CMS), those who do not opt out will be enrolled in the Demonstration for an initial six-month stable enrollment period. During this period, they will remain in the health plan into which they are enrolled. Enrollment will be phased in starting in calendar year 2013.

Specific terms of the Demonstration will be established in the Memorandum of Understanding (MOU) between CMS and the State. The MOU will include the provisions of SB 1008, including the beneficiary protections described in this Transition Plan. The CCI will build on lessons learned during the federal Bridge to Reform 1115 Waiver (Waiver) transition of Medi-Cal-only SPDs into managed care, including the following:

* *Continuity of care.* Beneficiaries and stakeholders have repeatedly emphasized the importance of care continuity when considering new delivery models. Beneficiaries will be informed about their enrollment rights and options, plan benefits and rules, and care plan elements with sufficient time to make informed choices. This information will be delivered in a format and language accessible to enrollees. DHCS is working collaboratively with physician organizations, health plans, and advocates to improve understanding and implementation of care protections and processes. DHCS will include this work in its beneficiary and provider outreach. Further, the Medi-Cal Managed Care Division (MMCD) of DHCS will continue to work with the members of the MMCD Advisory Group (AG) to improve both the understanding of these important protections and the processes through which they are pursued.
* *Person-Centered Care Coordination.* Health plans will be responsible for providing seamless access to networks of providers across this broader continuum of care, as well as upholding strong beneficiary protections established through the stakeholder process. The model of care will include person-centered care coordination supported by interdisciplinary care teams (ICTs) and other coordination strategies, including behavioral health, substance use, LTSS, and other covered services.
* *Beneficiary Protections.* The Demonstration will include unified requirements and administrative processes that accommodate both Medicare and Medicaid, including network adequacy requirements, outreach and education, marketing, quality measures, and grievances and appeals processes.
* *Plan Monitoring and Oversight.* The State will work closely with CMS, stakeholders and beneficiaries to provide strong monitoring and oversight of health plans, and to evaluate the CCI’s impact on quality and satisfaction, service utilization patterns, and costs.
* *Provider Outreach and Engagement.* The State and CMS will coordinate efforts to engage and educate providers about the CCI leading up to and during implementation. This work already is underway through the stakeholder work group focusing on provider outreach and engagement. The State continues to consider all stakeholder recommendations concerning the optimal tools, forums, and strategies to engage providers and beneficiaries about how the CCI can improve the delivery of care to beneficiaries.
* *Transparency.* Transparency and meaningful involvement of external stakeholders, including beneficiaries, has been a cornerstone in the development of the CCI and will remain so throughout its implementation. California has embarked on a stakeholder workgroup process and will require health plans to demonstrate ongoing stakeholder involvement at the local level that includes, at a minimum, a process for gathering ongoing feedback from beneficiaries and other external stakeholders on program operations, benefits, access to services, adequacy of grievance processes, and other beneficiary protections.

For ongoing stakeholder input, DHCS has organized a series of stakeholder workgroups. These workgroups involve departments throughout the California Health and Human Services Agency (CHHS) that have been developing policy recommendations through a team–based approach. Each workgroup is co-chaired by a public stakeholder (i.e., an advocate, beneficiary, county or plan representative) and a state agency representative.

**Health Plan Selection, Readiness, Contracts, and Oversight**

The State held a rigorous joint selection process with CMS to identify health plans with the requisite qualifications and resources best suited to provide beneficiaries seamless access to an integrated set of benefits for the initial eight counties. In February 2012, the State reviewed health plan responses to the State’s Request for Solutions (RFS) for the Demonstration. Later, in July 2012, the Model of Care for each health plan was independently evaluated by the National Committee for Quality Assurance (NCQA).

In addition, during the Fall of 2012, the State and CMS will jointly assess each health plan’s readiness using a jointly developed tool to ensure the plans will meet the operational requirements. The readiness review will concentrate on each plan’s operational capability to serve Medicare-Medicaid dual eligible beneficiaries, including the delivery of all Medicare Part A, B and D services, as well as all Medicaid services, including LTSS, and behavioral health services. The readiness review will test each health plan’s major systems, including the enrollment, claims processing, and payment systems and will review the health plan’s processes related to enrollment, continuity of care, care coordination, and beneficiary protections, among others.

The readiness review process demonstrates the health plan’s ability to:

* Provide timely access to medical care to beneficiaries, and measure the adequacy of the provider networks for medical, long-term care, and behavioral health services.
* Train its staff and ensure that its delegates provide appropriate staff and contractor training to implement coordination across the continuum of services for which the health plan will be responsible.
* Submit encounter data to the State on a routine basis.
* Administer an expanded model of care that reflects necessary changes in organizational structure, staffing, and policies and procedures.
* Demonstrate that sufficient infrastructure is established and ready to administer benefits and coordinate care for the beneficiaries.
* Oversee and monitor the health plan’s ability and processes for effective, timely, and appropriate oversight of its medical groups and other delegated providers, including but not limited to, its network of LTSS providers, (for IHSS, to the extent authorized by statute).
* Deliver care across the continuum to all beneficiaries in a culturally and linguistically competent manner.
* Identify and report performance data and quality assurance/ improvements activities.

The health plan readiness reviews are instrumental to the ongoing monitoring and oversight activity of the health plans that will be coordinated by DHCS involving CMS, DMHC, and other state departments and county agencies to ensure beneficiary care is being coordinated effectively. Following a successful health plan readiness review and the completion of any corrective actions that health plans may be required to undertake, DHCS and CMS will execute a three-way contract with the health plan for the demonstration that will reflect the MOU and the provisions of SB 1008. In addition, Medi-Cal contracts between the State and health plans will be amended to reflect the LTSS and other provisions of SB 1008 for dual eligible beneficiaries that opt out of the Demonstration and for Medi-Cal-only beneficiaries.

Oversight of the health plans to ensure contract compliance for the Demonstration will be carried out by a joint CMS-State contract management team. The contract management team will ensure access, quality, program integrity and financial solvency, including reviewing and acting on data and reports, conducting studies, and taking corrective action.

The contract management team will be responsible for day-to-day monitoring of each health plan. These responsibilities include, but are not limited to:

* Monitoring compliance with the terms of the three-way contract, including issuance of joint notices of non-compliance/enforcement.
* Coordination of periodic audits and surveys of the health plan.
* Receipt and response to complaints.
* Regular meetings with each health plan.
* Coordination of requests for assistance from health plans, and assignment of appropriate State and CMS staff to provide technical assistance.
* Coordinated review of marketing materials and procedures.
* Coordinated review of grievance and appeals data, procedures, and materials.

State agencies will conduct similar oversight activities for the CCI Medi-Cal contracts for the LTSS and other managed care provisions for dual eligibles not in the Demonstration and Medi-Cal-only beneficiaries.

**State Administrative Background**

DHCS is the single State Medicaid agency in California. DHCS partners with DMHC, CDSS, and CDA to implement the CCI. CHHS coordinates many aspects of the CCI that involve multiple departments. This collaboration will ensure the State has adequate capacity to implement and oversee the CCI in eight counties in 2013 and additional counties in future years.

Within DHCS, primary responsibility for CCI lies within the Health Care Delivery Systems (HCDS) program. Within this program, the MMCD develops and administers health plan contracts, monitors contract compliance and health plan quality, administers the Medi-Cal managed care ombudsman program, and oversees the State’s beneficiary enrollment contractor, Maximus. This division also administers an interagency agreement with DMHC for additional auditing and financial oversight services. The Long-Term Care Division operates, administers, monitors, and provides oversight for a number of HCBS services waivers in California, including CBAS, MSSP, and IHSS. This division also administers the Program of All-Inclusive Care for the Elderly (PACE) in California and a federal “Money Follows the Person” grant. Both of these divisions report to the Deputy Director of HCDS and work is done collaboratively within this reporting structure.

Additional divisions within DHCS provide critical functions for the CCI. Within the DHCS Health Care Financing program, the Capitated Rates Development Division develops and coordinates capitation rates and monitors health plan expenditures. For behavioral health, the DHCS Mental Health and Substance Use Disorder program provides statewide oversight and administration of county-administered mental health and substance use programs. For Medi-Cal pharmacy beneficiaries, the Pharmacy Benefits Division provides policy guidance and review of health plan formularies. The Audits and Investigations Division ensures the fiscal integrity, efficiency, and quality of the health plans.

Among partner agencies, DMHC licenses and regulates managed care health plans, conducts routine and non-routine financial and medical surveys, and operates a Help Center where beneficiaries may lodge complaints and receive assistance with problems they have with their plans. Each health plan seeking to participate in the CCI holds a current license issued by the DMHC under the Knox-Keene Act of 1975. To maintain its license, each health plan is required to continuously meet defined regulatory standards, including timely access to care through adequate provider networks, care coordination, continuity of care, financial solvency, and treatment decisions unencumbered by fiscal or administrative considerations. The DMHC Help Center provides comprehensive beneficiary assistance, including:

* A toll-free complaint and assistance line.
* A process for quickly resolving routine health plan issues.
* An urgent nurse process for treatment denials that require immediate assistance.
* External review of medical necessity and experimental/investigational disputes.
* A thorough review process for complaints concerning all other matters, including coverage denials.

CDSS provides state-level oversight and fiscal services for the county-administered IHSS program. CDSS has engaged in various activities ensuring the scope of services and clients' choices are strengthened while preparing for the transition to a managed care environment, focusing on the consumer experience, and promoting consumer rights as it moves forward into managed care. Activities include development of a MOU template for operations between managed care health plans and the counties and public authorities; planning an October 2012 event to work with partner agencies, managed care health plans, counties and stakeholders to identify important data sharing needs for the Demonstration, and ensuring IHSS contract mode agencies are certified both fiscally and programmatically. Additionally, CDSS staff have been working with California Office of Human Resources (CalHR) to assist in the information and data necessary for the transition to a statewide authority, as well as the development of a state-level advisory committee made up of consumers and stakeholders.

CDA administers MSSP and the Health Insurance Counseling and Advocacy Program (HICAP), which offers Medicare beneficiaries, as well as those about to become eligible for Medicare, counseling on Medicare, Medicare supplemental policies, health plans, and long-term care insurance.

**Transition Plan Components**

As required by SB 1008, in W&I Code §14182.17(d)(10)(B), this Transition Plan addresses each of the following:

1. A description of how access and quality of service shall be maintained during and immediately after implementation of these provisions, in order to prevent unnecessary disruption of services to beneficiaries.
2. Explanations of the operational steps, timelines, and key milestones for determining when and how the components of W&I Code §14182.17 (d), paragraphs (1) to (9), inclusive, shall be implemented. These paragraphs represent the core beneficiary protection provisions of the CCI.
3. The process for addressing consumer complaints, including the roles and responsibilities of the departments and health plans and how those roles and responsibilities shall be coordinated. The process shall outline required response times and the method for tracking the disposition of complaint cases. The process shall include the use of an ombudsman, liaison, and 24-hour hotline dedicated to assisting Medi-Cal beneficiaries in navigating among the departments and health plans to help ensure timely resolution of complaints.
4. A description of how stakeholders were included in the various phases of the planning process to formulate the Transition Plan, and how their feedback shall be taken into consideration after transition activities begin.

Note that while this Transition Plan incorporates many stakeholder comments, DHCS has carefully reviewed all submitted comments and will give all suggestions consideration in the process of implementing the components of the CCI.

**PART A - ACCESS AND QUALITY OF SERVICE**

*SB 1008 requirement: A description of how access and quality of service shall be maintained during and immediately after implementation of these provisions, in order to prevent unnecessary disruption of services to beneficiaries.*

The provisions below will allow beneficiaries to maintain continued access to providers and services during and after implementation of the CCI.

Note that DHCS and DMHC are collaborating to determine the overlap of state standards and services funded by the federal government.

* Network adequacy reviews, conducted by CMS and DHCS, are a key process to ensure that health plans have sufficient providers in their networks to meet the needs of members and provide sufficient access to care. For Medicare benefits, CMS has reviewed health plan networks and ensured they meet Medicare Advantage adequacy standards. For Medi-Cal LTSS benefits, DHCS will review health plan networks in the Fall of 2012, as part of the readiness review process, to ensure that the plans meet the State’s newly established LTSS network adequacy standards. Further details regarding network adequacy and the readiness review process are provided in Part B, paragraph 5 of this report.

The CCI provides key continuity of care and network adequacy provisions, as noted below. Advance planning regarding continuity of care issues, coupled with dedication to resolving transitional care issues faced by each beneficiary is central to meeting immediate care needs, while also ensuring optimal long-term outcomes. Continuity of care standards will be communicated to the health plans so that adequate care can be arranged for beneficiaries either in or out of network. DHCS, CMS, and DMHC will monitor and enforce these provisions as part of the readiness review process, throughout implementation, and on an ongoing basis. Additional information on implementation of these provisions is described in Part B, paragraph 5 of this report.

* + Medi-Cal Continuity of Care: Beneficiaries may, under specific conditions, have access to out-of-network Medi-Cal providers for up to 12 months after enrollment. [W&I Code §14182.17 (d)(5)(G)]
  + Medi-Cal Continuity of Care for Nursing Facility Care: For nursing facility care, managed care health plans will recognize any prior treatment authorization made by DHCS for up to twelve months after enrollment into the health plan. [W&I Code §14186.3 (c) (3)]
  + Medicare Continuity of Care: Beneficiaries will have access to   
    out-of-network Medicare providers for the first six months of enrollment. [W&I Code §14132.275 (l)(2)(A]
  + Medicare Part D Continuity of Care: DHCS and CMS will implement and enforce Medicare Part D transition of care provisions, to ensure that health plans provide an appropriate transition process for newly enrolled beneficiaries who are prescribed Part D drugs that are not on the health plan’s formulary [W&I Code §14182.17 (d)(2)(F)]
  + Health Plan Liaisons: Health plans will maintain liaisons to coordinate access for out of network Medi-Cal providers, and to coordinate with California’s Regional Centers, which help to coordinate services for individuals with developmental disabilities. The continuity of care liaison will ensure provider access and a smooth transition for each beneficiary into the demonstration. [W&I Code §14182.17 (5)(F) and (G)]
  + Provider Physical Accessibility: Health plans will contract with providers that meet physical accessibility requirements. [W&I Code §14182.17 (d)(5)(A)]
  + Alternative Format: Health plans will provide information in alternative formats [W&I Code §14182.17 (d)(5)(A)]
  + Listing of Providers’ Ability to Accept New Patients: Health plans will maintain an updated, accurate, and accessible listing. [W&I Code §14182.17(d)(5)(C)]
* DHCS will develop descriptions of continuity of care rights in all threshold languages and alternative, accessible formats, and distribute these materials to beneficiaries through plans and providers.
* To further strengthen provider access, DHCS is conducting a provider outreach workgroup and related activities to ensure that health care providers receive information about the CCI, and to document and address any concerns that they may have. Provider engagement and participation in health plan networks is a key component of maintaining access for beneficiaries.
* DHCS, CMS, and DMHC are currently reviewing responsibility for monitoring compliance with state and federal timely-access provisions. DMHC recently promulgated regulations regarding Timely Access to Non-Emergency Health Care Services (California Code of Regulations §1300.67.2.2). DHCS and DMHC are reviewing the applicability of the regulation to the Demonstration.

***Quality of Services:***  *Please see information under Part B, paragraph 8 of this report for a description of how DHCS, in collaboration with other state agencies, will implement provisions that will help maintain the quality of services during and immediately after implementation of the CCI.*

**PART B - OPERATIONAL STEPS, TIMELINES AND KEY MILESTONES FOR BENEFICIARY PROTECTION PROVISIONS OF CCI**

*SB 1008 requirement: Explanations of the operational steps, timelines, and key milestones for determining when and how the components of W&I Code* §*14182.17 (d), paragraphs (1) to (9), inclusive, shall be implemented.*

The key operational steps to implement these provisions are listed below. Stakeholder input will be incorporated throughout, by means of an ongoing process.

1. State and federal review of health plans’ Model of Care.
2. The MOU between the State and CMS.
3. The Readiness Review Process.
4. Three-way contracts and amended Medi-Cal contracts with the health plans.
5. Ongoing oversight through the Contract Management team.

**(1) Ensure timely and appropriate communication with beneficiaries**

To ensure timely and appropriate communication with beneficiaries, DHCS is undertaking the following activities.

Enrollment and Notification Strategy

Beneficiaries will be sent an informing notice at least 90 days prior to the health plan enrollment effective date, followed by a 60-day notice with plan information and selection materials and a 30-day reminder notice. A final confirmation letter will be sent to the beneficiary confirming his or her plan choice and the effective enrollment date.

* All beneficiary notices will be released for stakeholder review at least 60 days prior to mailing to the beneficiaries. DHCS will collect comments and update the material as appropriate. The release of beneficiary notices will be scheduled by population groups. The standard notification process will be based on a   
  phased-in enrollment schedule that may vary by county.
* All beneficiary notices and enrollment materials will require a reading proficiency no higher than sixth grade level and will be available in all the Medi-Cal threshold languages required under current state law, as well as in alternative formats, all of which are culturally, linguistically, and physically appropriate.
* For in-person enrollment, disability accommodation such as assistive listening systems, sign language interpreters, captioning, and written communication, will be available.
* DHCS is working with the enrollment contractor, Maximus, to clarify the process for authorizing legal representatives, such as a caregiver, family member, conservator, or a legal services advocate, to communicate with the contractor on enrollment issues and make elections on the beneficiary’s behalf when necessary and appropriate.
* Beneficiary notices will be made available for public view through the website [www.calduals.org](http://www.calduals.org) and made available to providers before they are mailed to beneficiaries.
* Eligible beneficiaries who are enrolled in and do not opt out of the Demonstration will be automatically assigned to a primary care provider to ensure coordinated health care delivery.

Transition of Care for Part D Benefits

Through the readiness review process, CMS and the State will ensure that health plans have policies and procedures in place to address the effective transition of beneficiaries from Medicare Part D plans not participating in the demonstration.

Outreach Plan: DHCS is developing a targeted outreach and education program informing dual eligible and Medi-Cal only SPD beneficiaries of their enrollment options and rights, including specific steps for working with consumer and beneficiary community groups. This plan will explore opportunities to contract with   
community-based, nonprofit consumer or health insurance assistance organizations, such as local HICAPs with expertise and experience in assisting beneficiaries in understanding their health care coverage options.

Communication Plan: DHCS is developing, in consultation with beneficiaries and other stakeholders, an overall communications plan that includes all aspects of developing beneficiary notices, including the enrollment notice time frame, alternative formats, accessible formats, and ensuring the materials are culturally and linguistically appropriate. This communications plan will build on the experience gained during the Medi-Cal-only SPD program transition process and the extensive input received during the stakeholder process and Transition Plan comment period. DHCS recognizes the need for its communication plan and strategy to consider alternative communications beyond the required notices to ensure beneficiaries and providers fully understand CCI’s benefits.

Health Plan Oversight for Enrollment Communication: DHCS will ensure that managed care health plans have prepared materials to inform beneficiaries of procedures for obtaining Medi-Cal benefits, including grievance and appeals procedures. Communication and services will be available in alternative formats that are culturally, linguistically, and physically appropriate through means including, but not limited to, assistive listening systems, sign language interpreters, captioning, written communication, plain language and written translations.

**(2) Initial Assessment Process**

Health plans will be responsible for an in-depth risk assessment process capable of timely identification of primary, acute, LTSS and behavioral health and functional needs. The multi-tiered process will begin with a risk stratification process, followed by a health risk assessment of each beneficiary, and a comprehensive assessment as needed, conducted upon enrollment in the Demonstration.

Health plans will use a risk stratification mechanism or algorithm developed by the health plan and reviewed and approved by DHCS to analyze historical Medicare and Medi-Cal utilization data and identify higher-risk, lower-risk and other stratification groups. Health plans will also conduct an initial health risk assessment. This initial assessment will serve as a triage for further assessment needs in a variety of areas including, but not limited to, mental health concerns, substance abuse concerns, chronic physical conditions, and potential needs related to key activities of daily living, dementia, cognitive status and the capacity to make informed decisions. DHCS is evaluating whether it will require health plans to complete beneficiary risk assessments within the 90-day window established for the Medicare Program, or the 45-day window for high risk beneficiaries and the 105-day window for low-risk beneficiaries established for the Medi-Cal-only SPDs. Health plans will be required to share assessment results and care plans with providers.

The initial and comprehensive assessment will help inform the health plan and providers in creating an appropriate individual care plan, and help beneficiaries in accessing all necessary resources. Individual care plans will be used to address risk factors, prevent health disparities, and reduce the effect of multiple co-morbidities. Care plans will be developed for beneficiaries that include member goals and preferences, measurable objectives and timetables to meet his or her medical, psychosocial, and long-term support needs that are identified in the assessment process.

DHCS will develop thoughtful delegation of oversight criteria and standards related to care coordination and assessment. Health plans will be required to adhere to these standards when overseeing their subcontracted providers, independent physician associations (IPA), and medical groups. Building on what was learned from the transition of the Medi-Cal-only SPD population into Medi-Cal managed care, the State will work with plans and providers to ensure necessary processes and procedures are in place to support timely health risk assessments. In addition, California’s health plans will use promising practices, such as repeated attempts to gather assessment information via various modes (phone, mail, interactive voice by phone) and web-based care planning tools that allow providers and beneficiaries to view and add to the care plan.

Strategies will also include review of fee-for-service utilization data to prioritize assessment and care planning, and to provide an appropriate transition process for newly enrolled beneficiaries who are prescribed Medicare Part D drugs that are not on the Demonstration site’s formulary. DHCS is developing data files for health plans for this purpose.

For the delegation oversight standards, health plans will be expected, and required, to oversee their subcontracted providers, IPAs, and medical groups in connection with the standards and criteria associated with care coordination and the assessment process. Further, DHCS will closely monitor delegation of oversight activities to ensure compliance with these standards. A review of health plan delegation oversight policies and procedures will also be part of the plan readiness review process. DHCS will monitor health plans’ communication with IPAs and medical groups, to ensure assessment information, at all levels, is being shared appropriately and used to develop care plans that are also shared appropriately.

**(3) Primary Care Physician Assignment**

This section of SB 1008 addresses primary care physician (PCP) assignment for dual eligible beneficiaries not enrolled in the Demonstration, by requiring Medi-Cal health plans to:

* Not interfere with a beneficiary’s PCP choice under Medicare.
* Not assign a full-benefit dual eligible beneficiary to a primary care physician except for specific circumstances.
* Assign a PCP to a partial-benefit dual eligible beneficiary receiving primary or specialty care through the Medi-Cal managed care plan.
* Provide a mechanism for partial-benefit dual eligible beneficiaries to request a specialist or clinic as the primary care provider.

Some of these provisions will be incorporated into existing Medi-Cal managed care health plan contracts as early as the Fall of 2012. DHCS will ensure that the remaining provisions are incorporated into the contracts, effective upon mandatory enrollment of dual eligible beneficiaries, and will monitor and enforce these contract provisions.

Dual eligible beneficiaries enrolled in the demonstration will be assigned a PCP. DHCS and health plans will make every effort to ensure PCP assignment matches the current PCP.

**(4) Care Coordination**

DHCS is operationalizing the care coordination provisions of SB 1008 through five steps: 1) review of the health plans’ Models of Care; 2) establishing care coordination standards; 3) confirmation that care coordination standards are met during the readiness review process; 4) reiterating the ongoing requirements in the contract terms and conditions, and 5) monitoring compliance and outcomes. DHCS is currently developing care coordination standards for the health plans. Connected to this ongoing work, DHCS will incorporate as appropriate, stakeholder comments and recommendations concerning LTSS standards and the role, composition and management of the Interdisciplinary Care Team (ICT). These standards will incorporate the following approaches in conjunction with the provisions specified in W&I Code §14182.17 (d) (4):

* Connect the medical assessment/coordination to LTSS and behavioral health assessment/care coordination process.
* Build on the existing knowledge and experience of health plans in the care coordination process for Medi-Cal-only SPDs.
* Incorporate key elements of the Dual Eligible Special Needs Plan (D-SNP) process, as required by SB 1008, to reflect local flexibility, Medicare requirements, and oversight through the NCQA review process.
* Incorporate beneficiary protections from SB 1008 and SB 1036, as well as lessons learned from other states and national guidelines.
* Provide flexibility for plan-specific modifications, subject to prior written approval by DHCS in consultation with CMS.
* Establish consistent terminology and clear, measurable expectations for health plans. Establish clear written reporting requirements relating to the assessment process so that the plans will be able to establish a basis for any quality withhold relating to compliance with the standards.

The Assessment and Care Coordination Standards are expected to provide specific requirements for health plans in the following areas:

* Definitions.
* Risk Stratification.
* Health Risk Assessment Process.
* Comprehensive Assessment Process.
* Individual Care Plans.
* Care Coordination General Requirements.
* Reassessment and Care Coordination Monitoring.
* Care Coordinator Responsibilities.
* Levels of Care Coordination, including ICTs.
* Requirements for Delegated Models.
* Care Transitions.

Ongoing Monitoring and Reassessment:

DHCS received numerous comments regarding the composition of the ICT and care coordination standards. The Care Coordination standards, scheduled for release for public comment in October 2012, will address those comments, and update the ICT description that was originally included in the draft transition plan.

Recording and storage of documentation and data:

The State requires the plan to ensure a care management system that documents, for each managed care member: the member’s completed health assessment; care plan; care notes; service provided; utilization pattern; and record of claims paid. This documentation/data may be subjected to random sampling and detailed case review by state reviewers or auditors for accuracy.

Case follow-up and monitoring:

The health plans will develop policies and procedures to implement an array of methods for follow-up and monitoring of cases. These may include face-to-face visits, telephone calls or direct e-mail contact as appropriate.

LTSS Care Coordination:

Health plans will enter into agreements with county social service agencies and Public Authorities, MSSP and CBAS sites, and nursing facilities. Those agreements will include care coordination roles and responsibilities. In addition, the readiness review process will require health plans to provide policies and procedures for joint care coordination between health plans and LTSS agencies and providers.

Behavioral Health Care Coordination:

Health plans will enter into an MOU with county behavioral health agencies, which will address joint behavioral health care coordination roles and responsibilities. In addition, the readiness review process will require health plans to provide policies and procedures for joint care coordination between health plans and behavioral health agencies and providers.

**(5) Network Readiness**

As mentioned earlier in this Transition Plan, the network readiness section is still under development and has received many comments, particularly around the State’s work to define LTSS. Some questions include development of standards for Durable Medical Equipment (DME) and Non-Emergency Medical Transportation (NEMT), and access to institutional long-term care and palliative care.

State network standards shall be utilized for LTSS and the prescription drugs covered by Medicaid which are excluded from Medicare Part D. Medicare network standards shall be used for Medicare prescription drugs and other services for which Medicare is the primary coverage. DME, home health services, and any other services for which Medicaid and Medicare coverage overlap shall be subject to State Medicaid network standards so long as the State can show that such standards are at least as stringent and beneficiary-friendly as Medicare standards.

Provider networks will be subject to confirmation through Demonstration plan readiness reviews in October and November 2012, including the following:

IHSS: Demonstration plans are required to have an MOU or contract with their respective county social services agencies and public authority entity to provide IHSS for their beneficiaries. Such agreements will require the county to provide:

* + - * IHSS eligibility assessment and authorization of IHSS hours.
      * Coordination of IHSS delivery with other Demonstration plan covered benefits.
      * Quality assurance.
      * IHHS provider enrollment, access and training.
      * IHHS background checks and registry services.
      * Data sharing.
      * A local IHSS advisory committee.

Demonstration plans must contract with CDSS to perform the following:

* + - * Pay wages to IHSS providers and perform provider payroll obligations and related technical assistance.
      * Share beneficiary and provider data.
      * Provide an option for Demonstration plans to participate in quality monitoring activities.

Demonstration plans may contract with other agencies to provide emergency backup personal care services, or in cases where a beneficiary cannot find a provider, for as long as such agencies are certified by CDSS. Demonstration plans shall provide county social services agencies with information regarding the authorization of services by the plan in accordance with the MOU agreements between the plan and social service agency.

Nursing Facilities: Demonstration plans will contract with licensed and certified nursing facilities. Demonstration plans must maintain continuity of care for beneficiaries residing in out-of-network facilities until a safe transfer can be made to an in-network facility. Demonstration plan contracted facilities will be located in zip code areas covered by the Demonstration and, to the extent possible, in adjacent zip code areas.

MSSP: Demonstration plans must contract with MSSP organizations in good standing with CDA in the covered zip code areas included in the Demonstration, and to the extent possible, in the adjacent zip code areas. The contract will cover the provision of MSSP case management and MSSP waiver services for MSSP waiver participants, and beneficiary data sharing. Additionally, health plans may contract with an MSSP organization to provide care coordination and MSSP-like services to non-waiver beneficiaries as needed. Health plans must allocate to the MSSP providers the same level of funding they would have otherwise received under their MSSP contract with CDA.

CBAS: Demonstration plans must contract with all willing, licensed, and certified CBAS centers that are located in the covered zip codes areas and in adjacent zip code areas, which must not be more than 60 minutes driving time away from the eligible individual’s residence. If a CBAS center does not exist in the targeted zip code areas, does not have service capacity, or does not have cultural competence to service specific health plan beneficiaries, health plans must coordinate IHSS and home health care services for CBAS-eligible enrollees.

The State will require that health plans ensure that each health plan has   
non-emergency, accessible medical transportation available in sufficient supply so that individuals have timely access to scheduled and unscheduled medical care appointments.

The State will require that health plans contract with a sufficient number of medical providers, ancillary service providers, and DME suppliers.

**(6) Medical and Social Needs**

Dental and vision may be required benefits, depending upon rate development. If these services are required, the scope of benefits will be described in the health plan contract. If they are not required, health plans may choose to offer these benefits. HCBS plan benefits will be required; DHCS is currently developing health plan requirements for those benefits.

Health plans will be required to incorporate referrals to community resources into their Models of Care and to provide other activities or services needed to assist beneficiaries in optimizing their health status. These services will be specified in the health plan contract requirements.

Health plans will be required to use the most recent common procedure terminology (CPT) codes, modifiers, and correct coding initiative edits.

**(7) Grievance and Appeals Process**

For the Demonstration, the grievance and appeals process is jointly managed by the State of California, County Social Services Agencies, and CMS. The overall intent for the first year is to build upon existing grievance and appeals processes. For years two and three, the DHCS goal is to develop a unified process. The unified process will not be more restrictive than the current Medi-Cal process. The unified process will be reviewed with stakeholders and will be communicated to beneficiaries and providers.

The grievance and appeals process for beneficiaries not enrolled in the Demonstration will be the current Medi-Cal process, which complies with W&I Code §14450, and Health and Safety Code §1368 and 1368.01. The departments will coordinate the grievance and appeals process among the various options in year one.

The IHSS grievance and appeals process will not change and is comprised of the following:

* A state fair hearing is conducted by the CDSS and the county.
* Following a final decision, a request for a rehearing review must be submitted within 30 days.
* Any request for a state court hearing must be filed within one year of the final decision.

The grievance and appeals process for prescription drugs under Medicare Part D will not change, and requires beneficiaries to coordinate with their health plan and CMS. With regard to the medical exemption process used for the SPD transition, beneficiaries eligible for the Demonstration will have the choice to opt-out of enrollment. The only anticipated use of an emergency disenrollment process for the Demonstration will be as a safeguard for populations that are otherwise excluded populations (e.g. persons with end stage renal disease [ESRD]) but are inadvertently passively enrolled.

*For additional information please see “Process for Addressing Consumer Complaints” section below.*

**(8) Monitor Health Plan Performance and Accountability Through Performance Measures, Quality Requirements, Joint Reports, and Utilization Results**

DHCS, DMHC, and CDSS will implement the monitoring requirements of this subdivision by doing the following:

* The State and CMS will jointly: 1) review the health plan’s provider network to ensure an adequate number of providers are available to beneficiaries; 2) examine financial solvency of the health plans; 3) verify that requirements of timely access to medical care are being met; and 4) conduct medical surveys with beneficiaries and onsite surveys of health plans on a recurring basis.
* DMHC and DHCS will submit an annual joint report on financial audits performed on health plans.
* DHCS will coordinate with DMHC, CDSS, and CMS to monitor corrective action plans and performance of the health plans.
* DHCS will continue to work with stakeholders and CMS to develop ongoing quality measures for health plans for the Demonstration, which will include primary and acute care, LTSS, and behavioral health services.
* The State will continue to contract with an External Quality Review Organization (EQRO) to audit health plans for quality measures and will contract with an EQRO to audit encounter data as well.
* In conjunction with the Demonstration evaluation efforts, DHCS and CDSS will monitor the utilization of medical services and LTSS (including IHSS), and will identify and share any significant changes in aggregate or average utilization among beneficiaries participating in the Demonstration.

**(9) Local Stakeholder Advisory Groups Established by Health Plans**

With CMS, DHCS is developing joint readiness review standards for health plans, which will include requirements for local stakeholder advisory groups. The health plans are meeting with stakeholder groups and planning ongoing meetings of advisory groups. Examples of local stakeholder outreach activities, by county, appear below. DHCS has encouraged health plans to obtain input from beneficiaries, and to conduct public beneficiary stakeholder meetings in their areas.

* **Alameda**
  + **Alameda Alliance for Health and Anthem/Blue Cross/CareMore**

This group formed the Alameda County Dual Demonstration Steering Committee meeting. The collective county-wide group met on May 23, June 3, June 28, and September 5, 2012. At these meeting, representatives from the following organizations/programs attend: County Social Services, County Public Authority, IHSS, Agency on Aging (AOA), MSSP, CBAS, County Mental Health, Hospital Association Regional Representatives, Centers for Independent Living, and Skilled Nursing Home and Residential Care Home facilities.

* **Los Angeles**
  + **LA Care**

LA Care held stakeholder meetings and has three more planned; is a member of the Duals Steering Committee; contracts with Neighborhood Legal Services for presentations; and formed the Hospital Advisory Committee.

* + **Health Net**

Health Net has collaborated with LA Care to develop a streamlined stakeholder outreach process for community agencies. Three workgroups have been formed and meet on a regular basis to help define and develop the operational model for incorporating LTSS and behavioral health into the Demonstration operating model. Participants include representatives from the health plans, CDSS, DHCS, AOA, Department of Mental Health (CDMH) and the Department of Public health (CDPH).

* **Riverside and San Bernardino**
  + **Inland Empire Health Plan**

Has three existing stakeholder committees: Inland Empire Disability Collaborative, Persons with Disabilities Workgroup, and Provider Advisory Committee. Has plans to form the Inland Empire Disability Collaborative to meet with over 400 representatives of community and social organizations each month. This facilitates flow of communications between Inland Empire Coordinated Care Advisory Committee and other groups.

* + **Molina**

Molina participates monthly in Inland Empire Disabilities Collaborative; plans to form Advisory Committee and subgroup; and to sponsor joint education sessions with county agencies and health plans. Through June and July 2012, county agencies and health plans participated in joint education sessions to learn about LTSS. In August 2012, the health plans (Molina and Inland Empire Health Plan) and agencies of the two counties established a design team for purposes of coordinating the IHSS and MSSP services.

* **San Diego**
  + **Care1st, Community Health Group, Health Net, and Molina**

The Demonstration health plans, Department of Aging and Independence Services (AIS), and Healthy San Diego, jointly identify areas of collaboration surrounding the Demonstration. To facilitate stakeholder input for the San Diego Demonstration, San Diego County's Long Term Care Integration Project has transformed into the San Diego Duals Advisory Committee. Membership in the Dual Eligible Demonstration Advisory Committee includes but is not limited to the following organizations and providers:

• Health Plans

• County of San Diego Health and Human Services Agency

• The County of San Diego In-Home Supportive Services Public Authority

• Dual eligible consumers of LTSS

• Hospital Association of San Diego and Imperial Counties

• The Consumer Center for Health Education and Advocacy

• The Health Insurance Counseling and Advocacy Program

• CBAS

• PACE

• Labor Unions

• Community Clinics

• HCBS providers of LTSS

• Skilled Nursing Facilities

• Hospice

* **San Mateo**
  + **Health Plan of San Mateo (HPSM)**

HPSM has already built support from key providers and stakeholders through a series of in-person meetings to discuss interest in this opportunity and program design ideas. Over a period of several years, HPSM has discussed integrating LTSS with these entities: hospitals in the community through the local Hospital Consortium; physicians through HPSM’s physician advisory committees; nursing facilities; Adults Day Health Care centers (now CBAS); the IHSS/Public Authority Advisory Committee; Commission on Aging; Commission on Disabilities; Mental Health and Substance Abuse Recovery Commission; Health and Human Services Committee of the Board of Supervisors; SEIU, the union representing IHSS providers; community forums such as for the reauthorization of the Older Americans Act; the New Beginnings Coalition (a broad locally based coalition of community advocates); and nonprofit housing providers.

* **Santa Clara**
  + **Santa Clara Family Health Plan and Anthem/Blue Cross/CareMore**
* These two plans have developed aDuals Steering Committee. The Steering Committee is comprised of representatives from the following organizations and programs: the Social Services Agency, Public Authority/IHSS, Council on Aging, MSSP, CBAS, County Mental Health Department, Hospital Association Regional Representatives, Centers for Independent Living, and Skilled Nursing Home and Residential Care Home facilities, and labor representatives.

**Key Milestones and Timeline**

*See Appendix A for timeline chart.*

Enrollment in the CCI will occur no sooner than March 1, 2013. However, a number of steps must occur well before that date, constituting the key milestones for implementation of the CCI. Other milestones indicate key dates for monitoring quality and outcomes after implementation.

(Note: These are not listed in priority order.)

1. Develop and maintain stakeholder distribution list:
   * DHCS has developed and is maintaining a stakeholder list that includes beneficiaries, advocates, health plan representatives and other interested parties. This list currently has over 2,300 participants and is ongoing.
   * DHCS will continue to augment the stakeholder list as it receives new contact information and will continue to send notices to these stakeholders as needed (ongoing).
2. Plan and conduct stakeholder meetings with beneficiaries; advocates; health plans; providers and their representatives; and county representatives, both before and after enrollment begins. Key components include:

* DHCS workgroup meetings:
  + - Beneficiary Enrollment, Notification, Appeals, and Protections   
      (met April 12, April 25, May 10, May 24, June 7, June 21 and   
      August 7, 2012).
    - Provider Outreach and Engagement (met April 19 and June 13, 2012).
    - IHSS Coordination (met May 11, May 17 and June 14, 2012).
    - LTSS Integration (met May 3, June 28, and August 8, 2012).
    - Behavioral Health Integration (met April 18, May 16, June 20, and August 15, 2012).
    - Fiscal and Rate Setting (met June 5, 2012).
    - Quality and Evaluation (met May 17, June 19, July 26, and August 14, 2012).
  + Ongoing communications:
    - Continuous consultation with stakeholders. All CCI materials will continue to be posted online at [www.calduals.org](http://www.calduals.org).
  + Stakeholder Review of Transition Plan:
    - DHCS consulted with stakeholders twice following production of a draft of the implementation plan and before submission to the Legislature. (Meetings were held August 29 and September 4, 2012.)

1. Develop, in consultation with consumers, beneficiaries, and other stakeholders, an overall communications plan that includes all aspects of developing beneficiary notices (expected by October 2012).
2. Conduct RFS process for the Demonstration:
   * Share draft for public comment (completed December 23, 2011).
   * Publish final (completed on January 27, 2012).
   * Health plan submissions (received February 2012).
   * Review health plan submissions (completed March 9, 2012).
   * Announce selection (Completed March 21, 2012).
3. Prepare and Submit Demonstration Proposal:
   * Draft for public comment (completed May 4, 2012).
   * Publish final and submit to CMS (completed May 31, 2012).
   * CMS approves California’s Demonstration Proposal by way of approving the MOU. Any changes to the Demonstration Proposal will be included in the MOU and as an addendum to the proposal.
4. Review Health Plans’ Models of Care and Plans’ Benefits Packages:

* Review health plan applications, identify deficiencies, and confirm that deficiencies have been corrected (completed July 20, 2012).
* Review formulary file submissions, identify deficiencies, and confirm that deficiencies have been corrected (completed August 31, 2012).
* Review plan benefit package, identify deficiencies, and confirm that deficiencies have been corrected (completed August 31, 2012).
* Review a unified model of care, identify deficiencies, and confirm that deficiencies have been corrected (completed August 31, 2012).

1. Execute MOU with CMS:

* CMS submit draft MOU language (completed July 2, 2012).
* CMS/DHCS conduct MOU negotiations (July–September, 2012).
* DHCS and CMS sign MOU (anticipated Fall 2012).

1. Develop Enrollment Process:

* Draft enrollment process and timelines (completed July 2012).
* Share draft enrollment phase-in timeline with stakeholders (completed   
  August 7, 2012).
* Finalize enrollment phase-in process and timeline (Fall 2012).
* Coordinate with CMS systems (Fall 2012).
* Submit final enrollment specifications to the Information Technology Services Division (ITSD) of DHCS and Maximus (Fall 2012).

1. Develop Beneficiary Notices:

* Develop joint notices and enrollment materials with CMS (July-September 2012).
* Share beneficiary notices and enrollment materials with stakeholders (September-October, 2012).
* Submit final notification specifications to Maximus (Fall 2012).
* Prepare DHCS website for posting enrollment and notification materials (Fall 2012).
* Maximus finalizes notices and programs into systems—including translations (Fall 2012).
* Begin initial notification mailings for December notices (Fall 2012).

1. Prepare Beneficiary and Provider Outreach and Education Plan:
   * Draft plan and share with stakeholders (complete by October 15, 2012).
   * Finalize plan (November 2012).
   * Conduct outreach activities (webinars, forums, presentations, etc.) throughout the Demonstration.
2. Develop Grievance and Appeals Process (Year 1):
   * Draft initial process and submit for stakeholder review (completed on   
     April 25, 2012).
   * Update processes and resubmit for stakeholder review (November 2012).
   * Finalize grievance and appeals process (December 2012).
   * Draft processes for year two (2013).
3. Develop LTSS Provider Network Adequacy Standards:
   * Draft standards (completed July-August 2012).
   * Post draft for public comment (completed on August 15, 2012).
   * Finalize standards (October 2012).
4. Complete Readiness Reviews:
   * Develop tool and consult with stakeholders (September-October 2012).
   * Share with plans (October 2012).
   * Conduct plan reviews (Fall-Winter 2012).
   * Identify deficiencies and communicate to plans (Fall-Winter 2012).
   * Follow up with plans to ensure deficiencies are corrected (Winter 2012).
   * Finalize reviews and summarize findings (Winter 2012).
5. Determine Supplemental Benefits Policy:
   * Develop draft guidelines for the scope, duration, and intensity of HCBS plan benefits and share with stakeholders (September-October 2012).
   * Review rates with CMS and determine whether dental, vision, chiropractic, and HCBS plan benefits will be required or optional for health plan benefit package (2012).
   * Finalize guidelines and standards for HCBS plan benefits   
     (September-October 2012).
6. Amend the Waiver:
   * DHCS will determine changes that are necessary to amend the Waiver (Fall 2012).
   * Submit the Waiver for CMS Approval (Fall-Winter 2012).
7. Provide Tribal Notification:
   * DHCS will provide tribal notification on any changes to the Waiver and obtain input as required by federal law (August 2012).
8. By February 2013, implement fully executed Medi-Cal Managed Care Health Plan Contracts:

* Coordinate with CMS to finalize demonstration contract boilerplate  
  (Fall 2012).
* Amend existing Medi-Cal health plan contracts to add LTSS benefits and dual eligible beneficiaries enrollment-related provisions of SB 1008 (Fall 2012).
* Fully execute all contracts (Winter 2012-2013).

1. Develop Interagency Agreement between DHCS and DMHC (September-October 2012):
   * Develop technical assistance guidelines for surveys.
   * Medical surveys to be conducted every three years.
   * Financial audits for CCI health plans every three years.
   * Network adequacy assessments every quarter.
2. Plan and Complete Information Technology (IT) System Changes:
   * Medi-Cal Eligibility Data System (MEDS)/ITSD Enrollment Systems (Winter 2013).
   * Capitation Payment System (CAPMAN) (Winter 2013).
   * Paid Claims Encounter System (Winter 2013).
   * CA-MMIS (Winter 2013).
   * Maximus System changes:
     + Notice release systems (Fall 2012).
     + Enrollment systems (Winter 2013).
   * CDSS Case Management, Information and Payrolling System (CMIPS) II transition (complete in eight counties by May 1, 2013).
3. Implement IHSS Managed Care Coordination:
   * Develop template MOUs between health plans and county social service organizations, and local public authorities (Fall 2012).
   * Provide technical assistance regarding data sharing and care coordination (September-October 2012).
   * Develop fiscal accounting processes (October 2012).
   * Ensure health plan and county MOUs are in place prior to initial enrollment (February 2013).
4. Implement Behavioral Health Managed Care Coordination:
   * Develop template MOU between health plans and county mental health agencies, and county substance use agencies (Fall 2012).
   * Provide technical assistance regarding data sharing and care coordination (Fall 2012).
5. Implement MSSP First Year Managed Care Coordination:
   * Develop draft template contract between health plans and MSSP sites and share with stakeholders (Fall 2012).
   * Finalize contract template (Fall 2012).
   * Develop fiscal accounting processes (Fall/Winter 2012/2013).
6. Implement Ongoing Monitoring and Oversight of Health Plans:
   * Joint CMS/DHCS contract management team monitors compliance with the terms of the three-way contract (upon implementation).
   * DMHC will conduct network adequacy assessments on a quarterly basis, and financial solvency audits and medical surveys on a three-year recurring basis pursuant to the interagency agreement (after implementation).
7. Develop and Implement Quality Measurement and Evaluation Plan:
   * Develop draft quality withhold measures and unified quality metrics  
     (August 10, 2012).
   * Share draft measures for stakeholder review (August 10, 2012).
   * Finalize quality withhold measures for MOU (September, 2012).
   * Develop thresholds for quality measures for health plan contracts (Fall 2012).
   * Develop Rapid-Cycle Quality Improvement Process for CCI (Fall/Winter 2012).
   * Develop Process Indicators Dashboard for CCI (Winter/Spring 2013).
   * Develop Evaluation Plan with CMS and stakeholder input (January 2013).
   * Collect data from health plans (July 2013 and ongoing).
   * Publish Dashboard measure results (July 2013 and ongoing).
   * Review and verify data and publish results (January 2014 and ongoing).
8. Reports to the Legislature:

* Programmatic Transition Plan – September 25, 2012.
* DHCS Readiness Report – First report January 1, 2013.
* DHCS Readiness Report – Second Report March 1, 2013.
* Health Plan Readiness Report – March 1, 2013.
* Annual Duals Enrollment Status, Quality Measures and State Costs Report – May 1, 2013, and annually thereafter.
* Annual LTSS Enrollment Status, Quality Measures and State Costs Report – May 1, 2013, and annually thereafter.
* MSSP waiver Transition Plan – January 1, 2014 (initial report).
* Health Plan Quality Compliance Report – January 10, 2014.
* Annual Plan Audit and Financial Summary Report – June 1, 2014 (first report).
* Annual Demonstration Evaluation Outcome Report – October 1, 2014 (first report).

**PART C – PROCESS FOR ADDRESSING CONSUMER COMPLAINTS**

*SB 1008 requirement: Describe the process for addressing consumer complaints, including the roles and responsibilities of the departments and health plans and how those roles and responsibilities shall be coordinated. The process shall outline required response times and the method for tracking the disposition of complaint cases. The process shall include the use of an ombudsman, liaison, and 24-hour hotline dedicated to assisting Medi-Cal beneficiaries in navigating among the departments and health plans to help ensure timely resolution of complaints.*

The State currently has several avenues for receiving beneficiary complaints about managed care health plans. In accordance with the provisions of SB 1008 in W&I Code §14182.17 (d) (10) (B) (iii) and (E)(vii), DHCS will work with DMHC, other departments, health plans, and stakeholders to develop a coordinated and consistent tracking mechanism for complaints, and will post information on DHCS’ website about the types of issues that arise and any data available on the resolution of complaints. DHCS anticipates a more comprehensive report on the process of posting this information in the next Legislative report.

Additional information is provided below about the current complaint resolution process.

* Beneficiaries who are not satisfied with the quality of care received, experience an error in their medical treatment, or encounter a delay in service, have the option to file a complaint. The beneficiary’s assigned health plan is the primary resource for initiating and managing the complaint process (except for complaints regarding quality of care delivered by an IHSS provider).   
  For complaints other than those concerning IHSS, health plan customer service agents provide personalized assistance. Complaints can also be filed electronically. In either case, the following response times apply to the processing of consumer complaints: Within 30 days of receiving the complaint from the beneficiary, the health plan must respond with a decision. For urgent medical problems, health plans must respond to the beneficiary within three days of receiving the complaint.

In addition to the health plans, beneficiaries have the choice to initiate a complaint directly with the State of California or CMS under the following conditions:

* The beneficiary does not agree with the health plan’s decision.
* The response time has exceeded 30 days (or three days in the case of an urgent medical problem). The beneficiary has an urgent medical condition that does not allow for the health plan to respond within the specified timeframes. In certain cases, beneficiaries may request an independent medical review as part of their complaint filing process.
* For complaints concerning services delivered by an IHSS provider, county social services offices or public authorities are responsible for responding to the beneficiary. As quality of care complaints regarding delivery of IHSS might impair the consumer's ability to remain safely at home, county social services agencies will continue to be the primary contact for these complaints. If the health plan becomes aware of an IHSS quality of care issue, it must make a referral in writing to the county social services agency responsible for addressing these issues in accordance with the terms specified in the MOUs between the health plan and the county social services agency and/or public authority.

The following state agencies currently provide consumer assistance and complaint processing for covered medical services:

* Department of Health Care Services (DHCS)
  + Assists Medi-Cal beneficiaries with complaints about contracted health plans and physicians.
  + MMCD, Office of the Ombudsman.
  + Health Care Options (HCO) is available Monday to Friday, 8AM to 5PM.
    - Provides informing and enrollment assistance to Medi-Cal managed care beneficiaries.
* Department of Managed Health Care (DMHC)
  + Provides comprehensive assistance to health plan enrollees regarding issues or disputes with health plans under DMHC jurisdiction. Available services include toll-free consumer assistance; "quick resolutions" of appropriate disputes directly with health plan representatives; "urgent nurse" reviews of appropriate clinical disputes and prescription medication issues; resolution of medical necessity; experimental/investigational, and emergency services disputes through independent medical review; and review of other consumer grievances. The DMHC Help Center is available Monday to Friday, 8AM to 6PM PST.
* California Department of Aging (CDA)
  + Health Insurance Counseling and Advocacy Program (HICAP) assists Medicare beneficiaries with questions and issues regarding their Medicare benefits.
* California Department of Public Health (CDPH)
  + Assists beneficiaries with complaints about licensed facilities in the State of California, including hospitals, nursing facilities, hospice, clinics, and intermediate care facilities.
  + Consumer complaints are processed through the Health Facilities Consumer Information System (HFCIS) website.
* California Department of Social Services (CDSS)
  + Assists with complaints regarding county-based adult residential services (residential care facilities and board and care homes).
  + Assists with complaints from beneficiaries and providers about IHSS.
  + CDSS is available by phone, Monday to Friday, 8AM to 5PM PST.
  + Manages the State Fair Hearing process for Medi-Cal and IHSS.
* Medical Board of California
  + Assists with complaints concerning physicians.
  + The Department of Consumer Affairs (DCA) is available by phone, Monday to Friday, 8AM to 5PM PST.

The following federal agency provides consumer assistance and complaint processing for Medicare services:

* Centers for Medicare and Medicaid Services (CMS)
  + Assists beneficiaries with complaints about hospital (inpatient and outpatient) services, mental health services, and other services covered by Medicare.
  + CMS Customer Service Center is available 24 hours per day, 7 days per week.

See Appendix D for a contact list for State of California agencies that process consumer complaints.

**ParT d – stakeholder ENGAGEMENT[[2]](#footnote-3)**

*SB 1008 requirement: A description of how stakeholders were included in the various phases of the planning process to formulate the Transition Plan and how their feedback will be taken into consideration after transition activities begin.*

Stakeholder Meetings:

Starting in April 2010, DHCS supported a broad stakeholder engagement process to inform the design and implementation of the CCI and the Demonstration. DHCS has organized numerous opportunities to learn directly from beneficiaries about their health care experiences, needs, preferences and reactions to proposed system changes.

Additionally, DHCS has organized dozens of stakeholder meetings focused on specific topics pertaining to the CCI. DHCS’ Legislative and Governmental Affairs staff relayed all critical information to key legislative staff members. DHCS released “save-the-date” meeting announcements, meeting invitations, and other related meeting materials via an email distribution list and also utilized the DHCS website [www.dhcs.ca.gov](http://www.dhcs.ca.gov). DHCS also posted this information on an additional website, [www.calduals.org](http://www.calduals.org). This stakeholder distribution list has grown throughout the process, as DHCS received numerous requests from individuals interested in the issues. As of late September 2012, over 2,300 individuals and organizations are on the Cal Duals email distribution list.

As required in SB 1008, DHCS hosted two stakeholder meetings during the period following production of a draft of the implementation plan and before submission of the plan to the Legislature.

The first meeting was held on August 29, 2012. The meeting had an in-person and   
call-in option. Over 60 people attended in person in Sacramento including beneficiaries, advocates, county staff, and health plan representatives. Over 200 people participated via the call-in option.

The second stakeholder conference call was held September 4, 2012, with over 150 participants.

Both meetings were similar in format. DHCS led an overview of the draft transition plan, with the remaining time allotted for questions from stakeholders.

DHCS posted a draft of this plan for public comment. DHCS received written comments from 45 entities including individual dual eligible beneficiaries, advocacy groups, health plans, providers, associations, and county agencies. All comments will be posted at [www.calduals.org](http://www.calduals.org).

Website

To facilitate easy public access to information about the dual eligible demonstration project and CCI, DHCS developed a new website dedicated to the California Demonstration, [www.calduals.org](http://www.calduals.org). The focus of this effort is to enable a transparent process and foster constructive, two-way dialogue among stakeholders.

Email Inbox:

DHCS created two dedicated email addresses to receive written stakeholder comments on the Demonstration: [duals@dhcs.ca.gov](mailto:duals@dhcs.ca.gov) and [info@calduals.org](mailto:info@calduals.org). DHCS staff members review the inbox daily and refer comments to the appropriate person for response.

Working with Stakeholders after the Transition is Underway

DHCS has obtained valuable input from stakeholders in this initial transition phase, and it will continue to engage stakeholders throughout the implementation and beyond. As previously mentioned, some of the recommendations represent efforts that DHCS cannot immediately implement and must address in future phases; therefore, DHCS expects to continue stakeholder engagement on an ongoing basis.

DHCS commits to working with stakeholders to keep abreast of how the program and its services are functioning and identify needed corrections or improvements. DHCS created six work groups dedicated to specific areas of the demonstration. As the project moves forward, DHCS will continuously reassess the input and strengths of these existing stakeholder groups. DHCS acknowledges the importance of stakeholder input regarding all aspects of Medi-Cal services and business practices and commits to having ongoing communication with its external partners.

Stakeholder input has shown to be an invaluable part of this process, bringing to light concepts and issues worthy of further investigation. Stakeholder comments have been sought at various points of this process and all comments have been posted to the DHCS website: <http://www.dhcs.ca.gov/Pages/DualsDemonstration.aspx>. DHCS, CDSS, CDA, the Department of Rehabilitation (DOR) and DMHC will continue to collaborate on all issues related to the CCI.


**APPENDIX A**

**CCI Timeline**

**Coordinated Care Initiative - Duals Demonstration project Major Milestones and Timelines for 2012-2013**

**APPENDIX B**

**Health Plan Monitoring and Oversight**

****

**APPENDIX C**

**Consumer Complaints**

**Additional Information for Section C**

Sources and contact information for State of California agencies that process health care-related consumer complaints.

**California Department of Aging (CDA)**

<http://www.aging.ca.gov/>

<http://www.aging.ca.gov/Programs/call_for_services.asp#LTC>

By County: <http://www.aging.ca.gov/ProgramsProviders/AAA/AAA_Listing.asp>

**HICAP/Department of Aging**

800-434-0222

<https://www.aging.ca.gov/hicap/countyList.aspx>

**California Health and Human Services Agency/Office of the Patient Advocate (OPA)**

<http://www.opa.ca.gov/>

1-866-466-8900

**California Department of Public Health (CDPH)**

<http://www.cdph.ca.gov/Pages/DEFAULT.aspx>

<https://hfcis.cdph.ca.gov/LongTermCare/ConsumerComplaint.aspx>

Licensing/certification: <http://www.cdph.ca.gov/programs/LnC/Pages/LnC.aspx>

(916) 558-1784

**California Department of Managed Health Care (DMHC)**

888-466-2219

(7A-7PM, M-F, excluding holidays)

<http://www.dmhc.ca.gov/default.aspx>

<http://www.dmhc.ca.gov/aboutthedmhc/gen/gen_contactus.aspx>

\*referrals to department of labor (jurisdiction over self-insured plans; federal COBRA), HCO, CDI, Medi-Cal hotline (800)541-5555, CMS – HICAP (800)434-0222

**California Department of Insurance (CDI)**

<http://www.insurance.ca.gov/> 800-927-4357

**California Department of Consumer Affairs (DCA), Medical Board of California (MBC)**

<http://www.dca.ca.gov/>

<http://www.mbc.ca.gov/consumer/complaint_info.html>

800-633-2322

**California Department of Social Services (CDSS)**

<http://www.ccld.ca.gov/PG400.htm>

<http://www.dss.cahwnet.gov/cdssweb/default.htm>

800-952-5253

**California Department of State Hospitals (DSH) (Formerly Department of Mental Health)**

<http://www.dsh.ca.gov/>

**Health Facilities Consumer Information System**

<http://www.cdph.ca.gov/data/informatics/tech/Pages/HFCIS.aspx>

The Health Facilities Consumer Information System (HFCIS) website is made available by the California Department of Public Health (CDPH), Center for Health Care Quality (CHCQ), Licensing and Certification Program (L&C) to provide immediate access to information about L&C’s licensed long-term care facilities and hospitals throughout California.

**DHCS/MMCD – Health Care Operations (HCO)**

<http://www.healthcareoptions.dhcs.ca.gov/HCOCSP/Home/default.aspx>

800-430-4263

**DHCS/MMCD – Office of the Ombudsman**

<http://www.dhcs.ca.gov/services/medi-cal/Pages/MMCDOfficeoftheOmbudsman.aspx>

888-452-8609

**DHCS-MMCD**

<http://www.dhcs.ca.gov/services/Pages/Medi-CalManagedCare.aspx>

916-449-5000

**DHCS – Main website**

<http://www.dhcs.ca.gov/>

<http://www.dhcs.ca.gov/services/medi-cal/Pages/default.aspx>

**Audits and Investigations**

DHCS/A&I

<http://www.dhcs.ca.gov/individuals/Pages/auditsinvestigations.aspx>

**CMS**

<http://www.medicare.gov>

800-633-4227 or 1-800-MEDI-CAID

Medicare Nursing Home Finder

[www.medicare.gov/nursinghomecompare/search.aspx?bhcp=1](http://www.medicare.gov/nursinghomecompare/search.aspx?bhcp=1)

**CMS/Quality Improve Organization – Hospitals, Doctors.**

Quality Improve Organization

CMS Health Services Advisory Group

<http://hsag.com/home.aspx>

(CA = 866-800-8749, 8-4:30 PST, M-F).

**CMS/California Department of Public Health (CDPH) - Nursing Facilities.**

State Survey Agency (CDPH = 800-236-9747, 8am-5pm, M-F).

State Health Insurance Assistance Programs (SHIPs)

(CA = 800-434-0222, 8am-5pm PST, M-F)

**APPENDIX D**

**Legislative Reporting Requirements**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Report Name** | **SB 1008 Citation** | **Reporting Requirements** | **Frequency** | **Initial Report Date[[3]](#footnote-4)** |
| Evaluation Outcome Report | Sec. 1, W&I 14132.275(m) | The department shall conduct an evaluation, in partnership with CMS, to assess outcomes and the experience of dual eligibles in these demonstration sites and shall provide a report to the Legislature after the first full year of demonstration operation, and annually thereafter. | Annual | October 1, 2014 |
| Duals Enrollment, Quality Measure and Cost Report | Sec. 1, W&I 14132.275(q)(1) | Beginning with the May Revision to the 2013–14 Governor’s Budget, and annually thereafter, the department shall report to the Legislature on the enrollment status, quality measures, and state costs of the actions taken pursuant to this section. | Annual | May 1, 2013 |
| Health plan quality compliance report | Sec. 4, W&I 14182.17(d)(8)(C) | Effective January 10, 2014, and for each subsequent year of the demonstration project authorized under Section 14132.275, provide a report to the Legislature describing the degree to which Medi-Cal managed care health plans in counties participating in the demonstration project have fulfilled the quality requirements, as set forth in the health plan contracts. | Annual | January 10, 2014 |
| Plan Audit and Financial Examination Summary Reports | Sec. 4, W&I 14182.17(d)(8)(D) | Effective June 1, 2014, and for each subsequent year of the demonstration project authorized by Section 14132.275, provide a joint report, from the Department of Health Care Services and from the Department of Managed Health Care, to the Legislature summarizing information from both of the following:  (i) The independent audit report required to be submitted annually to the Department of Managed Health Care by managed care health plans participating in the demonstration project authorized by Section 14132.275.  (ii) Any routine financial examinations of managed care health plans operating in the demonstration project authorized by Section 14132.275  that have been conducted and completed for the previous calendar year by the Department of Managed Health Care and the department. | Annual | June 1, 2014 |
| Programmatic Transition Plan | Sec. 4, W&I 14182.17(d)(10)(B) | Together with the State Department of Social Services, the California Department of Aging, and the Department of Managed Health Care, in consultation with stakeholders, develop a programmatic Transition Plan, and submit that plan to the Legislature within 90 days of the effective date of this section. | One time based on the June 27, 2012 bill chapter date | October 1, 2012 |
| Health Plan Readiness Report | Sec. 4, W&I 14182.17(d)(10)(D) | No later than 90 days prior to the initial plan enrollment date of the demonstration project, assess and report on the readiness of the managed care health plans to address the unique needs of dual eligible beneficiaries and Medi-Cal only seniors and persons with disabilities pursuant to the applicable readiness evaluation criteria and requirements set forth in paragraphs (1) to (8), inclusive, of subdivision (b) of Section 14087.48. The report shall also include an assessment of the readiness of the managed care health plans in each county participating in the demonstration project to have met the requirements set forth in paragraphs (1) to (9). | One time | March 1, 2013 |
| Program Readiness Report | Sec. 4, W&I 14182.17(d)(10)(E) | The Department of Health Care Services shall submit two reports to the Legislature, with the first report submitted five months prior to the commencement date of enrollment and the second report submitted three months prior to the commencement date of enrollment, that describe the status of all of the following readiness criteria and activities that the department shall complete. | 2 reports | January 1, 2013  March 1, 2013 |
| MSSP waiver Transition Plan | Sec. 6, W&I 14186.3(b)(4)(B)(C) | No later than January 1, 2014, the department, in consultation with the California Department of Aging and the Department of Managed Health Care, and with stakeholder input, shall submit a Transition Plan to the Legislature to describe how subparagraph (A) shall be implemented. The plan shall incorporate the principles of the MSSP in the managed care benefit, and shall include provisions to ensure seamless transitions and continuity of care. Managed care health plans shall, in partnership with local MSSP providers, conduct a local stakeholder process to develop recommendations that the department shall consider when developing the Transition Plan. | 2 Reports | January 1, 2014  90-days prior to implementation |
| LTSS Enrollment, quality measure and cost report | Sec. 6, W&I 14186.4(g) | Beginning with the May Revision to the 2013–14 Governor’s Budget, and annually thereafter, the department shall report to the Legislature on the enrollment status, quality measures, and state costs of the actions taken pursuant to this article. | Annual | May 1, 2013 |

**APPENDIX E**

**CCI Beneficiary Protections Statute**

W&I Code Section 14182.17

(d) Before the department contracts with managed care health plans or Medi-Cal providers to furnish Medi-Cal benefits and services pursuant to subdivision (b), the department shall do all of the following:

(1) Ensure timely and appropriate communications with beneficiaries as follows:

(A) At least 90 days prior to enrollment, inform dual eligible beneficiaries through a notice written at not more than a 6th-grade reading level that includes, at a minimum, how the Medi-Cal system of care will change, when the changes will occur, and who they can contact for assistance with choosing a managed care health plan or with problems they encounter.

(B) Develop and implement an outreach and education program for beneficiaries to inform them of their enrollment options and rights, including specific steps to work with consumer and beneficiary community groups.

(C) Develop, in consultation with consumers, beneficiaries, and other stakeholders, an overall communications plan that includes all aspects of developing beneficiary notices. (D) Ensure that managed care health plans and their provider networks are able to provide communication and services to dual eligible beneficiaries in alternative formats that are culturally, linguistically, and physically appropriate through means, including, but not limited to, assistive listening systems, sign language interpreters, captioning, written communication, plain language, and written translations.

(E) Ensure that managed care health plans have prepared materials to inform beneficiaries of procedures for obtaining Medi-Cal benefits, including grievance and appeals procedures, that are offered by the plan or are available through the Medi-Cal program.

(F) Ensure that managed care health plans have policies and procedures in effect to address the effective transition of beneficiaries from Medicare Part D plans not participating in the demonstration project. These policies shall include, but not be limited to, the transition of care requirements for Medicare Part D benefits as described in Chapters 6 and 14 of the Medicare Managed Care Manual, published by CMS, including a determination of which beneficiaries require information about their transition supply, and, within the first 90 days of coverage under a new plan, provide for a temporary fill when the beneficiary requests a refill of a non formulary drug.

(G) Contingent upon available private or public funds other than moneys from the General Fund, contract with community-based, nonprofit consumer, or health insurance assistance organizations with expertise and experience in assisting dual eligible beneficiaries in understanding their health care coverage options.

(H) Develop, with stakeholder input, informing and enrollment materials and an enrollment process in the demonstration site counties. The department shall ensure all of the following prior to implementing enrollment:

(i) Enrollment materials shall be made public at least 60 days prior to the first mailing of notices to dual eligible beneficiaries, and the department shall work with stakeholders to incorporate public comment into the materials.

(ii) The materials shall be in a not more than sixth grade reading level and shall be available in all the Medi-Cal threshold languages, as well as in alternative formats that are culturally, linguistically, and physically appropriate. For in-person enrollment assistance, disability accommodation shall be provided, when appropriate, through means including, but not limited to, assistive listening systems, sign language interpreters, captioning, and written communication.

(iii) The materials shall plainly state that the beneficiary may choose fee-for-service Medicare or Medicare Advantage, but must return the form to indicate this choice, and that if the beneficiary does not return the form, the state shall assign the beneficiary to a plan and all Medicare and Medi-Cal benefits shall only be available through that plan.

(iv) The materials shall plainly state that the beneficiary shall be enrolled in a Medi-Cal managed care health plan even if he or she chooses to stay in fee-for-service Medicare.

(v) The materials shall plainly explain all of the following:

(I) The plan choices.

(II) Continuity of care provisions.

(III) How to determine which providers are enrolled in each plan.

(IV) How to obtain assistance with the choice forms.

(vi) The enrollment contractor recognizes, in compliance with existing statutes and regulations, authorized representatives, including, but not limited to, a caregiver, family member, conservator, or a legal services advocate, who is recognized by any of the services or programs that the person is already receiving or participating in.

(I) Make available to the public and to all Medi-Cal providers copies of all beneficiary notices in advance of the date the notices are sent to beneficiaries. These copies shall be available on the department's Internet Web site.

(2) Require that managed care health plans perform an assessment process that, at a minimum, does all of the following:

(A) Assesses each new enrollee's risk level and needs by performing a risk assessment process using means such as telephonic, Web-based, or in-person communication, or review of utilization and claims processing data, or by other means as determined by the department, with a particular focus on identifying those enrollees who may need long-term services and supports. The risk assessment process shall be performed in accordance with all applicable federal and state laws.

(B) Assesses the care needs of dual eligible beneficiaries and coordinates their

Medi-Cal benefits across all settings, including coordination of necessary services within, and, when necessary, outside of the managed care health plan's provider network.

(C) Uses a mechanism or algorithm developed by the managed care health plan pursuant to paragraph (7) of subdivision (b) of Section 14182 for risk stratification of members.

(D) At the time of enrollment, applies the risk stratification mechanism or algorithm approved by the department to determine the health risk level of members.

(E) Reviews historical Medi-Cal fee-for-service utilization data and Medicare data, to the extent either is accessible to and provided by the department, for dual eligible beneficiaries upon enrollment in a managed care health plan so that the managed care health plans are better able to assist dual eligible beneficiaries and prioritize assessment and care planning.

(F) Analyzes Medicare claims data for dual eligible beneficiaries upon enrollment in a demonstration site pursuant to Section 14132.275 to provide an appropriate transition process for newly enrolled beneficiaries who are prescribed Medicare Part D drugs that are not on the demonstration site's formulary, as required under the transition of care requirements for Medicare Part D benefits as described in Chapters 6 and 14 of the Medicare Managed Care Manual, published by CMS.

(G) Assesses each new enrollee's behavioral health needs and historical utilization, including mental health and substance use disorder treatment services.

(H) Follows timeframes for reassessment and, if necessary, circumstances or conditions that require redetermination of risk level, which shall be set by the department.

(3) Ensure that the managed care health plans arrange for primary care by doing all of the following:

(A) Except for beneficiaries enrolled in the demonstration project pursuant to Section 14132.275, forgo interference with a beneficiary's choice of primary care physician under Medicare, and not assign a full-benefit dual eligible beneficiary to a primary care physician unless it is determined through the risk stratification and assessment process that assignment is necessary, in order to properly coordinate the care of the beneficiary or upon the beneficiary's request.

(B) Assign a primary care physician to a partial-benefit dual eligible beneficiary receiving primary or specialty care through the Medi-Cal managed care plan.

(C) Provide a mechanism for partial-benefit dual eligible enrollees to request a specialist or clinic as a primary care provider if these services are being provided through the Medi-Cal managed care health plan. A specialist or clinic may serve as a primary care provider if the specialist or clinic agrees to serve in a primary care provider role and is qualified to treat the required range of conditions of the enrollees.

(4) Ensure that the managed care health plans perform, at a minimum, and in addition to, other statutory and contractual requirements, care coordination, and care management activities as follows:

(A) Reflect a member-centered, outcome-based approach to care planning, consistent with the CMS model of care approach and with federal Medicare requirements and guidance.

(B) Adhere to a beneficiary's determination about the appropriate involvement of his or her medical providers and caregivers, according to the federal Health Insurance Portability and Accountability Act of 1996 (Public Law 104-191).

(C) Develop care management and care coordination for the beneficiary across the medical and long-term services and supports care system, including transitions among levels of care and between service locations.

(D) Develop individual care plans for higher risk beneficiaries based on the results of the risk assessment process with a particular focus on long-term services and supports.

(E) Use nurses, social workers, the beneficiary's primary care physician, if appropriate, and other medical professionals to provide care management and enhanced care management, as applicable, particularly for beneficiaries in need of or receiving long-term services and supports.

(F) Consider behavioral health needs of beneficiaries and coordinate those services with the county mental health department as part of the beneficiary's care management plan when appropriate.

(G) Facilitate a beneficiary's ability to access appropriate community resources and other agencies, including referrals as necessary and appropriate for behavioral services, such as mental health and substance use disorders treatment services.

(H) Monitor skilled nursing facility utilization and develop care transition plans and programs that move beneficiaries back into the community to the extent possible. Plans shall monitor and support beneficiaries in the community to avoid further institutionalization.

(5) Ensure that the managed care health plans comply with, at a minimum, and in addition to other statutory and contractual requirements, network adequacy requirements as follows:

(A) Provide access to providers that comply with applicable state and federal law, including, but not limited to, physical accessibility and the provision of health plan information in alternative formats.

(B) Meet provider network adequacy standards for long-term services and supports that the department shall develop.

(C) Maintain an updated, accurate, and accessible listing of a provider's ability to accept new patients, which shall be made available to beneficiaries, at a minimum, by phone, written material, and the Internet, and in accessible formats, upon request.

(D) Monitor an appropriate provider network that includes an adequate number of accessible facilities within each service area.

(E) Contract with and assign patients to safety net and traditional providers as defined in subdivisions (hh) and (jj), respectively, of Section 53810 of Title 22 of the California Code of Regulations, including small and private practice providers who have traditionally treated dual eligible patients, based on available medical history to ensure access to care and services. A managed care health plan shall establish participation standards to ensure participation and broad representation of traditional and safety net providers within a service area.

(F) Maintain a liaison to coordinate with each regional center operating within the plan's service area to assist dual eligible beneficiaries with developmental disabilities in understanding and accessing services and act as a central point of contact for questions, access and care concerns, and problem resolution.

(G) Maintain a liaison and provide access to out-of-network providers, for up to 12 months, for new members enrolled under Sections 14132.275 and 14182.16 who have an ongoing relationship with a provider, if the provider will accept the health plan's rate for the service offered, or for nursing facilities and Community-Based Adult Services, or the applicable Medi-Cal fee-for-service rate, whichever is higher, and the managed care health plan determines that the provider meets applicable professional standards and has no disqualifying quality of care issues in accordance with guidance from the department, including all-plan letters. A partial-benefit dual eligible beneficiary enrolled in Medicare Part A who only receives primary and specialty care services through a Medi-Cal managed care health plan shall be able to receive these Medi-Cal services from an out-of-network Medi-Cal provider for 12 months after enrollment. This subparagraph shall not apply to out-of-network providers that furnish ancillary services.

(H) Assign a primary care physician who is the primary clinician for the beneficiary and who provides core clinical management functions for partial-benefit dual eligible beneficiaries who are receiving primary and specialty care through the Medi-Cal managed care health plan.

(I) Employ care managers directly or contract with nonprofit or proprietary organizations in sufficient numbers to provide coordinated care services for long-term services and supports as needed for all members.

(6) Ensure that the managed care health plans address medical and social needs as follows:

(A) Offer services beyond those required by Medicare and Medi-Cal at the managed care health plan's discretion.

(B) Refer beneficiaries to community resources or other agencies or needed medical or social services or items outside the managed care health plan's responsibilities.

(C) Facilitate communication among a beneficiary's health care and personal care providers, including long-term services and supports and behavioral health providers when appropriate.

(D) Engage in other activities or services needed to assist beneficiaries in optimizing their health status, including assisting with self-management skills or techniques, health education, and other modalities to improve health status.

(E) Facilitate timely access to primary care, specialty care, medications, and other health services needed by the beneficiary, including referrals to address any physical or cognitive barriers to access.

(F) Utilize the most recent common procedure terminology (CPT) codes, modifiers, and correct coding initiative edits.

(7) (A) Ensure that the managed care health plans provide, at a minimum, and in addition to other statutory and contractual requirements, a grievance and appeal process that does both of the following:

(i) Provides a clear, timely, and fair process for accepting and acting upon complaints, grievances, and disenrollment requests, including procedures for appealing decisions regarding coverage or benefits, as specified by the department. Each managed care health plan shall have a grievance process that complies with Section 14450, and Sections 1368 and 1368.01 of the Health and Safety Code.

(ii) Complies with a Medicare and Medi-Cal grievance and appeal process, as applicable. The appeals process shall not diminish the grievance and appeals rights of IHSS recipients pursuant to Section 10950.

(B) In no circumstance shall the process for appeals be more restrictive than what is required under the Medi-Cal program.

(8) Monitor the managed care health plans' performance and accountability for provision of services, in addition to all other statutory and contractual monitoring and oversight requirements, by doing all of the following:

(A) Develop performance measures that are required as part of the contract to provide quality indicators for the Medi-Cal population enrolled in a managed care health plan and for the dual eligible subset of enrollees. These performance measures may include measures from the Healthcare Effectiveness Data and Information Set or measures indicative of performance in serving special needs populations, such as the National Committee for Quality Assurance structure and process measures, or other performance measures identified or developed by the department.

(B) Implement performance measures that are required as part of the contract to provide quality assurance indicators for long-term services and supports in quality assurance plans required under the plans' contracts. These indicators shall include factors such as affirmative member choice, increased independence, avoidance of institutional care, and positive health outcomes. The department shall develop these quality assurance indicators in consultation with stakeholder groups.

(C) Effective January 10, 2014, and for each subsequent year of the demonstration project authorized under Section 14132.275, provide a report to the Legislature describing the degree to which Medi-Cal managed care health plans in counties participating in the demonstration project have fulfilled the quality requirements, as set forth in the health plan contracts.

(D) Effective June 1, 2014, and for each subsequent year of the demonstration project authorized by Section 14132.275, provide a joint report, from the department and from the Department of Managed Health Care, to the Legislature summarizing information from both of the following:

(i) The independent audit report required to be submitted annually to the Department of Managed Health Care by managed care health plans participating in the demonstration project authorized by Section 14132.275.

(ii) Any routine financial examinations of managed care health plans operating in the demonstration project authorized by Section 14132.275 that have been conducted and completed for the previous calendar year by the Department of Managed Health Care and the department.

(E) Monitor on a quarterly basis the utilization of covered services of beneficiaries enrolled in the demonstration project pursuant to Section 14132.275 or receiving

long-term services and supports pursuant to Article 5.7 (commencing with Section 14186).

(9) Develop requirements for managed care health plans to solicit stakeholder and member participation in advisory groups for the planning and development activities relating to the provision of services for dual eligible beneficiaries.

(10) Submit to the Legislature the following information:

(A) Provide, to the fiscal and appropriate policy committees of the Legislature, a copy of any report submitted to CMS pursuant to the approved federal Waiver described in Section 14180.

(B) Together with the State Department of Social Services, the California Department of Aging, and the Department of Managed Health Care, in consultation with stakeholders, develop a programmatic transition plan, and submit that plan to the Legislature within 90 days of the effective date of this section. The plan shall include, but is not limited to, the following components:

(i) A description of how access and quality of service shall be maintained during and immediately after implementation of these provisions, in order to prevent unnecessary disruption of services to beneficiaries.

(ii) Explanations of the operational steps, timelines, and key milestones for determining when and how the components of paragraphs (1) to (9), inclusive, shall be implemented.

(iii) The process for addressing consumer complaints, including the roles and responsibilities of the departments and health plans and how those roles and responsibilities shall be coordinated. The process shall outline required response times and the method for tracking the disposition of complaint cases. The process shall include the use of an ombudsman, liaison, and 24-hour hotline dedicated to assisting Medi-Cal beneficiaries navigate among the departments and health plans to help ensure timely resolution of complaints.

(iv) A description of how stakeholders were included in the various phases of the planning process to formulate the transition plan, and how their feedback shall be taken into consideration after transition activities begin.

(C) The department, together with the State Department of Social Services, the California Department of Aging, and the Department of Managed Health Care, convene and consult with stakeholders at least twice during the period following production of a draft of the implementation plan and before submission of the plan to the Legislature. Continued consultation with stakeholders shall occur on an ongoing basis for the implementation of the provisions of this section.

**APPENDIX F**

**Acronyms**

|  |  |
| --- | --- |
| AG | Advisory Group |
| AIS | Aging and Independence Services |
| AOA | Agency on Aging |
| CalHR | California Office of Human Resources |
| CBAS | Community-Based Adult Services |
| CCI | Coordinated Care Initiative |
| CDA | California Department of Aging |
| CDI | California Department of Insurance |
| CDMH | California Department of Mental Health |
| CDPH | California Department of Public Health |
| CDSS | California Department of Social Services |
| CHHS | California Health and Human Services Agency |
| CMIPS | Case Management, Information and Payrolling System |
| CMS | Centers for Medicare and Medicaid |
| CPT | Common Procedure Terminology |
| DCA | Department of Consumer Affairs |
| Demonstration | Dual Eligible Demonstration Project |
| DHCS | Department of Health Care Services |
| DME | Durable Medical Equipment |
| DMHC | Department of Managed Health Care |
| DOR | Department of Rehabilitation |
| D-SNP | Dual Eligible Special Needs Plan |
| DSH | Department of State Hospitals (formerly Department of Mental Health) |
| EQRO | External Quality Review Organization |
| ESRD | End Stage Renal Disease |
| HCBS | Home- and Community-Based Services |
| HCDS | Health Care Delivery Systems |
| HCO | Health Care Options |
| HFCIS | Health Facilities Consumer Information System |
| HICAP | Health Insurance Counseling and Advocacy Program |
| HPSM | Health Plan of San Mateo |
| ICT | Interdisciplinary Care Teams |
| IHSS | In-Home Supportive Services |
| IPA | Independent Physician Associations |
| IT | Information Technology |
| ITSD | Information Services Technology Division |
| LTSS | Long Term Services and Supports |
| MBC | Medical Board of California |
| MEDS | Medi-Cal Eligibility Data System |
| MMCD | Medi-Cal Managed Care Division |
| MOU | Memorandum of Understanding |
| MSSP | Multipurpose Senior Services Program |
| NCQA | National Committee for Quality Assurance |
| NEMT | Non-Emergency Medical Transportation |
| OPA | Office of the Patient Advocate |
| PACE | Program of All-Inclusive Care for the Elderly |
| PCP | Primary Care Physician |
| RFS | Request for Solutions |
| SB | Senate Bill |
| SPDs | Seniors and Persons With Disabilities |
| Waiver | Federal Bridge to Reform 1115 Waiver |
| waiver | (lower case refers to all other waivers) |

1. SB 1036 also authorizes the creation of a Statewide Public Authority for In Home Supportive Services (IHSS) collective bargaining and a county Maintenance of Effort for funding IHSS. However, statute does not require that these provisions be included in the scope of this report. [↑](#footnote-ref-2)
2. See Appendix E for the DHCS timeline related to stakeholder participation and transition plan development. [↑](#footnote-ref-3)
3. Initial Report Date is based on March 1, 2013 state date for Mandatory Medi-Cal enrollment for   
   Medi-Cal only benefits and June 1, 2013 start date for the Demonstration Project [↑](#footnote-ref-4)