## 24 Month
Press TAB to move to input areas. Press UP or DOWN ARROW in column A to read through the document.
CalHEERS
CalHEERS 2023-2024 CRs / Initiatives
CR # | TITLE | OWNER | BRIEF DESCRIPTION | RELEASE | AB1296 Category | 24 Mo Business Goal | Prioritization Category | NOV 21 Advocate Comments | NOV 21 Responses | Advocate Follow-up Response
189274 | Update Incarceration Functionality for MAGI Medi-Cal | DHCS | CalHEERS will no longer “Pend” MAGI Medi-Cal eligibility when verification of incarcerated status is received from SSA and all other program requirements are met. Instead, CalHEERS shall simply determine this population as “Eligible”. CalHEERS will also determine this population as “Eligible” if an Admin verification of incarceration is received, regardless of whether the verification is passed or failed. Also, CalHEERS will need to have functionality to discontinue MAGI Medi-Cal eligibility when communicated by SAWS at the end of a suspension period, per incarceration policy. There shall be no change to incarceration verification functionality or the verification status sent to SAWS, as this information is still needed for County (and Maximus for MCAP/CCHIP) case management purposes. | 22.9 | Partner Reconciliation Improvements | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR & Warranty
TBD | Notices CR for 23.12 | Shared | The objective of this initiative is to update notice language to align with system changes made in this release within CalHEERS. | 23.12 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
147420 | Administrator Search Enhancements | Shared | This CR will begin the redesign of the Admin CalHEERS portal search screen to improve usability and provide more details for our admin users. With this change, CalHEERS will introduce enhanced case searching functionality. | 23.2 | Worker Productivity Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Innovation & Continuous Improvement
165890 | ROP Batch - Phase II | Covered CA | In Release 21.2, Phase I will be released. This CR is a placeholder to allow for any adjustments that may be needed to the system to ensure the efficient operation of the ROP Batch post that release. | 23.2 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR & Warranty
183098 | Placeholder for Federal Annual Updates | Shared | The CR is to address the changes in the New Benefit and Payment Parameters (NBPP) for the year 2022. | 23.2 | Program Updates | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | New Policy & Legislative Changes
189273 | Implement Eligibility Functionality for Family Planning, Access, Care and Treatment (Family PACT) Program in CalHEERS | DHCS | CalHEERS shall add the Family PACT application and eligibility process to the CalHEERS Portal and BRE, automate integration with MEDS, automate referrals for other IAP programs, and provide appropriate notices and messaging to Family PACT clients and Family PACT providers. Family PACT program aid code 8H is not considered MEC and shall not impact current CalHEERS functionality for determining eligibility for IAP programs. | 23.2 | New Programs |  | Enhancement CR & Warranty
TBD | Notices CR for 23.2 | Shared | The objective of this initiative is to update notice language to align with system changes made in this release within CalHEERS. | 23.2 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
183209 | Eligibility Notice Generation Enhancement – Phase 2 | Shared | Phase 2: The purpose of this initiative is to enhance the CalNOD01 noticing system that lives within the business rules engine that will have the ability to effectively, efficiently, and accurately notice consumers about their eligibility determination. | 23.6 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Innovation & Continuous Improvement
TBD | Notices CR for 23.6 | Shared | The objective of this initiative is to update notice language to align with system changes made in this release within CalHEERS. | 23.6 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
61104 | Implement Plan Dependent Rules | Covered CA | Update CalHEERS to implement the enforcement of plan dependent rules. CalHEERS enrollment grouping rules should include plan dependency definitions, by only allowing Married spouses, Registered domestic partners, Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners, Disabled adult children of any age (including 26 or above) and Siblings under the age of 26 to enroll in the same Covered CA plan. CalHEERS should also prevent enrollment of over-age dependents unless they meet the “disabled child” exception. | 23.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR & Warranty
88353 | Implementation of GI PCP Selection Module and Provider Map | Covered CA | The objective of this initiative is to add functionality to the existing Provider Directory for physicians designated as Primary Care Providers (PCPs). The new functionalities are part of the GI PCP Module: 1) PCP Assignment for QHP 2 ) Network Density Tools: This feature will allows consumers to search an area where they desire coverage and determine in real-time how many providers are active in an area for a health plan issuer. | 23.9 | Partner Interface Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR & Warranty
161090 | Value Based Insurance Design | Covered CA | Covered California would like to implement a Value Based Insurance Design pilot in select regions. Consumers in select regions will be enrolled in VBID plan designs. All consumers in the region will participate. There will be opportunity to opt in or out of this pilot. | 23.9 | New Programs | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Innovation & Continuous Improvement
166033 | Prospective Premiums for Renewals | Covered CA | Problem Statement: Currently the CCA Renewal notice does not include premium amounts for the renewal year. The carriers send consumers versions which include their current year's premium and the renewal year's premium, but without the APTC details. This can cause consumer panic when premiums rise, as they don't have a clear understanding that their APTC amount will likely go up with it. When sending out the Renewal letters each year, CCA would like them to include a prospective gross and net premium amount, which will require a prospective APTC amount. Intended Outcome: Better inform consumers about what their next year's APTC and premium amounts will be if they keep their same plan. | 23.9 | Report a Change (RAC)/Special Enrollment Period (SEP) | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR & Warranty
180018 | Spanish URLs for CalHEERS Portal Login and Shop & Compare | Shared | Covered CA is seeing a high drop rate of Spanish Consumers ending their sessions after landing on the English version of CalHEERS Portal Login (https://apply.coveredca.com/apspahbx/ahbx.portal) and Shop & Compare (https://apply.coveredca.com/lw-shopandcompare/) based on analyzing the stats collected from Google Analytics. Covered CA has determined that most Spanish Consumers are clicking on URLs provided by Covered CA Marketing campaigns and Covered CA partners. Covered CA would like dedicated Spanish URLs to direct Spanish Consumers to CalHEERS Portal Login and Shop & Compare and automatically select Spanish language. Spanish Consumers will land on CalHEERS Portal Login and Shop and Compare pages in Spanish when Consumer clicks on hyperlink provided by Covered CA Marketing campaigns and Covered CA Partners. | 23.9 | User Experience Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Innovation & Continuous Improvement
TBD | 2024 Renewals Placeholder CR | Shared | Placeholder for annual renewals CR Annual renewals related system enhancements | 23.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
TBD | Notices CR for 23.9 | Shared | The objective of this initiative is to update notice language to align with system changes made in this release within CalHEERS. | 23.9 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
183100 | SEP Dropdown and Workflow - Phase II | Shared | Problem Statement: The SEP reasons in the portal is not a comprehensive list that adheres to the federal regulations. The page does not have helpful information and causes confusion to the consumers in the Intake/RAC flow. Intended Outcome: The SEP reasons in the portal needs to be more intuitive and more helpful to the users: 1. Update and add to the available SEP reasons 2. Update and add to the business rules for each existing and new SEP reason 3. Dynamically display the SEP reasons in the drop down list based on the user role and application mode 4. Update the SEP page language 5. Allow users to capture multiple SEP reasons. System to determine the most advantageous SEP reason. 6. Capture SEP reasons at the household vs individual level. 7. Update eHIT/SAWS accordingly | 24.2 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
186216 | CalWIN Conversion to CalSAWS Wave 2 (Santa Clara, Tulare) | Infrastructure | Santa Clara and Tulare will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 02/2023. | 2023 Q1 |  |  | Technical Updates
186218 | CalWIN Conversion to CalSAWS Wave 3 (Orange, Santa Barbara and Ventura) | Infrastructure | Orange, Santa Barbara and Ventura will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 04/2023. | 2023 Q1 |  |  | Technical Updates
190570 | 2023 Annual FPL Updates | Shared | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 2023 Q1 | Program Updates |  | Program Support Services
186221 | CalWIN Conversion to CalSAWS Wave 4 (San Diego, San Mateo, Santa Cruz and Solano) | Infrastructure | San Diego, San Mateo, Santa Cruz and Solano will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 06/2023. | 2023 Q2 |  |  | Technical Updates
186317 | CalWIN Conversion to CalSAWS Wave 5 (Alameda, Fresno and Sonoma) | Infrastructure | Alameda, Fresno and Sonoma will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 04/2023. | 2023 Q2 |  |  | Technical Updates
189474 | Enrollment Module Transition | Covered CA | CCA has decided to implement a custom in-house solution for the Enrollment module. This will include all aspects of the current GI solution, including, but not limited to: SERFF Template Plan Load, Enrollment and Anonymous Shopping Experience, Provider Directory, EDI 834 Transaction Generation and Processing, CMS PBP Reporting, Pay Now, Renewals, Member Portal, Customer Admin Portal, Issuer Portal. | 2023 Q2 |  |  | Innovation & Continuous Improvement
96957 | Update CalHEERS to include downstream processing when an Individual is removed from a case | Shared | Provide messaging – Remove a member The objective of this initiative is to ensure downstream processes occur when a consumer requests to remove a household member from a case in CalHEERS. | 2023 Q3 | Program Updates |  | Enhancement CR & Warranty
122183 | Infants Initiative | DHCS | The objective of this initiative is to enhance functionality for Medi-Cal Deemed Infants, provide ability to add Medi-Cal Access Program infants (MCAIP) and renewal functionality in CalHEERS | 2023 Q3 | New Programs |  | Innovation & Continuous Improvement
132464 | CCHIP Enhancements | DHCS | To enhance current CCHIP eligibility and renewal functionality in CalHEERS. Adding Pending Eligibility determinations, resulting in update changes to noticing and CCHIP daily extract file. What: The purpose of these changes are to align CCHIP eligibility with the CMS MAGI Medicaid & CHIP Electronic Verification Plan Who: These fixes affect eligibility for CCHIP beneficiaries. Where: CalHEERS currently does not determine a CCHIP child as pending eligible when certain electronic verifications are not reasonably compatible. Conditionally eligible outcomes are not consistent with the approved CMS MAGI Medicaid & CHIP Electronic Verification Plan. Why: If the requested functionality is not added, CCHIP eligibility will not be in compliance with CMS MAGI Medicaid & CHIP Electronic Verification Plan. | 2023 Q3 | Program Updates |  | Enhancement CR & Warranty
186319 | CalWIN Conversion to CalSAWS Wave 6 (Sacramento, San Luis Obispo and San Francisco) | Infrastructure | Sacramento, San Luis Obispo and San Francisco will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 10/2023. | 2023 Q3 |  |  | Technical Updates
TBD | BREfS #7 - Carry Forward | TBD | This initiative will enhance and streamline the existing Carry Forward process by reducing the number of steps that eligibility workers are required to take in the current system. | 2023 Q3 |  |  | Enhancement CR & Warranty
40149 | Automation of the Application Missing Information Notice (NOD16) | Shared | The objective of this initiative is to allow admin roles to skip required fields and automatically send the consumer notification of missing information. | 2023 TBD |  | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Innovation & Continuous Improvement
170935 | Multiple Primary Tax Filers on the same case/application | Covered CA | Problem Statement: Currently, CalHEERS allows only one primary tax filer on a case/application. CalHEERS does not have the ability to calculate separate APTC amounts for multiple primary tax filer households on one case and also to enroll multiple tax households in one plan. Intended Outcome: Update CalHEERS to allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application/enrollment. Update the system to allow multiple different tax households with multiple different APTC amounts for one enrollment. Update the system to prevent any surplus APTC of one APTC tax household from being applied to another APTC tax household (even if both consumers are enrolled in the same plan). Update the system to generate multiple 1095s for multiple tax households that are enrolled on a single enrollment/plan. | 2023 TBD |  | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR & Warranty
TBD | BREfS #5 High Impact Business Validations | DHCS | This initiative will first require the analysis of the high impact eHIT Business Validations (BVs) to identify potentially redundant or antiquated BVs. Updates to the identified BVs would improve the accuracy and speed of automated eligibility determination results. | 2023 TBD | Business Rule Exposure for SAWS (BREfS) |  | Enhancement CR & Warranty
TBD | BREfS #8 eHIT Enhancement of Data Overlay | DHCS | This initiative will enable CalHEERS to process eHIT eligibility requests from SAWS without impacting exchange programs by overlaying required data elements. | 2023 TBD | Business Rule Exposure for SAWS (BREfS) |  | Enhancement CR & Warranty
82920 | BREfS #9 Verifications Only Service and Separation of Verifications by Source (previously BREfS - Phase D) | Shared | The intended outcome of this change is to modify both the CalHEERS portal and the eHIT architecture to add a separate Verifications Only service, while continuing to maintain the existing functionality described above for the combined VIED and BRE service. | 2024 Q1 | Business Rule Exposure for SAWS (BREfS) |  | Enhancement CR & Warranty
118769 | SAWS Integration with DIVS Solution | Shared | The purpose of this initiative is to incorporate the eHIT changes to align with the integration of the document imaging verification solution. | 2024 Q1 | CalHEERS - Efficiency Improvements |  | Technical Updates
151332 | MAGI Medi-Cal Income Budget Periods | DHCS | This initiative enhances the use of three budget periods to properly align with State law and Federal regulations and the budget period options selected in the SPA. As part of this initiative, the Projected Annual Income and Reasonably Predictable Future Income budget periods will be separated to allow for better alignment with current policy. | 2024 Q1 | Program Updates |  | Enhancement CR & Warranty
TBD | Alternative Formats – Accessibility Question | Shared | The purpose of this initiative is to add a question to CalHEERS Single Streamline Application for the applicant or representative to indicate any alternative format preferences. This initiative must align with all partner system enhancements for implementation. | 2024 Q1 | Notice Updates |  | Enhancement CR & Warranty | Alternative Formats changes need to be moved up prior to 2024 Q1. This is a disability accessibility issue and needs to be prioritized. | DHCS Response: This initiative is being prioritized for 2024 because it will have SAWS eHIT impacts that cannot be supported during CalSAWS migration.
186991 | Issuer Representative Account Maintenance | Covered CA | To establish functionality for the L1 and L2 Help Desk Users to provide assistance to the Issuer Representatives' or Issuer Enrollment Representatives' accounts for password resets or other necessary account maintenance (ie: user name retrieval) | 2024 Q1 |  |  | Enhancement CR & Warranty
45901 | SB 1341 AB 617 - BREfS Phase B | Shared | SB 1341 AB 617 - Notice Improvements - The objective of this initiative is to align CalHEERS with Senate Bill 1341 and Assembly Bill 617 and consolidate and send notices for Mixed Households in SAWS. | 2024 Q2 | Business Rule Exposure for SAWS (BREfS) |  | New Policy & Legislative Changes
TBD | 90-Day Cure Period | DHCS | This initiative will automate and streamline reinstatement of Medi-Cal eligibility in CalHEERS by SAWS when additional information needed to complete a redetermination is received within 90 days after discontinuance. This 90-day timeframe is referred to as the “cure period”. This initiative will help align the business processes across systems, and it may be merged with the broader BREfS: Application Life Cycle initiative. | 2024 Q2 | Business Rule Exposure for SAWS (BREfS) | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR & Warranty
TBD | Individual Level Eligibility | Shared | This initiative is intended to enhance and streamline the individual level eligibility functionality in CalHEERS. | 2024 Q2 | Program Updates |  | Innovation & Continuous Improvement
85672 | Medi-Cal Plan Selection | DHCS | The objective of this initiative is to provide the ability for MAGI Medi-Cal consumers to select a plan within CalHEERS. | 2024 Q3 | Program Updates |  | Enhancement CR & Warranty
144390 | CalHEERS MEDS Reconciliation File Enhancements | DHCS | The CalHEERS system currently maintains eligibility information for the COV-CA, MCAP, CCHIP, State Inmate, and Parole programs. CalHEERS sends information for these programs to DHCS for capture on the MEDS (Medi-Cal Eligibility) system. MEDS should be reconciled periodically with CalHEERS for consumers eligible for these programs (excluding Medi-Cal eligibility records). The data is currently being sent by CalHEERS on a monthly basis using the MEDS transaction RX20. In order for the RX20 transactions to process correctly through the existing MEDS Reconciliation process as mirrored by the SAWS-MEDS reconciliation process, CalHEERS must only submit data that meets certain validation requirements. | 2024 Q3 | Infrastructure Enhancements |  | Enhancement CR & Warranty
151861 | Change in MEC Value for Aid Code 01 | DHCS | Effective November 2019, refugees eligible for Medi-Cal aid code 01 are not entitled to Refugee Medical Assistance (RMA) benefits. Because aid code 01 will no longer include RMA benefits, it must NOT be considered Minimal Essential Coverage (MEC) in CalHEERS when the removal of RMA from aid code 01 takes effect. CalHEERS shall update the MEC table value for aid code 01 from TRUE to FALSE. Impacts to SAWS/Counties: SAWS will need to make noticing updates and potentially other changes per the pending ACWDL. | 2024 Q3 | Program Updates | (n/a - not an IAP CR for 24 month roadmap) | New Policy & Legislative Changes
173135 | Enhance eHIT to Transmit Verification Documents Uploaded in CalHEERS to SAWS | DHCS | Problem Statement: Consumers have the ability to upload outstanding verification documents in the CalHEERS portal. Currently the CalHEERS system does not notify counties/SAWS that Medi-Cal recipients have uploaded verification documents in the CalHEERS portal. In addition, the verification document is not transmitted to SAWS for verification by county eligibility workers. This Change Request will provide the functionality for CalHEERS to notify and send verification document/s to SAWS for county eligibility workers to complete verifications. Intended Outcome: Improved experience for business partners/SAWS. | 2024 Q3 | Infrastructure Enhancements |  | Technical Updates
TBD | Consumer Protection Programs | Shared | The objective of this initiative is to determine eligibility for the Consumer Protection Programs (CPPs) in the event a consumer lose eligibility in their coverage group. | 2024 Q3 | Program Updates |  | New Policy & Legislative Changes | Consumer Protections Programs changes need to be moved up prior to 2024 Q3. This has been pushed off for more than several years now. | DHCS Response: This initiative is being prioritized for 2024 because it will have SAWS eHIT impacts that cannot be supported during CalSAWS migration.
TBD | Explore Horizontal Integration Improvements | Shared | Explore Horizontal Integration Improvements | 2024 Q3 | Infrastructure Enhancements |  | Innovation & Continuous Improvement
123319 | 2022 Annual FPL Updates | Shared | The purpose of this CR is to create functionality for the Annual FPL Updates to be made independently of a release. Business would like to update the annual FPL values dynamically, without requiring a production release to make this annual process more efficient. | TBD | CalHEERS - Efficiency Improvements | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Innovation & Continuous Improvement
TBD | CalHEERS - SAWS Recon | DHCS | The objective of this initiative is to develop a monthly reconciliation process of case eligibility data between CH and SAWS. | TBD | Infrastructure Enhancements |  | Innovation & Continuous Improvement
TBD | Eligibility Results Page Phase II | DHCS |  | TBD | Program Updates |  |  | We do not see the changes to the Eligibility Results Page here. Is this already programmed for 2021/2022? If not, this needs to be included in the 2023 CR list. Presently, the eligibility results page includes some misleading information. o Inconsistent eligibility results identified in testing of CR 148955 in 20.2 release: - This household eligibility results summary page says “Also eligible for QHP/MCAP” but the actual result page says: Shannon is not eligible for … MCAP. But the eligibility determination factors say: you qualify for MCAP. - The Keep or Switch page says “Based on what you have told us, Covered California is most beneficial for your situation.”How is “most beneficial” determined? In this case the page goes on to say that MCAP has no deductibles or coinsurance, the baby will be covered for longer, and a whole host of other issues that makes it seem as though MCAP is more beneficial. | CalHEERS: The Eligibility Results page was redesigned in CR 166386 in Release 21.6. CalHEERS: Due to the redesign of the Eligibility Results page, this should be re-tested against the latest functionality to see if the new implementation resolves this disrecpancy. CalHEERS: CR 166386 did not modify language on the Keep or Switch Coverage page. Comment originated from Advocate testing of Account Home CR 148955 in Release 20.2, DHCS is working with CalHEERS to re-test this scenario and will address the potential change in Eligibility Results Page Phase II if the issue is still occurring in current production code base.
TBD | CalSAWS Migration | DHCS |  | TBD | Program Updates |  |  | What does "CalSAWS Migration Support" entail under the CR listed in the withdraw tab? My understanding is that the migration process runs through 2023, so I'm not understanding why it's being removed. | DHCS Response: Several specific CRs have been opened to support CalSAWS migration. This placeholder is no longer needed. CalHEERS: The project has created 6 CRs for the 6 waves of the migration support required through 2022-2023. Thus the TBD initiative can be withdrawn.