## Open Items
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
# | Date Logged | Policy Topic | Requestor | Action Item | Responding Organization | Owner | Deadline | Status | Notes
1 | 2017-01-13 | n/a | Stakeholder | For future IV&V Summaries, DHCS, Covered CA, and CalHEERS will discuss the strategy on how to build upon the IV&V reporting calendar and complete a roll up view for future IV&V updates. | CalHEERS / DHCS / Covered CA | CalHEERS / DHCS / Covered CA | TBD | Closed | 01/15/20 - CalHEERS, DHCS, and Covered CA have closed this action item. IV&V summary reports are internal reports and typically not shared externally. 7/24/19 - CalHEERS, DHCS, and Covered CA will continue to explore the opportunities in future meetings to share the IV&V reports 8/24/17 - CalHEERS, DHCS, and Covered CA will continue to explore the opportunities in future meetings to share the IV&V reports. 5/31/17 - CalHEERS, DHCS, and Covered CA will discuss the strategy in a future date.
2 | 2019-01-11 | IRS website link | Stakeholder | Cori R. asked whether the materials for applications assistors have been updated to reflect the new tax filing thresholds. | Covered CA | CC (Valerie York) | TBD | Complete | 5/3/19 - CC continue to work the material and will be providing once materials are finalize. 7/19/19 - Talking Points provided through HCA group in June 2019
3 | 2019-01-11 | Get Insured | Stakeholder | Alicia K. requested information as to whether or not the GI PCP Selection Module will differentiate between PCPs and gynecological PCPs | Covered CA | Covered CA | 2019-05-03 | Open | 12/13/19: At the AB 1296 meeting in December, Covered CA shared that when this initiative goes into design, they will reach out and provide interface information. 7/24/19 – This requires an interface with PCP provider data. The details will be finalized during the design session.
4 | 2019-05-03 | Non-Immigration Visa Holders | Stakeholder | Alicia K. requested screenshots for the new dynamically displayed language for a pop-up on the "Are you planning to file taxes" page. | Covered CA | CC (Valerie York) | 2019-07-30 | Complete | 12/26/19 - Complete per 9/16/19 email to advocates from Covered CA. 5/3/19 - CC and DHCS have added a UCD user story to the backlog to dynamically display language on the page when a user marks that they are not planning to file taxes. Once the user story is being designed, CC will provide. 7/19/19 - No update at this time
5 | 2019-05-03 | Bounce Back Rule (CR#125109) | Stakeholder | Cori R. requested follow up discussion/responses to the advocate feedback on the Bounce Back ACWDL (MCED-5147) | DHCS | DHCS/ Theresa H. | 2019-07-30 | Complete | 5/3/19 - Theresa to send email to Cori and set up meeting to walkthrough. 7/19/19- . Reponses were provided to Cori on 5/6/19 and there were no additional questions/follow up.
6 | 2019-05-03 | R19.9 Notices | Stakeholder | Alicia K. requested information on the changes that were made to R19.9 notices. CC/Emma indicated changes were very minor. | Covered CA | CC (Emma Z.) | 2019-07-30 | Complete | 5/3/19 - CC/Emma to send snippets to Alicia. 7/19/19- Information was provided to advocates on 5/3/19.

## Completed
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
Item Number | Date Logged | Policy Topic | Requestor | Action Item | Responding Organization | Owner | Deadline | Status | Notes
1 | 2016-09-07 | Renewal Language | Stakeholder | Covered CA to provide final notices with renewal languages based on CR# 59948. | Covered CA | Valerie York |  | Completed & Closed | Action item closed at the 1/13/17 meeting.
2 | 2016-09-07 | SAWS | Stakeholder | CWDA to check with SAWS to determine if the SAWS have the functionality to provide text messages and/or automatic phone calls. | CWDA | Assmaa Elayyat |  | Completed & Closed | 5/31/17 - CWDA/Cathy provided the response at the meeting.
3 | 2016-09-07 | Report a Change | Stakeholder | In a meeting with CWDA, the advocates understood from counties that for report a change of income, whole family will be re-evaluated. How will this impact those on APTC? | Covered CA | Thien Lam |  | Completed & Closed | 9/7/16 - Thien will circle back with Cori R. to clarify and respond. 1/13/17 - CC/Thien provided responses to question at the meeting.
4 | 2017-01-13 | n/a | Stakeholder | In addition to .pdf versions for the agenda and the CR Update document, post the Microsoft version. It will enable stakeholders to make necessary notes. | DHCS | Fei Collier/ Doina Culiuc |  | Completed & Closed | 8/24/17 - Update -- Due DHCS website publication standards, the Microsoft version of the documents will be posted on the AB 1296 website wherever possible instead of the including the .pdf version. 5/31/17 - Microsoft version and the .pdf version, for the Agenda and the CR Update document, have been posted on the AB 1296 website for the 5/31/17 meeting.
5 | 2018-01-12 | n/a | CH Project | All stakeholders to provide final comments to the 2019 Initiatives list by COB 1/19/18. | Stakeholders | CalHEERS / DHCS / Covered CA | 2018-01-19 | Closed
6 | 2018-01-12 | State Inmate | Stakeholder | Stakeholder requested further discussion and understand of the State Inmate CR (#82978). DHCS will add to the next CFSW or schedule separate meeting. | DHCS | DHCS | TBD | Completed & Closed | 09/11/18- currently this action item is being tracked on the CFSW action item log.
7 | 2018-01-12 | Horizontal Integration | Stakeholder | Stakeholder requested DHCS could consider horizontal integration as a future initiative | DHCS | DHCS | TBD | Completed & Closed | 4/26/19 - DHCS and CC added a line item to the 2020 Initiatives List "Explore Horizontal Integrratoin Improvements". DHCS, Covered CA, and CalHEERS Project will explore the capacity and feasibility during 2020 of adding this initiatives.
8 | 2018-08-30 | Release Notes Glossary | Stakeholder | Unplanned Pregnant Woman (UPW) - R18.6; R18.9 glossaries contain this acronym that doesn’t have an explanation. CH to take this item back, review, and provide the definition of the UPW if applicable/used in the document. | CalHEERS | Chris (CalHEERS) | TBD | Completed & Closed | 5/3/19 - CalHEERS provided clarity/correction during the meeting that UPW is Unmarried Pregnant Woman and not Unplanned Pregnant Woman.
9 | 2018-08-30 | IRS website link | Stakeholder | Alicia Kauk informed the group regarding a broken link on the IRS website. The expectation is that consumers are informed and guidance to the county is issued. Alicia will share the link webpage via the AB1296 inbox (email received on 09/10). CalHEERS and DHCS & CC will follow up with Accenture (who is the federal liaison) and work on more facts findings with the internal team | CalHEERS and DHCS & CC | CalHEERS/ DHCS/ CC | TBD | Completed & Closed | 1/14/19 - the IRS 2018 link has been updated with the new tax year. This link is an ever-green link that does not need to be changed. 2/6/19 - DHCS, Covered CA, and advocates discussed the best ways to support applicants and beneficiaries. The agreement reached was for DHCS to publish an ACWDL that includes a table from an IRS publication. DHCS expects to publish the ACWDL within the next few weeks. Eligibility workers are informed to share a IRS link and publication with consumers to assist with determining whether or not they are required to file taxes.
10 | 2018-08-30 | DIVS | Stakeholder | DIVS - how many documents are received by fax | Covered CA | CC | TBD | Completed & Closed | 5/3/19 - CC/Trisha provide count of 5,140 faxes are received per month. 9/11/18 - CC receives from 100-150 faxes per day total. CC will be able to determine what portion of these are DIVS documents after the implementation of DIVS mail/fax in the October R18.9 release.
11 | 2018-12-12 | List of Notices | Stakeholder | Stakeholders requested a list of CalHEERS generated consumer notices. | Covered CA | CC | 2019-01-11 | Completed & Closed | 3/28/19 - The list of consumer friendly document names for CalHEERS notices were sent on 3/28 to the key advocate team members.
12 | 2019-01-11 | R18.12 | Stakeholder | Cori R. requested a screenshot of the "My Account/Application" page to see the updates that have been made. | CalHEERS | Chris (CalHEERS) | TBD | Completed & Closed | Screen shots provided to Cori & Alicia K. on 2/6/19.
13 | 2019-01-11 | General | DHCS, CC, & CalHEERS | As part of AB 1296 Agenda item VI, DHCS/CC/CalHEERS requested feedback from Stakeholders regarding the CalHEERS Functionality & Progress since the system went live. Representing the key advocate team, Cori R. provided verbal feedback and will follow up and provide in writing. | Stakeholders | Stakeholders (Cori R.) | By 2nd 2019 AB 1296 Meeting | Completed & Closed | 5/1/19 - DHCS, CC, and CalHEERS received the letter from key advocate groups providing feedback on CalHEERS' functionality and progress.
14 | 2019-01-11 | 2020 Initiatives | DHCS, CC, & CalHEERS | DHCS/CC/CalHEERS will send responses to the stakeholder feedback (received on 1/2/19) on the 2020 CalHEERS Initiatives | DHCS, CC, & CalHEERS | DHCS, CC, & CalHEERS | 2019-01-22 | Completed & Closed | 1/23/19 - Adjusted deadline date for the responses to 1/24/19.
15 | 2019-01-11 | 2020 Initiatives | DHCS, CC, & CalHEERS | All stakeholders to review & provide 2nd round of feedback to DHCS/CC/CalHEERS' responses to the initial final comments to the 2019 Initiatives list by COB 1/19/18. | Stakeholders | Stakeholders (Cori R.) | 2019-02-02 | Completed & Closed | 1/23/19 - Adjusted deadline date for stakeholder feedback to 2/5/19.
16 | 2019-01-11 | 2020 Initiatives | DHCS, CC, & CalHEERS | DHCS/CC/CalHEERS will send 2nd round of responses to the stakeholder feedback and finalize the 2020 CalHEERS Initiatives. | DHCS, CC, & CalHEERS | DHCS, CC, & CalHEERS | 2019-03-01 | Completed & Closed | Finalized 2020 Initiatives List on 3/19/2019
17 | 2019-01-11 | Income & Deductions | Stakeholder | Alicia K. requested an updated Income & Deductions Chart, which was released with MEDIL 19-03. | DHCS | DHCS | 2019-05-03 | Completed & Closed | 4/29/19 - MEDIL 19-03 released January 14, 2019. Updated Income & Deductions Chart has been sent to requestor.
18 | 2019-01-11 | Notices | Stakeholder | Alicia K. requested updated list of consumer-friendly document names for CalHEERS notices. | Covered CA | Covered CA | 2019-05-03 | Completed & Closed | 3/28/19 - The list of consumer friendly document names for CalHEERS notices were sent on 3/28 to the key advocate team members. Note: This is similar request and action item on 12/12/18.