## Go-Live
Acronyms are defined on the Acronyms sheet. Use Control + page down to navigate to the new sheet. Bold Cells indicate changes from prior version. | DHCS Major Program Initiatives - Go-Live Dates (pending readiness and federal approvals) | [12 empty] | 2024-11-22
Category | Activity | 1/24 | 6/24 | 7/24 | 10/24 | 12/24 | 1/25 | 2/25 | 2024-05-25 | 7/25 | 12/25 | 1/26 | 2024-05-26 | 2024-07-26 | 2027
Behavioral Health Transformation | Bond BHCIP Round 1 |  |  | RFA Released |  |  |  |  | Awards
| Bond BHCIP Round 2 | [7 empty] | RFA Released |  |  |  | Awards
| Behavioral Health Services Act | [12 empty] | X
CalAIM/Waiver | Administrative Integration of SMH and SUD | [5 empty] | Phase II Voluntary Behavioral Health Contract Integration (County Option) | [7 empty] | Fully Integrated
| Benefits Standardization | ICF/DD & Subacute Care Facilities Carved Into Managed Care in all counties
| Enhanced Care Management (ECM)/Community Supports (ILOS) | Birth Equity Population of Focus & Individuals Transitioning from Incarceration
| Incentive Payment Program | X
| PATH Initiatives (ECM, Community Supports, Justice-Involved) | CITED Round 3 Opens (Q1 2024) |  |  |  |  | CITED Round 4 Opens
| Regional Capitation Rates and Shared Savings/Risk | [5 empty] | SPD & LTC Blend Non-COHS |  |  |  |  | Regional Rates1 |  |  | Prospective Shared Savings
| Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment (BH-CONNECT) | [5 empty] | No Sooner Than
| Medi-Medi Plans (D-SNP) Expansion Statewide | [10 empty] | Most Non-CCI Counties |  |  | Remaining Non-CCI Counties
Transition to Statewide MLTSS (TBD)
| Justice-Involved Initiative |  |  |  | Pre-Release Medi-Cal Services (24-month phase-in period begins)
| Population Health Management Service (Medi-Cal Connect) |  |  | Release 1 |  | Release 2 Late 2024 / Early 2025 |  |  |  | Release 3 Mid 2025 | Release 4 Late 2025 | Release 5 Early 2026
| County CCS Oversight | [8 empty] | X
| NCQA Accreditation | [10 empty] | X
Full Integration Plans (TBD)
| County Eligibility and Oversight |  | X
| DMC-ODS Traditional Healers and Natural Helpers | [5 empty] | X
Improving Beneficiary Contact and Demographic Information (TBD)
| Transitional Rent | [8 empty] | X (Optional) |  | X (Mandatory, Phase In)
Children and Youth Behavioral Health (BH) Initiative | BH Service Virtual Platform (including e-Consult) | X
| Statewide Fee Schedule and BH Network | X (Phase In)
| Wellness Coaches | [5 empty] | X
Eligibility | Eliminate Medi-Cal Asset Test | X
| Expansion of Full-Scope Medi-Cal Coverage to All Adults Regardless of Immigration Status | X
| Continuous Coverage Through Age 4 | [10 empty] | X2
| Share of Cost Reform | [10 empty] | X2
Benefits | Mobile Crisis Services | Services Begin (46 counties) |  | Services Begin (Remaining 12 Counties)
Financial | FQHC Alternative Payment Methodology |  |  | Cohort 1 | [7 empty] | Cohort 2
| Equity and Practice Transformation Payments | X
Other | Medi-Cal Managed Care New Contract | X
| Behavioral Health Bridge Housing Program |  |  | Round 3 Awards | [5 empty] | Round 4 RFA Release | Round 4 Awards
| Community Assistance, Recovery and Empowerment (CARE) Court |  |  |  |  | Cohort II
| Health Equity Roadmap |  |  |  |  | Phase 2: Co-design
Bold cells indicate change from prior version
Quarters (Q) are based on calendar year
1 Potential phase in through 2026, as applicable
2 Subject to appropriation, federal approval, and state readiness

## Acronyms
Acronyms | Definition
BH | Behavioral Health
BHCIP | Behavioral Health Continuum Infrastructure Program
BH-CONNECT | Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment
CalAIM | California Advancing and Innovating Medi-Cal
CCI | Coordinated Care Initiative
CCS | California Children's Services
CITED | Capacity and Infrastructure Transition, Expansion, and Development
COHS | County Organized Health Systems
DMC-ODS | Drug Medi-Cal Organized Delivery System
D-SNP | Dual Eligible Special Needs Plan
ECM | Enhanced Care Management
FQHC | Federally Qualified Health Center
ICF/DD | Intermediate Care Facility for the Developmentally Disabled
ILOS | In Lieu of Services (renamed Community Supports)
LTC | Long-Term Care
MLTSS | Managed Long-Term Services and Supports
NCQA | National Committee for Quality Assurance Accreditation Workgroup
PATH | Providing Access and Transforming Health
RFA | Request for Application
SMH | Specialty Mental Health
SPD | Seniors and Persons with Disabilities
SUD | Substance Use Disorder
TBD | To Be Determined