## Go-Live
A10 | DHCS Major Program Initiatives - Go-Live Dates (pending readiness and federal approvals) |  |  |  | Updated: 8/14/2026
Category | Activity | 1/26 | 2024-03-26 | 2026-05-26 | 2024-07-26 | 2026-09-26 | 2026-10-26 | 2025-12-26 | 2025-01-27 | 2025-07-27 | 2025-10-27 | 2028 | 2029
Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment (BH-CONNECT) | Activity Funds |  |  |  |  | X
| High Fidelity Wraparound |  |  |  | X
Behavioral Health Transformation | Bond BHCIP Round 2 |  | Awards
| Behavioral Health Services Act |  |  |  | X
CalAIM | Administrative Integration of SMH and SUD | [7 empty] | Fully Integrated
| PATH Initiatives (to support ECM, Community Supports, Justice-Involved) | Technical Assistance Marketplace Closes | [5 empty] | PATH Initiative Ends
| Population Health Management Service (Medi-Cal Connect) |  | Release 5
| CalAIM Renewal |  |  | Submit to CMS |  |  |  |  | X
| Transitional Rent | Mandatory Phase-In
| Medi-Medi Plans (D-SNP) Expansion Statewide | Most Non-CCI Counties | [9 empty] | Remaining Non-CCI Counties Phase-in
| NCQA Accreditation | X
| Enhanced Care Management - Refined Eligibility, Definitions, and Utilization Management | [7 empty] | X
| Community Supports - Refined Referral Pathways, Eligibility, Definitions, and Utilization Management | [7 empty] | X
| Justice-Involved Re-Entry Initiative | [5 empty] | All Correctional Facilities Launch
Benefits | Eliminate Glucagon-Like Peptide-1 (GLP-1) Coverage for Weight Loss | X
| Qualifying Community-Based Mobile Crisis Services - Benefit Extension | [8 empty] | Benefit Extension Ends
| Eliminate State-Only Dental Benefits, Adults 19 and Older with Unsatisfactory Immigration Status | [8 empty] | X
Eligibility | Enrollment Freeze for Full-Scope State-Only Medi-Cal Expansion, Adults 19 and Older | X
| Reinstate Medi-Cal Asset Test Limits | Phase 1 Reduction | [7 empty] | Phase 2 Reduction
| H.R. 1 Work Requirements for Medi-Cal Expansion Adults 19 to 64 | [7 empty] | X
| H.R. 1 Redetermine Eligibility for Medi-Cal Expansion Adults Every Six Months 19 to 64 | [7 empty] | X
| State-Only Medi-Cal Premiums, Adults 19 Through 59 with Unsatisfactory Immigration Status | [8 empty] | X
| Restrictions on Immigrant Eligibility - Transition of Qualified Non-Citizens to Restricted-Scope Medi-Cal | [8 empty] | X
| Reduced Retroactive Medi-Cal Coverage Timeframes | [7 empty] | No Sooner Than January 1, 2027
| H.R 1 Copayments for Specified Expansion Adults | [10 empty] | X
| Transition of Individuals with Unsatisfactory Immigration Status from Managed Care to Fee-for-Service | [7 empty] | X
Financial | H.R. 1 Provider Tax Changes | [9 empty] | Multiyear Phase-Down
| Eliminate State-Only Prospective Payment System Rates to Federally Qualified Health Centers and Rural Health Clinics for Individuals with Unsatisfactory Immigration Status | [8 empty] | X
| Eliminate General Fund Proposition 56 Medi-Cal dental supplemental incentive payments | [8 empty] | X
| H.R. 1 Regular FMAP for Emergency Medi-Cal for Individuals with Unsatisfactory Immigration Status | [5 empty] | X
| H.R. 1 State Directed Payment Restrictions | [10 empty] | Multiyear Phase-Down
| MCO Tax Expiration and Federally Compliant Renewal (SB 125) | [6 empty] | No Later Than 12/31/26 Submit MCO Tax Renewal
| H.R. 1 Federal Funding Repayment Penalties | [11 empty] | X
Bold cells indicate change from prior version
X indicates an Activity is going live in the designated month

## Acronyms
Acronyms | Definition
BHCIP | Behavioral Health Continuum Infrastructure Program
BH-CONNECT | Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment
CalAIM | California Advancing and Innovating Medi-Cal
CCI | Coordinated Care Initiative
CMS | Centers for Medicare and Medicaid Services (Federal Agency)
D-SNP | Dual Eligible Special Needs Plan
ECM | Enhanced Care Management
FMAP | Federal Medical Assistance Percentage
H.R. | House of Representatives (Federal Legislation)
NCQA | National Committee for Quality Assurance
PATH | Providing Access and Transforming Health
SMH | Specialty Mental Health
SUD | Substance Use Disorder

## Go-Live ( updated 0725) (hidden)
Acronyms are defined on the Acronyms sheet. Use Control + page down to navigate to the new sheet. Bold Cells indicate changes from prior version. | DHCS Major Program Initiatives - Go-Live Dates (pending readiness and federal approvals) | [19 empty] | 2025-07-02
Category | Activity | 7/24 | 8/24 | 10/24 | 11/24 | 12/24 | 1/25 | 2/25 | 3/25 | 4/25 | 2024-05-25 | 2025-06-25 | 7/25 | 8/25 | 10/25 | 11/25 | 12/25 | 1/26 | 4/26 | 2024-05-26 | 2024-07-26 | 2025-12-26 | 2027
Behavioral Health Transformation | Bond BHCIP Round 1 | RFA Released | [8 empty] | Awards
| Bond BHCIP Round 2 | [9 empty] | RFA Released | [8 empty] | Awards
| Behavioral Health Services Act | [19 empty] | X
CalAIM/Waiver | Administrative Integration of SMH and SUD | [5 empty] | Phase II Voluntary Behavioral Health Contract Integration (County Option) | [15 empty] | Fully Integrated
| Enhanced Care Management (ECM)/Community Supports (ILOS) |  | ECM CS Q2 2024 data |  | ECM CS Q3 2024 data |  |  | ECM CS Q4 2024 data |  |  | ECM CS Q1 2025 data |  |  | ECM CS Q2 2025 data
| PATH Initiatives (ECM, Community Supports, Justice-Involved) |  | Develop CalAIM DSAG 3.0 toolkit for Justice-Involved Populations |  |  |  | CITED Round 4 Opens | [8 empty] | Pre-Release & Reentry Health Services – Justice-Involved Data Enablement |  | SDN 24033 Phase III – System Update for Justice-Involved BH Provider Claim Adjudication
| Regional Capitation Rates and Shared Savings/Risk | [5 empty] | SPD & LTC Blend Non-COHS | [10 empty] | Regional Rates1 | Justice-Involved Advisory Group Meetings |  |  | CalAIM 1115 waiver demonstration Re-entry | Prospective Shared Savings
| Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment (BH-CONNECT) | [6 empty] | Content/Page updated on DHCS site
| Medi-Medi Plans (D-SNP) Expansion Statewide | [8 empty] | Invoice Approved | [7 empty] | Most Non-CCI Counties |  |  |  |  | Remaining Non-CCI Counties
| Justice-Involved Initiative |  |  | Pre-Release Medi-Cal Services (24-month phase-in period begins) | [7 empty] | X
| Population Health Management Service (Medi-Cal Connect) | Release 1 |  |  |  | Release 2 Late 2024 / Early 2025 | [6 empty] | Release 3 Mid 2025 |  |  |  | Release 4 Late 2025 | Release 5 Early 2026
| NCQA Accreditation |  |  |  | Assessment Review & Follow-Up | [12 empty] | X
| County Eligibility and Oversight | [9 empty] | Report published to requester
| DMC-ODS Traditional Healers and Natural Helpers |  |  |  | Informative video published
| Transitional Rent | [7 empty] | Updated Transitional Rent Fact Sheets | [8 empty] | X (Mandatory, Phase In)
Children and Youth Behavioral Health (BH) Initiative | Wellness Coaches |  |  |  | Establish the Wellness Coach as a new distinct provider type
| Mobile Crisis Services | Services Begin (Remaining 12 Counties) | [12 empty] | Data Reporting Project
Financial | FQHC Alternative Payment Methodology | Cohort 1 | [15 empty] | Cohort 2
Equity and Practice Transformation Payments
Other | Medi-Cal Managed Care New Contract
| Health Equity Roadmap |  |  |  |  | Phase 2: Co-design
| Community Assistance, Recovery and Empowerment (CARE) Court |  |  |  |  | Cohort II
Bold cells indicate change from prior version
Quarters (Q) are based on calendar year
1 Potential phase in through 2026, as applicable
2 Subject to appropriation, federal approval, and state readiness