## 2023 CalHEERS Roadmap
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
CalHEERS
CRs / Initiatives
CR # | TITLE | BRIEF DESCRIPTION | RELEASE
121903 | Document Image Conversion tool | This CR provides functionality in CalHEERS to convert all user uploaded documents related to verification / eligibility to PDF in order to standardize a single file format to be stored in CalHEERS. | 22.9
171266 | Notices Updates for R22.9 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 22.9
186107 | CalWIN Conversion to CalSAWS Wave 1 (Placer, Contra Costa and Yolo) | This initiative is the first of six waves to support the CalWIN to CalSAWS Migration for Placer, Contra Costa and Yolo counties. | 22.9
188309 | Updates to Terminate case, Duplicate case closure and CancelDER functionalities | The following functional changes are requested in CR 188309: Terminate Applications: - When a case is terminated the case status will be updated to "INACTIVE" -When an admin submits case for termination, the Case Transaction History Screen will have a record "Case Terminated" If Cases Closed as Duplicate/ Cancel DER is received from SAWS: - Case Transaction History page will have a record "Duplicate Case Closure" -all individuals on a case will be discontinued for the current benefit year at the end of the current month - if the case has been renewed, eligibility will be all individuals for the future benefit year effective 1/1, and Account Transfer will be sent for current and future benefit years | 22.9
189274 | Update Incarceration Functionality for MAGI Medi-Cal | This CR's goal is to ignore the incarceration verification and admin fail for MAGI Medi-Cal Individuals. Therefore, individuals will now be eligible if otherwise eligible for MAGI Medi-Cal even if they have an outstanding/Pending Incarceration Verification. A new Negative Action will be added to allow for the discontinuance of MAGI Medi-Cal individuals due to incarceration. | 22.9
190956 | State-Level Cost Sharing Reduction program | CalHEERS system will build a new Temporary CSR program that will be configuration driven which will allow CovCA to select either an existing Permanent CSR or the new Temporary CSR program for an enrollment year. Temporary CSR program will have a configurable functionality which will allow business to map CS level with FPL range. | 22.9
191292 | 2023 Renewals | The functional changes requested in CR 191292 are enhancements to the annual Renewals process based on lessons learned from previous Renewals. The functional changes span across HBX and GI systems including bots to address fall out populations, Account Transfer changes, batch changes, eligibility changes, screen changes, HX20 changes, and enrollment changes. | 22.9
197324 | ARPA Postpartum Coverage Extension for all MAGI Medi-Cal and MCAP Programs - Phase II | CalHEERS system will update the MCAP program eligibility determination logic where MCAP discontinuance will only be built if an eligibility is run during the month when MCAP program is ending. CalHEERS system will end date specific Negative Actions or Non-Compliance codes received for a pregnant or postpartum individual with eligibility run date which didn't result in discontinuance of MAGI Medi-Cal benefits. | 22.9
197806 | Security Enhancements for Portal Pages | CR 197806 will implement the following security enhancements for portal pages: - Limit Non-Admin password changes to once per calendar day - Mask Date of Birth field for Consumers and Authorized Representatives - Include messaging to notify the user that profile changes will not impact the application - Require Consumers and Authorized Representatives to enter a one time password (OTP) to access pre-2022 tax documentation | 22.9
207486 | Changes to the Text in the NOD22 Issuer Bill Statement Notice | CalHEERS system will update the header and footer with additional details for NOD22. | 22.1
208654 | Renewal Closure Batch to withdraw RRC application that have future year eligibility established on the last day of renewal. | Renewal Closure Batch should withdraw Renewal reported change(RRV) case/application on the last day of renewal, if eligibility has been run on the case in renewal mode. This would ensure that the case will get into RAC mode. | 22.1
211452 | NOD01 Box Snippet for 2023 | Currently the law states that the ARP benefits expire on 12/31/2022, and the state budget passed by the legislature includes a provision that State Subsidy shall be in place for 2023 if the ARP benefits are not extended. Covered CA would like messaging in the NOD01 to notify the consumers about the changes. | 22.1
171267 | Notices Updates for R22.12 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 22.12
208859 | Apply Soft Pause to beneficiaries that are placed in Pending eligibility status due to pending verifications following SAWS renewal. | Beneficiaries in a Pending eligibility status should be placed into soft pause (when appropriate) using existing soft pause rules when the previous eligibility status was Eligible or Conditionally Eligible in order to ensure correct eligibility and time for counties to evaluate for Non-MAGI Medi-Cal eligibility. | 22.12
209628 | SB260 - ChatBot | CCA Chatbot requires access to various CalHEERS APIs to provide consumer support such as, completing the Opt In and/or Opt Out for SB260 Auto Plan Selection (APS) process. Testing of the API connection will also be required. | 22.12
147420 | Administrator Search Enhancements | This CR will begin the redesign of the Admin CalHEERS portal search screen to improve usability and provide more details for our admin users. With this change, CalHEERS will introduce enhanced case searching functionality. | 23.2
200349 | Notices CR for 23.2 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.2
190570 | 2023 Annual FPL Updates | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 23.2.1
189474 | Plan Choice and Assister Portal Project (PCAP) | Replace the existing COTS product(s) with a custom solution that is integrated with the HBEX custom solution to produce custom software solution or a combination of a custom/Salesforce solution for the CalHEERS Eligibility and Enrollment functionality. Note that 6 child CRs were created in RTC to support the initiative from an administration perspective: CR 193111 - Plan Choice and Assister Portal Project (PCAP) - Plan Management CR 193114 - Plan Choice and Assister Portal Project (PCAP) - Enrollment & Shopping CR 193115 - Plan Choice and Assister Portal Project (PCAP) - EDI & Enrollment Batches CR 193140 - Plan Choice and Assister Portal Project (PCAP) - Agent & CEC Portal CR 193143 - Plan Choice and Assister Portal Project (PCAP) - Issuer Portal CR 193144 - Plan Choice and Assister Portal Project (PCAP) - Admin Self-Service CR 193145 - Plan Choice and Assister Portal Project (PCAP) - Policy Based Payments & Renewal Batches | 23.4
165890 | ROP Batch - Phase II | In Release 21.2, Phase I will be released. This CR is a placeholder to allow for any adjustments that may be needed to the system to ensure the efficient operation of the ROP Batch post that release. | 23.6
190310 | Supplemental Notices Insert and Notices Hold Release | Covered CA would like to have the option of automating a supplemental notice insert (content previously known as buck slip) with a notice, so that the generated pdf has the supplemental notice insert and it can be scanned as a whole notice and uploaded to the consumer account. Covered CA would also like to have the supplemental insert in all the supported languages with the capability to handle full color/gray scale, bold, italics, underline, special characters, charts, tables and images and printed on a single or double page (half, third of a sheet, full sheet) with the option of selecting the positioning of the supplemental notice insert in the notice package. Covered CA would like to expand the functionality of an Admin Notice (NOD00), so that the admin notice can be generated in all the supported languages with the capability to handle full color/gray scale, bold, italics, underline, special characters, charts, tables and images. It should also include the short version of the babel page and the non-discrimination 1557 language. Covered CA would also like to hold/release a notice through an automated process that can be easily managed and tracked by the team. | 23.6
199836 | Periodic Verifications No Response from Consumers | The Periodic Verification process for Medicare and Deceased should be updated to exclude cases with inactive case status. If the consumers have been notified of a verification received from the PVC run and the consumer does not respond within the allowed time frame, then the batch that is run for no response should discontinue the consumers from the appropriate program(s) based on the identified data inconsistency. | 23.6
200350 | Notices Updates for R23.6 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.6
40149 | Automation of the Application Missing Information Notice (NOD16) | The objective of this initiative is to allow admin roles to skip required fields and automatically send the consumer notification of missing information. | 23.9
61104 | Implement Plan Dependent Rules | Update CalHEERS to implement the enforcement of plan dependent rules. CalHEERS enrollment grouping rules should include plan dependency definitions, by only allowing Married spouses, Registered domestic partners, Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners, Disabled adult children of any age (including 26 or above) and Siblings under the age of 26 to enroll in the same Covered CA plan. CalHEERS should also prevent enrollment of over-age dependents unless they meet the “disabled child” exception. | 23.9
96957 | Update CalHEERS to include downstream processing when an Individual is removed from a case | Provide messaging – Remove a member The objective of this initiative is to ensure downstream processes occur when a consumer requests to remove a household member from a case in CalHEERS. | 23.9
166033 | Prospective Premiums for Renewals | The intended outcome is to better inform consumers about what their next year's APTC and premium amounts will be if they keep their same plan. | 23.9
180018 | Spanish URLs for CalHEERS Portal Login and Shop & Compare | Covered CA is seeing a high drop rate of Spanish Consumers ending their sessions after landing on the English version of CalHEERS Portal Login (https://apply.coveredca.com/apspahbx/ahbx.portal) and Shop & Compare (https://apply.coveredca.com/lw-shopandcompare/) based on analyzing the stats collected from Google Analytics. Covered CA has determined that most Spanish Consumers are clicking on URLs provided by Covered CA Marketing campaigns and Covered CA partners. Covered CA would like dedicated Spanish URLs to direct Spanish Consumers to CalHEERS Portal Login and Shop & Compare and automatically select Spanish language. Spanish Consumers will land on CalHEERS Portal Login and Shop and Compare pages in Spanish when Consumer clicks on hyperlink provided by Covered CA Marketing campaigns and Covered CA Partners. | 23.9
199832 | Eligibility Determinations after APS (SB 260) Phase 2 | With the current implementation of SB 260 with CR 160531, CalHEERS can only retain the Auto Plan Selection (APS) flag if the APS enrollment is available. If due to a subsequent RAC, the APS enrollment is terminated or canceled, the consumer will not be able to take Opt In/Opt Out actions because the enrollment status for the APS Enrollment is no longer in a “Pending” state for the consumer to take action on. The APS flag is attached to the enrollment for which the consumer is auto plan selected to. It is not attached to any new enrollments which result due to changes in eligibility. This applies to all eligibility determinations including the ones that are not submitted by the consumer. If the subsequent RAC enrolled the consumer in a $0 net premium plan, the consumer no longer has the option to opt-in or opt-out since the APS enrollment is no longer valid. In addition, consumers for whom a change results in the APS enrollment being automatically updated from >$0 to a $0 net premium need to be informed of their new obligation to provide an active Opt-in in order to keep the APS plan. With the initial CR, a simple banner message has been added to the eligibility dashboard, but the message is vague, over-applied, and is only seen by users that did the RAC in CalHEERS versus SAWS transactions. | 23.9
200352 | 2024 Renewals | Annual renewals related system enhancements | 23.9
200353 | Notices Updates for R23.9 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.9
TBD | BREfS #7 - Carry Forward | This initiative will enhance and streamline the existing Carry Forward process by reducing the number of steps that eligibility workers are required to take in the current system. | 23.9
200351 | Notices Updates for 23.12 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.12
186216 | CalWIN Conversion to CalSAWS Wave 2 (Santa Clara, Tulare) | Santa Clara and Tulare will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 02/2023. | 2023-02-27
186218 | CalWIN Conversion to CalSAWS Wave 3 (Orange, Santa Barbara and Ventura) | Orange, Santa Barbara and Ventura will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 04/2023. | 2023-04-24
186221 | CalWIN Conversion to CalSAWS Wave 4 (San Diego, San Mateo, Santa Cruz and Solano) | San Diego, San Mateo, Santa Cruz and Solano will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 06/2023. | 2023-07-03
186317 | CalWIN Conversion to CalSAWS Wave 5 (Alameda, Fresno and Sonoma) | Alameda, Fresno and Sonoma will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 04/2023. | 2023-09-04
186319 | CalWIN Conversion to CalSAWS Wave 6 (Sacramento, San Luis Obispo and San Francisco) | Sacramento, San Luis Obispo and San Francisco will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 10/2023. | 2023-10-30
213355 | Manual Trigger of APS | APS is only triggered from the initial transition transaction. Covered CA needs a manual process to trigger Automatic Plan Selection when a transitioning member changes from unsub to subsidized during the transition period. | 2023 Q1
213539 | BPM Workflow Improvements II | The intended outcome of this CR is: 1. To prevent Duplicate MWS cases from being created in Salesforce when multiple household members upload the same document. 2. To ensure that the Annual Document – 1095, document types for Deceased and Incarceration are routed to the correct queues for Service Center processing. 3. Case origin field is populated to identify the origin of the document. | 2023 Q1
214183 | Eligibility Results page to display the current Eligibility run and Eligibility start date to be determined correctly for prior year application | Eligibility Results page to display the current Eligibility run and Eligibility start date to be determined correctly for prior year application | 2023 Q1
214185 | Move Enum to the reference data caching for the screens part of the LW Phase 5 | Enum will be moved to the reference data caching providing easier way to maintain these static values. | 2023 Q1
114946 | Consumer Document Upload Functionality and Admin Task Management | This CR is split from CR 99895 and includes consumer document upload functionality requirements and task management as a result of that upload functionality. | 2023 Q2
202401 | Eligibility Changes due to Attestation to AI/AN Tribes | If a consumer attests to being a member of a federally recognized AI/AN tribe and a tribe other than "Tribe not listed" is selected, CalHEERS should grant unconditional AI/AN CSR eligibility, if the consumer is otherwise eligible to exchange. If a consumer attests to being a member of a federally recognized AI/AN tribe and the tribe "Tribe not listed" is selected, CalHEERS should continue to grant conditional AI/AN CSR eligibility, if the consumer is otherwise eligible to exchange. | 2023 Q2
202496 | Automatic enrollment updates for consumers with pending SSN | CalHEERS should move consumers with pending SSNs and the system date is past their ROP date into unsubsidized plans via a BOT process. | 2023 Q2
210202 | Expansion of full scope Medi-Cal for eligible adults from 26 through 49 years of age, inclusive, regardless of citizenship or immigration status | Per the Governor’s Proposed Budget (2022-2023), CalHEERS will need to modify current business rules to grant full scope MAGI Medi-Cal to eligible adults from 26 through 49 years of age, inclusive, regardless of citizenship or immigration status if they meet all other criteria. | 2023 Q3
173678 | Medicare Coverage Dates | CalHEERS should be able to persist and read the partial Medicare coverage details from the Medicare response for the year and then evaluate consumers eligible for subsidy only for months that are not covered by Medicare. If the response indicates a Medicare Coverage End Date in the future, system should be able to make a correct determination of whether it should count as a Medicare covered month. CalHEERS should have the functionality to not read ALL partial coverage year scenarios as not covered by Medicare. | 2023 TBD
189273 | Implement Eligibility Functionality for Family Planning, Access, Care and Treatment (Family PACT) Program in CalHEERS | CalHEERS shall add the Family PACT application and eligibility process to the CalHEERS Portal and BRE, automate integration with MEDS, automate referrals for other IAP programs, and provide appropriate notices and messaging to Family PACT clients and Family PACT providers. Family PACT program aid code 8H is not considered MEC and shall not impact current CalHEERS functionality for determining eligibility for IAP programs. | 2023 TBD
82920 | BREfS #9 Verifications Only Service and Separation of Verifications by Source (previously BREfS - Phase D) | The intended outcome of this change is to modify both the CalHEERS portal and the eHIT architecture to add a separate Verifications Only service, while continuing to maintain the existing functionality described above for the combined VIED and BRE service. | 2024 Q1
118769 | SAWS Integration with DIVS Solution | The purpose of this initiative is to incorporate the eHIT changes to align with the integration of the document imaging verification solution. | 2024 Q1
128730 | Automation of Termination Reason Codes due to Fraud and Medi-Cal Eligibility | The objective of this initiative is to automate reason codes in 835 File Transactions between CalHEERS and Qualified Health Plans (QHP) that are conducted manually currently. | 2024 Q1
151332 | MAGI Medi-Cal Income Budget Periods | This initiative enhances the use of three budget periods to properly align with State law and Federal regulations and the budget period options selected in the SPA. As part of this initiative, the Projected Annual Income and Reasonably Predictable Future Income budget periods will be separated to allow for better alignment with current policy. | 2024 Q1
165890 | ROP Batch - Phase II | In Release 21.2, Phase I will be released. This CR is a placeholder to allow for any adjustments that may be needed to the system to ensure the efficient operation of the ROP Batch post that release. | 2024 Q1
183100 | SEP Dropdown and Workflow - Phase II | Problem Statement: The SEP reasons in the portal is not a comprehensive list that adheres to the federal regulations. The page does not have helpful information and causes confusion to the consumers in the Intake/RAC flow. Intended Outcome: The SEP reasons in the portal needs to be more intuitive and more helpful to the users: 1. Update and add to the available SEP reasons 2. Update and add to the business rules for each existing and new SEP reason 3. Dynamically display the SEP reasons in the drop down list based on the user role and application mode 4. Update the SEP page language 5. Allow users to capture multiple SEP reasons. System to determine the most advantageous SEP reason. 6. Capture SEP reasons at the household vs individual level. 7. Update eHIT/SAWS accordingly | 2024 Q1
TBD | Alternative Formats – Accessibility Question | The purpose of this initiative is to add a question to CalHEERS Single Streamline Application for the applicant or representative to indicate any alternative format preferences. This initiative must align with all partner system enhancements for implementation. | 2024 Q1
45901 | SB 1341 AB 617 - BREfS Phase B | SB 1341 AB 617 - Notice Improvements - The objective of this initiative is to align CalHEERS with Senate Bill 1341 and Assembly Bill 617 and consolidate and send notices for Mixed Households in SAWS. | 2024 Q2
TBD | 90-Day Cure Period | This initiative will automate and streamline reinstatement of Medi-Cal eligibility in CalHEERS by SAWS when additional information needed to complete a redetermination is received within 90 days after discontinuance. This 90-day timeframe is referred to as the “cure period”. This initiative will help align the business processes across systems, and it may be merged with the broader BREfS: Application Life Cycle initiative. | 2024 Q2
TBD | Individual Level Eligibility | This initiative is intended to enhance and streamline the individual level eligibility functionality in CalHEERS. | 2024 Q2
85672 | Medi-Cal Plan Selection | The objective of this initiative is to provide the ability for MAGI Medi-Cal consumers to select a plan within CalHEERS. | 2024 Q3
88353 | Implementation of GI PCP Selection Module and Provider Map | The objective of this initiative is to add functionality to the existing Provider Directory for physicians designated as Primary Care Providers (PCPs). The new functionalities are part of the GI PCP Module: 1) PCP Assignment for QHP 2 ) Network Density Tools: This feature will allows consumers to search an area where they desire coverage and determine in real-time how many providers are active in an area for a health plan issuer. | 2024 Q3
151861 | Change in MEC Value for Aid Code 01 | Effective November 2019, refugees eligible for Medi-Cal aid code 01 are not entitled to Refugee Medical Assistance (RMA) benefits. Because aid code 01 will no longer include RMA benefits, it must NOT be considered Minimal Essential Coverage (MEC) in CalHEERS when the removal of RMA from aid code 01 takes effect. CalHEERS shall update the MEC table value for aid code 01 from TRUE to FALSE. Impacts to SAWS/Counties: SAWS will need to make noticing updates and potentially other changes per the pending ACWDL. | 2024 Q3
165044 | Changing Shop & Compare Defaults to Reduce Choice Errors for Silver 87- and Silver 94-eligible consumers | The intended outcomes will be (1) a substantial reduction in CSR choice errors and (2) enhanced tracking for data analysis. | 2024 Q3
173135 | Enhance eHIT to Transmit Verification Documents Uploaded in CalHEERS to SAWS | Problem Statement: Consumers have the ability to upload outstanding verification documents in the CalHEERS portal. Currently the CalHEERS system does not notify counties/SAWS that Medi-Cal recipients have uploaded verification documents in the CalHEERS portal. In addition, the verification document is not transmitted to SAWS for verification by county eligibility workers. This Change Request will provide the functionality for CalHEERS to notify and send verification document/s to SAWS for county eligibility workers to complete verifications. Intended Outcome: Improved experience for business partners/SAWS. | 2024 Q3
TBD | Consumer Protection Programs | The objective of this initiative is to determine eligibility for the Consumer Protection Programs (CPPs) in the event a consumer lose eligibility in their coverage group. | 2024 Q3
TBD | Explore Horizontal Integration Improvements | Explore Horizontal Integration Improvements | 2024 Q3
122183 | Infants Initiative | The objective of this initiative is to enhance functionality for Medi-Cal Deemed Infants, provide ability to add Medi-Cal Access Program infants (MCAIP) and renewal functionality in CalHEERS | 2024 TBD
125938 | EDD Interface - Employer Address Information | The objective of this initiative is to enhance the EDD interface to collect employer addresses. This will reduce the need for consumers to enter employer contact information. This will ensure CCA has accurate information to send the required employer notifications. | 2024 TBD
132464 | CCHIP Enhancements | To enhance current CCHIP eligibility and renewal functionality in CalHEERS. Adding Pending Eligibility determinations, resulting in update changes to noticing and CCHIP daily extract file. What: The purpose of these changes are to align CCHIP eligibility with the CMS MAGI Medicaid & CHIP Electronic Verification Plan Who: These fixes affect eligibility for CCHIP beneficiaries. Where: CalHEERS currently does not determine a CCHIP child as pending eligible when certain electronic verifications are not reasonably compatible. Conditionally eligible outcomes are not consistent with the approved CMS MAGI Medicaid & CHIP Electronic Verification Plan. Why: If the requested functionality is not added, CCHIP eligibility will not be in compliance with CMS MAGI Medicaid & CHIP Electronic Verification Plan. | 2024 TBD
161090 | Value Based Insurance Design | Covered California would like to implement a Value Based Insurance Design pilot in select regions. Consumers in select regions will be enrolled in VBID plan designs. All consumers in the region will participate. There will be opportunity to opt in or out of this pilot. | 2024 TBD
170935 | Multiple Primary Tax Filers on the same case/application | Problem Statement: Currently, CalHEERS allows only one primary tax filer on a case/application. CalHEERS does not have the ability to calculate separate APTC amounts for multiple primary tax filer households on one case and also to enroll multiple tax households in one plan. Intended Outcome: Update CalHEERS to allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application/enrollment. Update the system to allow multiple different tax households with multiple different APTC amounts for one enrollment. Update the system to prevent any surplus APTC of one APTC tax household from being applied to another APTC tax household (even if both consumers are enrolled in the same plan). Update the system to generate multiple 1095s for multiple tax households that are enrolled on a single enrollment/plan. | 2024 TBD
183098 | Placeholder for Federal Annual Updates | Placeholder for automation improvements / reminder to improve efficiencies, whether process or system efficiencies | 2024 TBD
183209 | Eligibility Notice Generation Enhancement – Phase 2 | Phase 2: The purpose of this initiative is to enhance the CalNOD01 noticing system that lives within the business rules engine that will have the ability to effectively, efficiently, and accurately notice consumers about their eligibility determination. | 2024 TBD
202230 | Build Back Better Plan - Administration 2021 Changes (Phase 1) | Build Back Better Plan - Administration 2021 Changes (Phase 1) | 2024 TBD
TBD | BREfS #5 High Impact Business Validations | This initiative will first require the analysis of the high impact eHIT Business Validations (BVs) to identify potentially redundant or antiquated BVs. Updates to the identified BVs would improve the accuracy and speed of automated eligibility determination results. | 2024 TBD
TBD | BREfS #8 eHIT Enhancement of Data Overlay | This initiative will enable CalHEERS to process eHIT eligibility requests from SAWS without impacting exchange programs by overlaying required data elements. | 2024 TBD
212712 | Google Doc AI Pilot | This is a pilot effort for CalHEERS to adopt the latest technologies to improve the automated document verification rate. This pilot will forecast the improvement of the automated document verification rate that can be achieved using Google Document AI. | N/A - Pilot in Non-Prod, 2022 Q3
213633 | BeyondTrust Privileged Access Management (PAM) system implementation | Privileged account credentials of CalHEERS application are stored and secured by Oracle Privileged Access Manager(OPAM). Current OPAM product version support is ending on 06/2023. Current product does not meet ongoing needs of CalHEERS. It is required to be replaced with a futuristic, robust and modernized PAM solution. | Non-Release: 3/31/23
211307 | MARS-E 2.2 Related Security Changes - Pre OE 2022 | This CR will address the below four Security Related items: in a phased manner with the completion date of R22.9 go live: 1. Due to a new MARS-E 2.2 requirement (CA-8) CalHEERS needs to perform both internal and external penetration testing within every 365 days at the minimum. 2. Due to a new MARS-E 2.2 requirement SI-4 (16) CalHEERS needs to correlate information from monitoring tools employed throughout the infrastructure to get a more comprehensive view of the information system activity. | Non-Release: 9/30/22
203445 | Tax Credit Eligibility Assessment | To effectively administer the income verification activities for the program, Covered California would like to compare the attested income of historical CalHEERS consumers to their filed income at end of the coverage/tax year. This will be accomplished with a Batch job that would fetch the relevant tax related details for consumers using the Existing FTB API. The Data will be persisted in the Data Warehouse for Analysis and Reporting. | Non-Release: TBD
158891 | Create/Assign CalHEERS Unique Person Identifier | The Create/Assign CalHEERS Unique Person Identifier CR aims to create a new CalHEERS Unique Identifier (CUI) that is assigned to all individuals on CalHEERS. Using CUI, CalHEERS will be able to map an individual who has been added multiple times to multiple cases on CalHEERS to a single unique identifier for that individual. | TBD
TBD | Eligibility Results Page Phase II | TBD | TBD