## 24 Month Release Roadmap
Press TAB to move to input areas. Press UP or DOWN ARROW in column A to read through the document
CR # | SUMMARY | FISCAL OWNER | BRIEF DESCRIPTION | RELEASE
247110 | Lawful Presence Updates | Shared | As per the new regulations, DACA recipients will be considered as a valid immigration status to define Lawful Presence and CalHEERS should grant eligibility based on eligibility criteria. | 23.1
200351 | Notices Updates for 23.12 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.12
234868 | DHCS Logo Change | DHCS | Update CalHEERS portal and notices with new DHCS and Medi-Cal to Covered CA logos. | 23.12
200349 | Notices CR for 23.2 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.2
216713 | Apply Soft Pause for Pending Medi-Cal Eligibility (Phase II) | Shared | CalHEERS system will place beneficiaries under Awaiting Review if the individual was determined as Discontinued during SAWS Batch Renewal for MAGI Medi-Cal program. | 23.2
219790 | Removal of Soft Pause indicator when a MAGI Medi-Cal beneficiary moves from non-premium MAGI Medi-Cal to premium MAGI Medi-Cal. | Shared | CalHEERS will not place beneficiaries into Soft Pause when they are moving from a Non-Premium aid code to a Premium aid code for MAGI Medi-Cal. | 23.2
147420 | Administrator Search Enhancements | Shared | Administrator Search Enhancements combines the existing (as of 22.9) Admin Home and Individual Search to put the search functionality on Admin Home, including a navigational header at the top, and including bookmark functionality. | 23.6
190310 | Supplemental Notices Insert and Notices Hold Release | Shared | CalHEERs shall create a Notice page on the portal that contains modules for creating a supplemental notice (content previously known as buck slip) with a notice, creating an admin notice, configuring the active/hold/suppress function of the notices, and creating a box snippet in a notice. | 23.6
199836 | Periodic Verifications No Response from Consumers | Covered CA | This CR provides the functionality to withhold selected populations from the Medicare and Deceased PVC process and discontinue consumers from the appropriate program(s) following the no-response process. | 23.6
209628 | SB260 - ChatBot | Covered CA | The changes requested in CR 209628 is to extend the existing IVR SB260 Opt In/Opt Out functionality/back end APIs to the Covered CA Chat Bot. | 23.6
231783 | Color Printing of NOD01T Flier | Shared | CalHEERS should insert supplemental information (flier in color) in the NOD01T, which is sent to consumers transitioning from MAGI Medi-Cal/CCHIP/MCAP to APTC and they are auto plan selected into a new health plan. | 23.6
200352 | 2024 Renewals | Shared | The functional changes requested in CR 200352 are enhancements to the annual Renewals process based on lessons learned from previous Renewals. | 23.9
200353 | Notices Updates for R23.9 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. | 23.9
216356 | Accelerated Enrollment in SAWS | DHCS | The functional changes requested in CR 216356 is to extend the Accelerated Enrollment for Children and Adults functionality to the SAWS Access Channel. The changes span across eligibility, MEDS, notices, and reporting. This change is configurable. | 23.9
223157 | Negative Actions - Updates to Exchange eligibility | Shared | When a consumer is under active Exchange eligibility and a negative action is applied (Configuration is turned OFF in system), CalHEERS system will determine Discontinuance due to Negative action only when individual is not enrolled in an active plan. | 23.9
224879 | MEC MEDS Check for Exchange Eligibility Programs | Shared | CalHEERS shall update the eligibility rules to utilize the results from a MEDS MEC check while determining eligibility to IAP programs | 23.9
248890 | Enhancement to Disposition functionality to accept IE status for MAGI Medi-Cal Awaiting Review (DS) | DHCS | CalHEERS should use the Disposition with MAGI Medi-Cal Ineligible (IE) status to lift the Awaiting Review Discontinuance status resulting in the final MAGI Medi-Cal eligibility of Discontinued (DS) in CalHEERS and evaluate eligibility for the Exchange programs. | 23.9
228982 | Notices Updates CR for 24.12 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.12
219978 | Admin Override and Enrollment & Shopping enhancements | Covered CA | This CR Provides Enhancements to Admin Portal | 24.2
228956 | Federal Rule Changes for Exchange programs | Covered CA | CalHEERS shall change the Reasonable compatibility % computation for APTC/CAPS/CSR consumers. CalHEERS shall create a new page that allows authorized users to configure reasonable compatibility threshold % and threshold dollar amount. CalHEERS shall evaluate a household as reasonably compatible for income for exchange financial assistance programs (APTC/CSR) if the response code from IRS is “Return information is unavailable”. CalHEERS shall create a new SEP configuration page. | 24.2
228977 | Notices Updates CR for 24.2 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. | 24.2
250237 | Microsite for IEHP | Covered CA | Implement a microsite and co-branded application process for the new Carrier. | 24.2
256054 | Medicare Exchange Errors | DHCS | If the Medicare exchange returns an error for a person aged 19-64, CalHEERS should consider their Medicare status as consistent and unchanged and continue to process the renewal. | 24.3
165890 | ROP Batch - Phase II | Covered CA | Covered CA has to ensure consumers are held accountable for not providing proof of their attested income. The goal of the CR is to have the verification attribute "Household Income - State Subsidy" as one of the configurable attributes for which Reasonable Opportunity Period (ROP) batch functionality can be turned on. | 24.6
173678 | Medicare Coverage Dates | Shared | CalHEERS will persist and read the partial Medicare coverage details from the Medicare response for the benefit year as part of this CR. CalHEERS will only evaluate consumers eligible for a subsidy for months not covered by Medicare.If the response indicates a Medicare Coverage End Date in the future or does not have a Medicare Coverage End Date, the system should be able to determine whether or not the month should be counted as a Medicare covered month. CalHEERS will display the Medicare coverage dates on the Personal Verification Page, and the dates will be consumed by SAWS as a result. | 24.6
203445 | Tax Credit Eligibility Assessment | Covered CA | Covered California is looking to perform analysis of attested income for a prior tax year to the income consumer used on their taxes for that year to identify if APTC / SS amounts were over / under allocated.To perform this analysis, Covered California is looking to run a batch multiple times in a year to get 540 income API response for a consumer population that would be provided by Covered California.CalHEERS will create a new table (FTB_540_AUDIT) within the existing secured schema and invoke the API beginning with the tax year 2019 and onwards to maintain the individuals' history. Once the 540 income API response is received for the consumer population, make the data available for a select Covered California group to conduct the analysis | 24.6
214183 | Eligibility Results page to display the current Eligibility run and Eligibility start date to be determined correctly for prior year application | Shared | The purpose of this CR is to have correct Eligibility results displayed on the Eligibility results page. The system should determine correct Eligibility even though the initial application was for a prior year. | 24.6
228979 | Notices Updates CR for 24.6 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.6
230828 | Affordable Coverage for dependents of ESI – Family Glitch changes | Shared | Covered CA is expecting the following changes: • New functionality to collect the cost of ESI for employee only and entire family. • New functionality to default the responses for the ESI questions based on the information provided for other individuals in the household • Addition of a configurable percentage by benefit year which will be used to calculate ESI affordability threshold. • Change in eligibility status of APTC/CSR/CAPS for the employee when the cost to cover the employee only does not exceed a configurable percentage of total household family income (APTC budget). • Change in eligibility status of APTC/CSR/CAPS for the other household members covered by an employer offer when the cost to cover the entire family does not exceed a configurable percentage of total household family income (APTC budget). • Appropriate updates to Budget worksheet, Eligibility pages, Notices updates (NOD01), Reports | 24.6
257111 | Add DHCS Logo to Medi-Cal Eligibility Confirmation Letter | DHCS | The confirmation letter has both Covered California and DHCS/Medi-Cal logos to ensure the letter is understood to be specific to Medi-Cal, reduce confusion and calls to the Covered California Service Center for this issue. | 24.6
61104 | Implement Plan Dependent Rules | Covered CA | The purpose of this CR is to update CalHEERS to implement the enforcement of plan dependent rules. CalHEERS enrollment grouping rules should include plan dependency definitions, by only allowing Married spouses, Registered domestic partners, Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners, Disabled adult children of any age (including 26 or above) and Siblings under the age of 26 to enroll in the same Covered CA plan. CalHEERS should also prevent enrollment of over-age dependents unless they meet the “disabled child” exception. | 24.9
227922 | Verification Caching Phase IV (VC IV) | Shared | The updates to the personal verification page as well as verification functionality will clarify the functionality for 5 Year Bar and PRUCOL, and will retain the information received from the electronic data sources when an Admin Pass/Fail is received (success or error codes). Implement the HCD redesign of the Personal Verification Page in react framework to align with the CalHEERS application as well as it’s underlying architecture. Ensure that SSN, Income, Non-ESI and ESI verification statuses are appropriate for the response from the electronic source and the consumer attestation. Allows the Admin users to close and recall VLP Step 1 or the step in error after the 24 hour retry period.. | 24.9
228980 | Notices Updates CR for 24.9 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.9
229850 | 2025 Renewals | Shared | The functional changes requested are enhancements to the annual Renewals process based on lessons learned from previous Renewals. The functional changes span across HBX and GI systems including bots to address fall out populations, Account Transfer changes, batch changes, eligibility changes, screen changes, HX20 changes, and enrollment changes. | 24.9
242023 | Continuity of Coverage | Covered CA | CalHEERS should implement a process where continuity of care can be provided to the consumers transitioning from MAGI MC to Covered CA. CalHEERS would be provided with the list of health plans that the consumer was enrolled in through the Medi-Cal coverage, and CalHEERS should factor that information into the APS action that would be taken for the consumer. | 24.9
256054 | Medicare Exchange Errors | DHCS | If the Medicare exchange returns an error for a person aged 19-64, CalHEERS should consider their Medicare status as consistent and unchanged and continue to process the renewal. | 24.9
257891 | SEP Enhancements for 2025 | Shared | Beginning 2025, CalHEERS should allow consumers who are newly eligible due to release from incarceration, consumers who permanently moved to/within CA to enter a QLE date up to 60 days in the future. The effective dating rule for Permanently moved to/within California should also be updated in the configuration table to give eligibility from the first of the month following the QLE date. QLE determination should follow the most advantageous QLE rule and should not override an unexpired QLE with a QLE that is less beneficial to the consumers. Placeholder QLEs should be enhanced such that the portal displays use the effective dates of the QLEs to reflect the correct QLE description that the consumer attested to at the time of the application, thus enabling the placeholder QLE codes to be reused. | 24.9
237063 | Bot - Process for cases with Reasonable Compatibility Changes | Covered CA | Per regulation, CalHEERS should evaluate percent attested income amount is below the income amount received from electronic sources. Using aggregated data pulled by data warehouse team, bot to log into portal “Admin Pass" and re-run eligibility for individuals eligible. | 23.10.3
190570 | 2023 Annual FPL Updates | Shared | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 23.2.2
225474 | RIDP Security Enhancements | Shared | The purpose of this CR is to add a check to validate whether a user has completed the confirm identity process before allowing their intake application to be submitted. | 23.2.2
228555 | Income Update in Effective Dating | Shared | Consumer or admin user will be prevented from entering an income/deduction start date which is later than the end date for a previously ended income/deduction. Also, CalHEERS will capture the Start Date and/or End Date of the Income/Deduction records based on consumer or admin user's input. | 23.2.2
232307 | Automatic eligibility and enrollment updates for consumers via ROP BOT post PCAP | Covered CA | Automating process for consumers with “Pending” or “Not Verified” SSN, MEC, or American Indian/Alaskan Native (AI/AN) past their ROP date. | 23.7.1.2
230676 | Bot - Process for cases with no income data from IRS | Covered CA | Accept the household's attested income, when IRS returns with no income data available, thus making the individual Eligible | 23.9.1
230526 | 2024 Annual FPL Updates | Shared | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 24.2.X (Go-Live: 3/1/24)
246829 | Medi-Cal Backlog | DHCS | This change request aims to update the design document to reflect the process and incorporate any modifications resulting from eligibility-related updates. | DW Release TBD - 1/19/2024
202496 | Automatic eligibility and enrollment updates for consumers via ROP BOT | Covered CA | ROP BOT will perform File Validation, Fail Verification, Eligibility Redetermination, Enrollment, and Reporting for the impacted population provided by CCA. | Non-Release: 3/27/2023
213355 | Manual Trigger of APS | Shared | APS is only triggered from the initial transition transaction. Covered CA needs a manual process to trigger Automatic Plan Selection when a transitioning member changes from unsub to subsidized during the transition period. | 24.2.1

## Pipeline
Press TAB to move to input areas. Press UP or DOWN ARROW in column A to read through the document
CR # | TITLE | FISCAL OWNER | BRIEF DESCRIPTION | RELEASE
40149 | Automation of the Application Missing Information Notice (NOD16) | Shared | The objective of this initiative is to allow admin roles to skip required fields and automatically send the consumer notification of missing information. | 2025 Q2
45901 | SB 1341 AB 617 - BREfS Phase B | Shared | SB 1341 AB 617 - Notice Improvements - The objective of this initiative is to align CalHEERS with Senate Bill 1341 and Assembly Bill 617 and consolidate and send notices for Mixed Households in SAWS. | 2025 Q4
82920 | BREfS Initiative #9: Verifications Only Service and Separation of Verifications by Source | Shared | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and triggers the eligibility business rules engine (BRE) in CalHEERS. CalHEERS uses VIED to coordinate the verifications responses into the BRE and return an eligibility determination via the Determination of Eligibility Response (DER) operation. The intended outcome of this change is to modify both the CalHEERS portal and the eHIT architecture to add a separate Verifications Only service, while continuing to maintain the existing functionality described above for the combined VIED and BRE service. | 2025 Q2
85672 | Medi-Cal Plan Selection | DHCS | The objective of this initiative is to provide the ability for MAGI Medi-Cal consumers to select a plan within CalHEERS. | 2025 Q3
88353 | Implementation of PCP Selection Module and Provider Map | Covered CA | The objective of this initiative is to add functionality to the existing Provider Directory for physicians designated as Primary Care Providers (PCPs). The new functionalities are part of the GI PCP Module: 1) PCP Assignment for Qualified Health Plans (QHP) 2 ) Network Density Tools: This feature will allows consumers to search an area where they desire coverage and determine in real-time how many providers are active in an area for a health plan issuer. | 2025 Q2
96957 | Enhancements to 'Remove an Individual' functionality from CalHEERS access channel | Shared | Provide messaging – Remove a member The objective of this initiative is to ensure downstream processes occur when a consumer requests to remove a household member from a case in CalHEERS. | 2025 TBD
114946 | Consumer Document Upload Functionality and Admin Task Management | Shared | This CR will allow a consumer to upload their own identity proofing documents as alternative to RIDP or following an RIDP failure. It will also provide verification automation and admin verification capabilities. | 2025 TBD
118769 | SAWS Integration with DIVS Solution | Shared | The purpose of this initiative is to incorporate the eHIT changes to align with the integration of the document imaging verification solution. | 2025 TBD
122183 | Infants Initiative | DHCS | The objective of this initiative is to provide functionality for Medi-Cal Deemed Infants, provide ability to add Medi-Cal Access Program infants (MCAIP) and renewal functionality in CalHEERS. This CR will allow parents to enroll infants directly through the online portal. This includes Deemed Infants and non-Deemed, as well as infants enrolled in MCAIP. | 2025 Q1
128730 | Automation of Termination Reason Codes due to Fraud and Medi-Cal Eligibility | Covered CA | The objective of this initiative is to automate reason codes in 835 File Transactions between CalHEERS and Qualified Health Plans (QHP) that are conducted manually currently. | 2026 Q1
132464 | CCHIP Enhancements | DHCS | The purpose of this initiative is to enhance current CCHIP eligibility and renewal functionality in CalHEERS. Adding Pending Eligibility determinations, resulting in update changes to noticing and CCHIP daily extract file. What: The purpose of these changes are to align CCHIP eligibility with the CMS MAGI Medicaid & CHIP Electronic Verification Plan Who: These fixes affect eligibility for CCHIP beneficiaries. Where: CalHEERS currently does not determine a CCHIP child as pending eligible when certain electronic verifications are not reasonably compatible. Conditionally eligible outcomes are not consistent with the approved CMS MAGI Medicaid & CHIP Electronic Verification Plan. Why: If the requested functionality is not added, CCHIP eligibility will not be in compliance with CMS MAGI Medicaid & CHIP Electronic Verification Plan. | 2025 Q1
151332 | MAGI Medi-Cal Income Budget Periods | Shared | This initiative enhances the use of three budget periods to properly align with State law and Federal regulations and the budget period options selected in the State Plan Amendment (SPA). As part of this initiative, the Projected Annual Income (PAI) and Reasonably Predictable Future Income budget periods will be separated to allow for better alignment with current policy. | 2025 TBD
151861 | Change in MEC Value for Aid Code 01 | Shared | Effective November 2019, refugees eligible for Medi-Cal aid code 01 are not entitled to Refugee Medical Assistance (RMA) benefits. Because aid code 01 will no longer include RMA benefits, it must NOT be considered Minimal Essential Coverage (MEC) in CalHEERS when the removal of RMA from aid code 01 takes effect. CalHEERS shall update the MEC table value for aid code 01 from TRUE to FALSE. Impacts to SAWS/Counties: SAWS will need to make noticing updates and potentially other changes per the pending ACWDL. | 2025 Q2
170935 | Multiple Primary Tax Filers on the same case/application | Shared | Problem Statement: Currently, CalHEERS allows only one primary tax filer on a case/application. CalHEERS does not have the ability to calculate separate APTC amounts for multiple primary tax filer households on one case and also to enroll multiple tax households in one plan. Intended Outcome: Update CalHEERS to allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application/enrollment. Update the system to allow multiple different tax households with multiple different APTC amounts for one enrollment. Update the system to prevent any surplus APTC of one APTC tax household from being applied to another APTC tax household (even if both consumers are enrolled in the same plan). Update the system to generate multiple 1095s for multiple tax households that are enrolled on a single enrollment/plan. | 2025 Q3
183100 | SEP Dropdown and Workflow - Phase 2 | Shared | Problem Statement: The Special Enrollment Period (SEP) reasons in the portal is not a comprehensive list that adheres to the federal regulations. The page does not have helpful information and causes confusion to the consumers in the Intake/Report A Change (RAC) flow. Intended Outcome: The SEP reasons in the portal needs to be more intuitive and more helpful to the users: 1. Update and add to the available SEP reasons 2. Update and add to the business rules for each existing and new SEP reason 3. Dynamically display the SEP reasons in the drop down list based on the user role and application mode 4. Update the SEP page language 5. Allow users to capture multiple SEP reasons. System to determine the most advantageous SEP reason. 6. Capture SEP reasons at the household vs individual level. 7. Update eHIT/SAWS accordingly | 2025 Q3
183209 | Eligibility Notice Generation Enhancement – Phase 2 | Shared | Phase 2: The purpose of this initiative is to enhance the CalNOD01 noticing system that lives within the business rules engine that will have the ability to effectively, efficiently, and accurately notice consumers about their eligibility determination. | 2026 TBD
216717 | BREfS Initiative #7 - Carry Forward Enhancements | Shared | BREfS Initiative #7 - Carry Forward Enhancements CR initiative will enhance and streamline the existing Carry Forward process by reducing the number of steps that eligibility workers have to take to lift the Carry Forward and to transition individuals to MAGI Medi-Cal. | 2025 Q2
220303 | BREfS #5 High Impact Business Validations | Shared | This initiative will first require the analysis of the high impact eHIT Business Validations (BVs) to identify potentially redundant or antiquated BVs. Updates to the identified BVs would improve the accuracy and speed of automated eligibility determination results. | 2025 Q1
224724 | Consent to Contact transmitted to MEDS | DHCS | A consent question will be added to CalHEERS to capture a “yes” or “no” response and modes in which the individual may be contacted. This consent and contact information will be stored in the CalHEERS systems and sent/received via eHIT to SAWS. For CCHIP and MCAP, This consent and contact information will be stored in the CalHEERS systems and added to the daily extract file that is generated for Maximus. | 2025 TBD
227448 | BREfS #8 eHIT Enhancement of Data Overlay | Shared | This initiative will enable CalHEERS to process eHIT eligibility requests from SAWS without impacting exchange programs by overlaying required data elements. | 2025 Q1
227501 | Modernize Notices Generation tool | Infrastructure | Adobe Experience Manager (AEM) forms component is the Document Management System used for generating correspondence notices for CalHEERS. Adobe has notified that they will be changing their licensing model in 2023 from the current core-based licensing. State and Deloitte will need to find a replacement and modernize the document management solution to support the continued functionality of notices in CalHEERS. | 2025 Q2
228450 | CalHEERS security groups will be centralized for all accounts using AWS Firewall Manager | Infrastructure | AWS Firewall Manager's centralized solution enables visibility, network controls over common security groups, as well as content and usage audit security group policies. | 2025 Q1
232889 | CalHEERS API Exposure to Support CCA Chatbot and IVR Password Reset and Unblock Functions | Covered CA | Allow Chabot and IVR consumers to create a fully authenticated session. Allow Chabot and IVR consumers to unblock accounts and reset passwords through a user validation process. | TBD
233034 | Inclusion of Reasonable Explanation to CalHEERS | DHCS | Incorporate reasonable explanations into CalHEERS as part of the application, renewal and change in circumstance process, when income is unable to be electronically verified with the following: • A drop down menu of reasonable explanations for a MAGI Medi-Cal applicant or beneficiary to choose from when income is not reasonably compatible, • The ability for CalHEERS to either verify or pend income when specific reasonable explanations are selected by the applicant or beneficiary, and • Allow for reasonable explanations within CalHEERS to be sent to the SAWS via electronic health information transfer (eHIT). | 2025 Q1
238808 | Enroller Portal Splunk Integration | Covered CA | This CR will support CalHEERS additional resources to 1) Configure Splunk Cloud as a log aggregator for Covered California’s critical systems, networks, and devices and 2) Generate reports, alerts, and dashboards as an leading practice, for use by Covered California . | TBD
249764 | Consumers moving out of region | Covered CA | CalHEERS should identify and give appropriate Portal messaging to consumers who updated their address to a region in which their current plan is not available, and they have not updated their enrollment. NOD01 snippet updates need to be made, to notify the consumer that the plan that they are currently enrolled in is not valid in the region that they have moved to. CalHEERS should also have the capability to terminate the enrollment (end of month) when the SEP has ended if enrollment has not been updated. | 2025 Q1
250226 | Consumer Take Away Pages | Covered CA | Enrollers will be able to easily and quickly save and/or print take-away material including QHP/QDP quote and enrollment details, plan cost, and delegation information after a session with a Consumer. The ability for an Enroller save and provide the consumer a clean, printable page for their records will aid in efforts to enroll more qualifying Californians into a QHP/QDP. | 2025 Q1
250248 | New Intermediate Table related to CCP Income Tables for Analytics enhancements | Covered CA | CalHEERS shall create a new intermediate table for CCP budget calculation with a similar structure as MAGI Medi-Cal budget calculation table(ELIG_BUDGET_INCOME_DETL). | 2025 Q2
251718 | Unsubsidized Medi-Cal Transitioners (MCTs) due to "planning to file taxes" application question | Shared | Executive leadership is requesting CalHEERS portal enhancements to educate consumers (and admin/enroller users who assist consumers) on the CalHEERS portal about updating their tax information to be assessed for subsidies that they would otherwise be eligible to/assessed for. Portal design enhancements may include, but are not limited to, messaging and UI/UX modifications in various places to educate and inform consumers of consequences of not filing taxes and its impact on their subsidies. | 2025 Q2
251910 | Modifications to the Admin search results page | Covered CA | To enable the admin user to search and view results that allow the admin to efficiently identify the correct case to utilize for subsequent actions as needed to assist the consumer. The desires is to have SSN and DOB viewable in the search results table for all household members on a case. To enable the user to navigate to the case specific flex app from the search results page. | 2025 Q1
253304 | Verification Documents sent to CalHEERS from CalSAWS | Shared | A transfer mechanism is required for CalSAWS to be able to send hard copy of the verifications documents used to substantiate their Administrative Verification | 2025 Q1
253663 | MAGI MC Disposition Processing prior to APS Triggers for SB260 | Shared | Update CalHEERS logic to require a disposition be processed prior to effectuating a MAGI MC discontinuance, triggering APS, and transitioning a MC beneficiary to Covered CA programs. This should apply to both negative actions sent in eHIT or eligibility changes that would result in a discontinuance. The disposition finalizes the eligibility change from counties and SAWS and it should meet the 10-day notice requirement. | 2025 TBD
255076 | PCAP Admin Portal view of 834 transaction content | Covered CA | PCAP Admin Portal view of 834 transaction content | 2025 Q3
255968 | Enrollment UI Enhancements, Phase 4 | Covered CA | UI changes to address unintended gaps/issues identified in PCAP implementation of 193144 and restore existing functionality in Production before PCAP implementation | 2025 Q1
256055 | Collect Electronic Verification of Income Data for Noncitizens | Shared | Verify income through the Franchise Tax Board (FTB) interface using Individuals Taxpayers Identification Numbers (ITINs). Eliminate the requirements that an individual must have SSA data to verify their income. Income verification is currently blocked on verifying Title II income via SSA, which does not accept ITINs. Title II income is not available to individuals without SSNs, so this rule should be removed. | 2025 TBD
256174 | Enhance processing of 1095 and 3895 architecture | Covered CA | The intended outcome for CalHEERS is enhance the system and to generate the 1095/3895 Payloads/form correctly as per the IRS/FTB guidelines. | 2024 Q3
257485 | MEDS Enhancements to Improve Data Integrity | DHCS | Improved synchronization between CalHEERS and MEDS, resulting in correct application of eligibility data in MEDS. | 2025 TBD
258142 | Update 90-Day Cure Period to accept Information received as a New Application | Shared | This initiative will support the automation changes needed to align with CMS policy clarifications regarding the treatment of a submitted renewal during the 90 day cure period as a new application. This 90-day timeframe is referred to as the “cure period”. This initiative will help align the business processes across systems, including SAWS and county business process changes. | 2025 Q3
258401 | Microbatch - Modernize legacy batches to a micro batch architecture - Phase 2 | Covered CA | By implementing the solution in advance of OE 2025 renewal cycle, annual passive renewal and tax batches would complete on schedule, allowing: • Timely transmission of files - such as monthly Carrier files, monthly IRS files, monthly CMS payment files. • Timely transmission of Meds reconciliation files • Timely transmission of notices to the consumers | 2025 Q2
258711 | CalHEERS Provider Directory - Molina and Kaiser File Processing Off Cycle | Covered CA | Molina and Kaiser unable to provide a complete provider directory file before the file cutoff window, resulting in a data issue. This CR is to run an out-of-cycle carrier data load to ensure the provider files uploaded with the latest data. | Non-Release TBD
258882 | Individual Level Eligibility | Shared | CalHEERS and SAWS will work in conjunction to enhance ILE in the systems to remove the necessity for county eligibility worker workarounds. The enhancements must continue to allow for income to be admin failed on an individual basis, without affecting other household members that are dependent on that income, if the income for those members has already been e-verified. | 2025 Q2
258883 | Continuous Coverage of Children Ages 0-4 | DHCS | CalHEERS will build functionality to maintain Medi-Cal and Children’s Health Initiative Program (CHIP) eligibility for children until the child reaches age 5. Annual renewals for children ages 0-4 would only check for: · Age out · Loss of state residence. · Voluntary requests for disenrollment · Child’s death Children would receive a full redetermination when reaching the age of 5. | 2025 Q1
TBD | Devsecops modernization - Phase 1 | Infrastructure | A modernized CalHEERS DevSecOps platform incrementally providing capabilities, DevSecOps Data Lake that gives insights into the CalHEERS system at all levels of the organization, Tighter unification of software development, security, and operations processes for faster time to market adoption and early integration of leading security practices into software development and operations to identify and address vulnerabilities early on, reducing the risk of security breaches and data leaks. | 2025 Q2
TBD | Devsecops modernization - Phase 2 | Infrastructure | A modernized CalHEERS DevSecOps platform incrementally providing capabilities, DevSecOps Data Lake that gives insights into the CalHEERS system at all levels of the organization, Tighter unification of software development, security, and operations processes for faster time to market adoption and early integration of leading security practices into software development and operations to identify and address vulnerabilities early on, reducing the risk of security breaches and data leaks. | 2025 Q4
TBD | Data Obfuscation / Test Data Fidelity | Infrastructure | Establish an approach to copy masked Production cases into testing, performance, and training environments for enhanced prod-like simulations and improved validations. | 2025 Q1
TBD | Explore Horizontal Integration Improvements | Shared | Placeholder CR to Explore Horizontal Integration Improvements | 2026 Q4
257848 | Consumer Protection Program (CPP) Eligibility Determination | Shared | The objective of this initiative is to determine eligibility for the Consumer Protection Programs (CPPs) in the event the consumer experiences a loss of eligibility in their coverage group. | 2025 Q2