## 24 Month Release Roadmap
Press TAB to move to input areas. Press UP or DOWN ARROW in column A to read through the document.
CalHEERS
2024 - 2025 CRs / Initiatives
CR # | SUMMARY | FISCAL OWNER | BRIEF DESCRIPTION | RELEASE (if value is a date, the CR is non-release) | AB1296 Category | 24 Mo Business Goal | Prioritization Category
228982 | Notices Updates CR for 24.12 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.12 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
262775 | R24.12 UI enhancements - placeholder | Shared | A regular Change Request for each system release would make it easier to track smaller but important portal changes. This is a placeholder similar to Notices and Reporting. | 24.12 | User Experience Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Enhancement CR
219978 | Admin Override and Enrollment & Shopping enhancements | Covered CA | This CR Provides Enhancements to Admin Portal | 24.2 | Worker Productivity Updates | 3. Authorized End Users are appropriately equipped with tools and trained to serve consumers effectively and to handle exceptional situations. | Enhancement CR
228956 | Federal Rule Changes for Exchange programs | Covered CA | CalHEERS shall change the Reasonable compatibility % computation for APTC/CAPS/CSR consumers. CalHEERS shall create a new page that allows authorized users to configure reasonable compatibility threshold % and threshold dollar amount. CalHEERS shall evaluate a household as reasonably compatible for income for exchange financial assistance programs (APTC/CSR) if the response code from IRS is “Return information is unavailable”. CalHEERS shall create a new SEP configuration page. | 24.2 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
228977 | Notices Updates CR for 24.2 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. | 24.2 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
250237 | Microsite for IEHP | Covered CA | Implement a microsite and co-branded application process for the new Carrier. | 24.2 | Partner Interface Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Program Support Services
257110 | Retain the MAGI Medi-Cal valid discontinuance during the Continuous Coverage Period | Shared | If the Medicare exchange returns an error for a person aged 19-64, CalHEERS should consider their Medicare status as consistent and unchanged and continue to process the renewal. | 24.2 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
259525 | “No Wrong Door” UX Enhancements | DHCS | CalHEERS shall add Medi-Cal banner on Account Home and Log-In page to enhance rate of Medi-Cal renewals and improved UX. | 24.2 | User Experience Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Enhancement CR
165890 | ROP Batch - Phase II | Covered CA | Covered CA has to ensure consumers are held accountable for not providing proof of their attested income. The goal of the CR is to have the verification attribute "Household Income - State Subsidy" as one of the configurable attributes for which Reasonable Opportunity Period (ROP) batch functionality can be turned on. | 24.6 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
173678 | Medicare Coverage Dates | Shared | CalHEERS will persist and read the partial Medicare coverage details from the Medicare response for the benefit year as part of this CR. CalHEERS will only evaluate consumers eligible for a subsidy for months not covered by Medicare.If the response indicates a Medicare Coverage End Date in the future or does not have a Medicare Coverage End Date, the system should be able to determine whether or not the month should be counted as a Medicare covered month. CalHEERS will display the Medicare coverage dates on the Personal Verification Page, and the dates will be consumed by SAWS as a result. | 24.6 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
203445 | Tax Credit Eligibility Assessment | Covered CA | Covered California is looking to perform analysis of attested income for a prior tax year to the income consumer used on their taxes for that year to identify if APTC / SS amounts were over / under allocated.To perform this analysis, Covered California is looking to run a batch multiple times in a year to get 540 income API response for a consumer population that would be provided by Covered California.CalHEERS will create a new table (FTB_540_AUDIT) within the existing secured schema and invoke the API beginning with the tax year 2019 and onwards to maintain the individuals' history. Once the 540 income API response is received for the consumer population, make the data available for a select Covered California group to conduct the analysis | 24.6 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
214183 | Eligibility Results page to display the current Eligibility run and Eligibility start date to be determined correctly for prior year application | Shared | The purpose of this CR is to have correct Eligibility results displayed on the Eligibility results page. The system should determine correct Eligibility even though the initial application was for a prior year. | 24.6 | Partner Interface Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
224268 | AB2530 Subsidies for Strike/Lockout Workers | Shared | This CR will have CalHEERS implement a new program based on AB 2530 for Strike/Lockout Benefits, for consumers who specify that their Loss of MEC is due to a labor dispute. | 24.6 | New Programs | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
228979 | Notices Updates CR for 24.6 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.6 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
230828 | Affordable Coverage for dependents of ESI – Family Glitch changes | Covered CA | Covered CA is expecting the following changes: • New functionality to collect the cost of ESI for employee only and entire family. • New functionality to default the responses for the ESI questions based on the information provided for other individuals in the household • Addition of a configurable percentage by benefit year which will be used to calculate ESI affordability threshold. • Change in eligibility status of APTC/CSR/CAPS for the employee when the cost to cover the employee only does not exceed a configurable percentage of total household family income (APTC budget). • Change in eligibility status of APTC/CSR/CAPS for the other household members covered by an employer offer when the cost to cover the entire family does not exceed a configurable percentage of total household family income (APTC budget). • Appropriate updates to Budget worksheet, Eligibility pages, Notices updates (NOD01), Reports | 24.6 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
231622 | Intelligent Document Verification Platform | Shared | Deloitte Intelligent Document Verification API enabled by google Doc AI and RedHat Rules Engine | 24.6 | User Experience Updates | 3. Authorized End Users are appropriately equipped with tools and trained to serve consumers effectively and to handle exceptional situations. | Tech Refresh
232582 | Update the existing SCR Read-Only role in CalHEERS and update the Security Role Matrix to reflect their access. | Shared | Update the existing SCR Read-Only role so that this user can see the pages, the data on the pages in the CalHEERS portal, and update the Security Role Matrix to reflect their access. The SCR Read-Only role should not be able to edit any CalHEERS data. | 24.6 | Administrator Screen Enhancements | 3. Authorized End Users are appropriately equipped with tools and trained to serve consumers effectively and to handle exceptional situations. | Technical Updates
257111 | Add DHCS Logo to Medi-Cal Eligibility Confirmation Letter | DHCS | The confirmation letter has both Covered California and DHCS/Medi-Cal logos to ensure the letter is understood to be specific to Medi-Cal, reduce confusion and calls to the Covered California Service Center for this issue. | 24.6 | Notice Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Enhancement CR
61104 | Implement Plan Dependent Rules | Covered CA | The purpose of this CR is to update CalHEERS to implement the enforcement of plan dependent rules. CalHEERS enrollment grouping rules should include plan dependency definitions, by only allowing Married spouses, Registered domestic partners, Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners, Disabled adult children of any age (including 26 or above) and Siblings under the age of 26 to enroll in the same Covered CA plan. CalHEERS should also prevent enrollment of over-age dependents unless they meet the “disabled child” exception. | 24.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
173135 | BREfS: Enhance eHIT to Transmit Verification Documents Uploaded in CalHEERS to SAWS | DHCS | The purpose of this CR is to notify and send verification document/s to SAWS for county eligibility workers to complete verifications | 24.9 | Infrastructure Enhancements | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Technical Updates
206195 | Alternative Formats | Shared | The purpose of this CR is to add a question to CalHEERS Single Streamlined Application/FlexiApp for consumers to indicate alternative format preferences, send and receive consumer alternative format preferences with SAWS, and create a framework to send notices in the consumer's alternative format preference. | 24.9 | User Experience Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | New Policy & Legislative Changes
227922 | Verification Caching Phase IV (VC IV) | Shared | The updates to the personal verification page as well as verification functionality will clarify the functionality for 5 Year Bar and PRUCOL, and will retain the information received from the electronic data sources when an Admin Pass/Fail is received (success or error codes). Implement the HCD redesign of the Personal Verification Page in react framework to align with the CalHEERS application as well as it’s underlying architecture. Ensure that SSN, Income, Non-ESI and ESI verification statuses are appropriate for the response from the electronic source and the consumer attestation. Allows the Admin users to close and recall VLP Step 1 or the step in error after the 24 hour retry period.. | 24.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
228980 | Notices Updates CR for 24.9 | Shared | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.9 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
229850 | 2025 Renewals | Shared | The functional changes requested are enhancements to the annual Renewals process based on lessons learned from previous Renewals. The functional changes span across HBX and GI systems including bots to address fall out populations, Account Transfer changes, batch changes, eligibility changes, screen changes, HX20 changes, and enrollment changes. | 24.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
242023 | Continuity of Coverage | Covered CA | CalHEERS should implement a process where continuity of care can be provided to the consumers transitioning from MAGI MC to Covered CA. CalHEERS would be provided with the list of health plans that the consumer was enrolled in through the Medi-Cal coverage, and CalHEERS should factor that information into the APS action that would be taken for the consumer. | 24.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
250042 | Enhancements to State-Level CSR | Covered CA | The following needs to be addressed so that Covered CA has the option to turn ON the functionality for Enhanced CSR, if needed for a future benefit year: - CalHEERS should send the enhanced CS level to the enrollment system and the system should determine the applicable Silver level plans depending on the CS levels. - When the Enhanced CSR amount and Baseline CSR amount are the same, 2750 loop with N102 “SUPPLEMENTAL CSR AMT” and REF02 with the calculated supplemental CSR amount (Enhanced CSR amount – Baseline CSR amount) as 0.00 should be sent. This was logged in SIR 213957. - The calculation for Enhanced CSR functionality should be based on PMPM computation which will use the rating region, and FPL of the household into consideration. - Shop and Compare tool for a benefit year should use the CSR configuration that is set for a benefit year in CalHEERS application and display the plans accordingly. | 24.9 | New Programs | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
256054 | Medicare Exchange Errors | DHCS | If the Medicare exchange returns an error for a person aged 19-64, CalHEERS should consider their Medicare status as consistent and unchanged and continue to process the renewal. | 24.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
256142 | Failure to Reconcile enhancements | Covered CA | CalHEERS should have the ability to utilize the new Failure to Reconcile response codes within our existing Failure to Reconcile logic. Changes to the following functionality need to be implemented with the new FTR code: - Configuration page for FTR - Tax attestation - Eligibility Determination - Portal pages for eligibility snippets - Notices - Reporting | 24.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
257891 | SEP Enhancements for 2025 | Covered CA | Beginning 2025, CalHEERS should allow consumers who are newly eligible due to release from incarceration, consumers who permanently moved to/within CA to enter a QLE date up to 60 days in the future. The effective dating rule for Permanently moved to/within California should also be updated in the configuration table to give eligibility from the first of the month following the QLE date. QLE determination should follow the most advantageous QLE rule and should not override an unexpired QLE with a QLE that is less beneficial to the consumers. Placeholder QLEs should be enhanced such that the portal displays use the effective dates of the QLEs to reflect the correct QLE description that the consumer attested to at the time of the application, thus enabling the placeholder QLE codes to be reused. | 24.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
258400 | Modernize time-sensitive annual batches | Infrastructure | By implementing the solution in advance of OE 2025 renewal cycle, annual passive renewal and tax batches would complete on schedule, allowing: • Timely receipt of January APTC payments and carrier invoices to the consumers • Timely receipt of tax forms to consumers | 24.9 | Annual Renewals | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Innovation & Continuous Improvement
260133 | Enroller Portal/Salesforce Enhancements for 24.9 involving HBX/SF Integration | Covered CA | Implementation of functionality and features that will improve or not disrupt day-to-day operations for external and internal users. · Enhancements to SF Lead Application and Objects · Recording of SmartyStreet selection and SmartyStreet/Lightweight service responses · Enhancement to LMS integration with SF regarding LMS training status (Inactive) | 24.9 | Agent Sales & Carrier Integration | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
261916 | SOGI Questions Enhancements to Collect Intersexuality | Shared | CalHEERS will modify the existing SOGI questions to collect information about intersexuality. CalHEERS will modify eHIT to share the information between CalHEERS and CalSAWS consistent with how SOGI information is shared today. CalHEERS will submit the information to MEDS consistent with how the information is submitted to MEDS today. CalHEERS shall have the SOGI questions in the application flow as optional data collection items. The data collected for the questions will be sent in 834 transactions. | 24.9 | User Experience Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Enhancement CR
189273 | Implement Eligibility Functionality for Family Planning, Access, Care and Treatment (Family PACT) Program in CalHEERS | DHCS | CalHEERS shall add the Family PACT application and eligibility process to the CalHEERS Portal and BRE, automate integration with MEDS, automate referrals for other IAP programs, and provide appropriate notices and messaging to Family PACT clients and Family PACT providers. Family PACT program aid code 8H is not considered MEC and shall not impact current CalHEERS functionality for determining eligibility for IAP programs. | 25.1 | New Programs | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
252585 | Notices Updates for R25.12 | Shared | This Notices Updates CR is the result of the Long Term Notices Design Approach. Any CR in 25.12 Release that has notice requirements will be moved to this CR. Additional business requirements, unrelated to 25.12 Change Requests, may be added to this CR upon approval of a Decision Item for additional scope. | 25.12 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
220303 | BREfS #5 High Impact Business Validations | Shared | Improve the success rate of eHIT transactions sent to CalHEERS to facilitate eligibility determinations for MAGI MC and in ICT situations. | 25.2 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
228450 | CalHEERS security groups will be centralized for all accounts using AWS Firewall Manager | Infrastructure | AWS Firewall Manager's centralized solution enables visibility, network controls over common security groups, as well as content and usage audit security group policies. | 25.2 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Security
249764 | Consumers moving out of region | Covered CA | CalHEERS should identify and give appropriate Portal messaging to consumers who updated their address to a region in which their current plan is not available, and they have not updated their enrollment. NOD01 snippet updates need to be made, to notify the consumer that the plan that they are currently enrolled in is not valid in the region that they have moved to. CalHEERS should also have the capability to terminate the enrollment (end of month) when the SEP has ended if enrollment has not been updated. | 25.2 | CalHEERS - Efficiency Improvements | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
251910 | Modifications to the Admin search results page | Covered CA | To enable the admin user to search and view results that allow the admin to efficiently identify the correct case to utilize for subsequent actions as needed to assist the consumer. The desires is to have SSN and DOB viewable in the search results table for all household members on a case. To enable the user to navigate to the case specific flex app from the search results page. | 25.2 | Administrator Screen Enhancements | 3. Authorized End Users are appropriately equipped with tools and trained to serve consumers effectively and to handle exceptional situations. | Enhancement CR
252582 | Notices Updates for R25.2 | Shared | This Notices Updates CR is the result of the Long Term Notices Design Approach. Any CR in 25.3 Release that has notice requirements will be moved to this CR. Additional business requirements, unrelated to 25.2 Change Requests, may be added to this CR upon approval of a Decision Item for additional scope. | 25.2 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
253304 | Verification Documents sent to CalHEERS from CalSAWS | Shared | A transfer mechanism is required for CalSAWS to be able to send hard copy of the verifications documents used to substantiate their Administrative Verification | 25.2 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
253341 | Multifactor Authentication for Consumers | Shared | MARS-E compliance recommends mandatory multifactor authentication methods be utilized for consumers to protect against security breaches. CalHEERS does not currently require MFA for consumers. | 25.2 | User Experience Updates | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Security
253663 | MAGI MC Disposition Processing prior to APS Triggers for SB260 | Shared | Update CalHEERS logic to require a disposition be processed prior to effectuating a MAGI MC discontinuance, triggering APS, and transitioning a MC beneficiary to Covered CA programs. This should apply to both negative actions sent in eHIT or eligibility changes that would result in a discontinuance. The disposition finalizes the eligibility change from counties and SAWS and it should meet the 10-day notice requirement. Please note that this section will be updated after a discovery session is complete. | 25.2 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
255968 | Enrollment UI Enhancements, Phase 4 | Covered CA | Phase 4 implementation (original CR 246135 for Phase 1) SCRs are experiencing pain points related to changes in the User Interface post PCAP implementation due to gaps/issues in the design | 25.2 | Administrator Screen Enhancements | 3. Authorized End Users are appropriately equipped with tools and trained to serve consumers effectively and to handle exceptional situations. | Enhancement CR
257849 | Zero Income Reasonable Compatibility Conditions | DHCS | Medi-Cal members who self-attest to zero income, will meet reasonable compatibility conditions when information is received from one of the electronic sources (i.e., SSA, FTB, EDD, IRS, or VCI) to pass ex-parte and e-verify the self-attested zero income. | 25.2 | New Programs | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
258401 | Modernize batches – Notices (Eligibility) | Infrastructure | By implementing the solution in advance of OE 2025 renewal cycle, annual passive renewal and tax batches would complete on schedule, allowing: • Timely transmission of files - such as monthly Carrier files, monthly IRS files, monthly CMS payment files. • Timely transmission of Meds reconciliation files • Timely transmission of notices to the consumers | 25.2 | Annual Renewals | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Technical Updates
262000 | Update to Medi-Cal Eligibility Confirmation Letter | DHCS | This CR intends to make changes to the current Medi-Cal Eligibility Confirmation Letter which would allow the document to meet the requirements of a true temporary BIC for cases where accelerated enrollment has been initiated. This CR will require concurrent changes in MEDS to facilitate the activation and expiration of temporary BICs issued through CalHEERS. | 25.2 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
TBD | Data Obfuscation / Test Data Fidelity | Infrastructure | Establish an approach to copy masked Production cases into testing, performance, and training environments for enhanced prod-like simulations and improved validations. | 25.2 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Security
266495 | Enroller Portal/Salesforce Enhancements for 25.2 involving HBX/SF Integration | Covered CA | HBX - SF Integration Changes for 25.2 | 25.2 | Agent Sales & Carrier Integration | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
TBD | Cloud Security Posture Management (CSPM) | Infrastructure | CalHEERS leading to multi cloud strategy shall require a CSPM that identifies and remediates risk by automating visibility, uninterrupted monitoring, threat detection, and remediation workflows to search for misconfigurations across diverse cloud environments/infrastructure to keep our system secure and complaint. | 25.2 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Enhancement CR
227501 | Modernize Notices Generation tool | Infrastructure | Migrating to Adobe's SaaS cloud platform is aligned to CalHEERS adoption of cloud native solutions and future-ready approach for technology modernization. | 25.4 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Technical Updates
TBD | SNOW Configuration Management Database (CMDB) | Infrastructure | CalHEERS growing infrastructure and services footprint makes our system prone to misconfigurations and other changes leading to increased risk exposures. An effective CMDB solution shall help CalHEERS to makes it possible for risk management activities to take place prior to implementing the change, thereby significantly bringing the risk down. | 25.4 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Security
TBD | IDP Phase II | Shared | This is phase 2 of CR 231622 Intelligent Document Processing (IDP) System. It will include ~25 additional doc types and UX updates. | 25.4 | CalHEERS - Efficiency Improvements | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Security
88353 | Implementation of PCP Selection Module and Provider Map | Covered CA | This functionality is desired by PMD to provide additional information to consumers and assist carriers with understanding their consumers by providing information on the provider selection for those plans that do not require that the consumer select a Primary Care Physician. Currently, carriers assign consumers to providers, even though it is not mandatory that the consumers see the assigned physician. This satisfies the internal requirement that each subscriber have a PCP on record. | 25.6 | CalHEERS - Efficiency Improvements | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
114946 | Consumer Document Upload Functionality and Admin Task Management | Shared | This CR is split from CR 99895 and includes consumer document upload functionality requirements and task management as a result of that upload functionality. | 25.6 | CalHEERS - Efficiency Improvements | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Program Support Services
216717 | BREfS Initiative #7 - Carry Forward Enhancements | Shared | This initiative would enhance and streamline the existing Carry Forward process by reducing the number of steps that eligibility workers are required to take in the current system when transitioning individuals to MAGI MC. Due to SAWS migration, this CR may require two phases (pre and post migration). Create the ability for a profile driven Carry Forward Flag Lift Override feature through the ServiceNow Ticketing via an established process to be determined for cases stuck in Carry Forward status after the SAWS case has been discontinued. | 25.6 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
227448 | BREfS #8 eHIT Enhancement of Data Overlay | Shared | Data that was sent from SAWS to CalHEERS is not correctly syncing with the correct data overlay. The expectation is for the system to compare data elements from SAWS and CalHEERS and to identify missing elements or gaps. | 25.6 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
233034 | Inclusion of Reasonable Explanation to CalHEERS | DHCS | Incorporate reasonable explanations into CalHEERS as part of the application, renewal and change in circumstance process, when income is unable to be electronically verified with the following: • A drop down menu of reasonable explanations for a MAGI Medi-Cal applicant or beneficiary to choose from when income is not reasonably compatible, • The ability for CalHEERS to either verify or pend income when specific reasonable explanations are selected by the applicant or beneficiary, and • Allow for reasonable explanations within CalHEERS to be sent to the SAWS via electronic health information transfer (eHIT). | 25.6 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | New Policy & Legislative Changes
251718 | Unsubsidized Medi-Cal Transitioners (MCTs) due to "planning to file taxes" application question | Shared | Executive leadership is requesting CalHEERS portal enhancements to educate consumers (and admin/enroller users who assist consumers) on the CalHEERS portal about updating their tax information to be assessed for subsidies that they would otherwise be eligible to/assessed for. Portal design enhancements may include, but are not limited to, messaging and UI/UX modifications in various places to educate and inform consumers of consequences of not filing taxes and its impact on their subsidies. | 25.9 | Administrator Screen Enhancements | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
252583 | Notices Updates for R25.6 | Shared | This Notices Updates CR is the result of the Long Term Notices Design Approach. Any CR in 25.3 Release that has notice requirements will be moved to this CR. Additional business requirements, unrelated to 25.6 Change Requests, may be added to this CR upon approval of a Decision Item for additional scope. | 25.6 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
254836 | Federal Annual Updates for 2025 | Shared | The CR is to address the changes in the NBPP for the year 2025. | 25.6 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | New Policy & Legislative Changes
257485 | MEDS Enhancements to Improve Data Integrity | DHCS | Improved synchronization between CalHEERS and MEDS, resulting in correct application of eligibility data in MEDS. | 25.6 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
258142 | Update 90-Day Cure Period to accept Information received as a New Application | DHCS | This initiative will support the automation changes needed to align with CMS policy clarifications regarding the treatment of a submitted renewal during the 90 day cure period as a new application. This 90-day timeframe is referred to as the “cure period”. This initiative will help align the business processes across systems, including SAWS and county business process changes. | 25.6 | Business Rule Exposure for SAWS (BREfS) | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | New Policy & Legislative Changes
266496 | Enroller Portal/Salesforce Enhancements for 25.6 involving HBX/SF Integration | Covered CA | HBX - SF Integration Changes for 25.6 | 25.6 | Agent Sales & Carrier Integration | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
TBD | Automated Access Evaluation and Certification | Infrastructure | CalHEERS must undergo an access certification for all internal user on quarterly basis. This process is currently manual, time consuming and prone to human error. An automated process shall help CalHEERS to meet this compliance in timely manner with higher accuracy. | 25.6 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Security
82920 | BREfS Initiative #9: Verifications Only Service and Separation of Verifications by Source | Shared | • Retain the MAGI Medi-Cal business rules and electronic verification services within CalHEERS. • Create a simple and distinct electronic verification service, decoupled from the eligibility Business Rules Engine, that is accessible both via the CalHEERS portal and to SAWS via eHIT. • Provide the ability to request separate verifications by verification source both via the CalHEERS portal and to SAWS via eHIT. • Facilitate long-term sustainability, maintainability, and scalability of the eHIT interface. • Reduce the maintenance effort of MAGI Medi-Cal eligibility rules and the eHIT interface. • Minimize the overall amount of transactions from the current eHIT architecture by eliminating the need for all transactions to run through the existing single combined VIED and BRE service. • Help mitigate the impact of the daily FDSH outages that occur during the SAWS batch windows. • Utilize a single schema to support all operations whenever possible. • Provide an electronic verification service that can be leveraged for potential use with Non-MAGI Medi-Cal and/or other non-health programs in the future. ***The ICR is not final-Sponsors request a full evaluation and updates with all partners during discovery sessions. | 25.9 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
144390 | CalHEERS MEDS Reconciliation File Enhancements | Shared | The CalHEERS system currently maintains eligibility information for the COV-CA, MCAP, CCHIP, State Inmate, and Parole programs. CalHEERS sends information for these programs to DHCS for capture on the MEDS (Medi-Cal Eligibility) system. MEDS should be reconciled periodically with CalHEERS for consumers eligible for these programs (excluding Medi-Cal eligibility records). The data is currently being sent by CalHEERS on a monthly basis using the MEDS transaction RX20. In order for the RX20 transactions to process correctly through the existing MEDS Reconciliation process as mirrored by the SAWS-MEDS reconciliation process, CalHEERS must only submit data that meets certain validation requirements. | 25.9 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
151332 | MAGI Medi-Cal Income Budget Periods | Shared | Intended Outcomes •PAI functionality will be added to CalHEERS to determine eligibility to MAGI Medi-Cal, MCAP, and CCHIP as a separate budget period aligning with the federal regulations and be based on the calendar year income. •PAI functionality will only apply to beneficiaries, not applicants. •A redetermination of eligibility will be prompted at the end of the calendar when the PAI budget period is used. | 25.9 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
183209 | Eligibility Notice Generation Enhancement – Phase 2 | Shared | In OPA Based NOD01 Phase 2 , the final intended outcome would be for the NOD01 to be generated with relevant eligibility snippets and action snippets that happened across multiple BRE runs on the day. This would lead to better details on the NOD01 and will print relevant information from an action which may not have happened in the latest BRE run for the day. Currently NOD01 is not triggered when a Negative Action or Rescind is received from SAWS. This will be addressed with this CR as well. (We may pull this functionality into previous Notice CR). Suppression of notices should have a more streamlined process, where Covered CA would be able to submit a list of cases and the NOD01s for those cases should be suppressed. CalHEERS should be able to generate an alternate version of NOD01 with a dynamic snippet that can be provided and built on a short notice. | 25.9 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Innovation & Continuous Improvement
224724 | Consent to Contact transmitted to MEDS | DHCS | A consent question will be added to CalHEERS to capture a “yes” or “no” response and modes in which the individual may be contacted. This consent and contact information will be stored in the CalHEERS systems and sent/received via eHIT to SAWS. For CCHIP and MCAP, This consent and contact information will be stored in the CalHEERS systems and added to the daily extract file that is generated for Maximus. | 25.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
238810 | Delegation Not Updating After Primary Contact Change by SAWS | Shared | HBX will trigger a transfer delegation to the same Enroller if impacted Consumer case has active delegation and primary contact is changed by a SAWS transaction. Enroller will continue to be able to access Consumer case in HBX and see Consumer case in his/her book of business. Also, HBX will no longer generate an EDR error when SAWS transmits a primary contact change for a delegated Consumer case. | 25.9 | Program Updates | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
252584 | Notices Updates for R25.9 | Shared | This Notices Updates CR is the result of the Long Term Notices Design Approach. Any CR in 25.3 Release that has notice requirements will be moved to this CR. Additional business requirements, unrelated to 25.9 Change Requests, may be added to this CR upon approval of a Decision Item for additional scope. | 25.9 | Notice Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
252595 | 2026 Renewals | Shared | Annual renewals related system enhancements | 25.9 | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
255076 | PCAP Admin Portal view of 834 transaction content | Covered CA | Enhance the Enrollment Snapshot screen in the PCAP Admin Portal to display additional information in business-friendly language as the EDI transactions are populated with codes. | 25.9 | Administrator Screen Enhancements | 3. Authorized End Users are appropriately equipped with tools and trained to serve consumers effectively and to handle exceptional situations. | Enhancement CR
256055 | Collect Electronic Verification of Income Data for Noncitizens | Shared | Verify income through the Franchise Tax Board (FTB) interface using Individuals Taxpayers Identification Numbers (ITINs). Eliminate the requirements that an individual must have SSA data to verify their income. Income verification is currently blocked on verifying Title II income via SSA, which does not accept ITINs. Title II income is not available to individuals without SSNs, so this rule should be removed. | 25.9 | Partner Interface Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
TBD | PasswordLess Authentication | Infrastructure | MARSE2.2 enforced password rotation for consumers which will potentially increase burden on CalHEERS to support consumers for forgot password. CalHEERS shall implement alternative secure solutions to enable consumers to login without the need of a password. | 25.9 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Security
266497 | Enroller Portal/Salesforce Enhancements for 25.9 involving HBX/SF Integration | Covered CA | HBX - SF Integration Changes for 25.9 | 25.9 | Agent Sales & Carrier Integration | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR
262404 | A/B Testing for Shop and Compare Preference Questions | Covered CA | This CR enhances the Preference screen questions in the Enrollment module | 24.2.1 | User Experience Updates | 4. Provide Consumers and End Users with Improved Consumer Experience. | Enhancement CR
230526 | 2024 Annual FPL Updates | Shared | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 24.2.X | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
261909 | Continuous Eligibility for Children-Accelerated Enrollment | DHCS | SHO Letter 23-004, children who qualify for Medi-Cal or CHIP based on attested information will be entitled to a 12-month continuous eligibility period. Starting January 1, 2024, states are not allowed to terminate coverage for such children during the 12-month continuous eligibility period, even if they obtain information that indicates the child does not meet all the eligibility requirements during post-enrollment verification. This information will be considered a change in circumstance, and the child's coverage cannot be terminated unless it supports one of the limited exceptions for continuous eligibility. | 24.3.2 | New Programs | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Enhancement CR
221896 | eHIT Services suite update to Rest | Infrastructure | The intended outcome is to have the eHIT services suite updated to REST. | 24.7.2 | Infrastructure Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Technical Updates
252591 | 2025 Annual FPL Updates | Shared | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 25.2.X | Program Updates | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Program Support Services
224645 | Replace MPLS network between CoveredCA-CalHEERS with Internet/VPN | Covered CA | Highly redundant and complex MPLS circuitry will be simplified to an internet/VPN connectivity. | Non-Release: June 2024 | Security Software Upgrades and Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Technical Updates
228441 | CalHEERS Network Modernization | Infrastructure | · Configuring high availability active-active HA on firewalls to provides seamless redundancy · Network segmentation which improves access control, lowers the attack surface, and improves performance with congestion on CalHEERS infrastructure interface traffic. | Non-Release: September 2024 | Security Software Upgrades and Enhancements | 5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. | Technical Updates
268244 | Bot - Move to a new Region | Covered CA | Enrolls consumers whose enrollment could not be automated after reporting a change in address to a different rating region, into a new plan. This Bot will perform the plan selection to keep the members in the same carrier/product/metal tier in their new region. | Non-Release: May 2024 | CalHEERS - Efficiency Improvements | 1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. | Innovation & Continuous Improvement
261911 | County of Responsibility Enablement Batch update | DHCS | CalHEERS shall update the COR enablement batch to look for Dispositions that are processed beyond 24 hours and release the COR in the nightly batch when the Disposition is received. CalHEERS shall release the County of Responsibility (COR) lock for the cases that are Negative Actioned and shall not look for Disposition to be processed. | 2025 Q1/Q2 | CalHEERS - Efficiency Improvements | 2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Enhancement CR

## Lists (hidden)
24 Month Business Goals List: | Display? | Initiative Category List | Fiscal Owner | Initiator Organization | Category
1. Ensure Consumers receive accurate & timely eligibility determination and correct plan enrollment, initially and during any change or renewal event. |  | (Do Not Display on list for AB 1296) | Covered CA | Accenture | Enhancement CR
2. Ensure Business Partners are able to receive, exchange and reconcile appropriate Consumer information on a timely basis. | Y | Administrator Screen Enhancements | Coverd CA Service Center | CalHEERS State | Technical Updates
3. Authorized End Users are appropriately equipped with tools and trained to serve consumers effectively and to handle exceptional situations. | N | Agent Sales & Carrier Integration | DHCS | Deloitte | Program Support Services
4. Provide Consumers and End Users with Improved Consumer Experience. |  | Annual Renewals | Infrastructure | DHCS | New Policy & Legislative Changes
5. Ensure the technical infrastructure is properly maintained, current, secure and supports capacity demands and completion of business goals. |  | Business Rule Exposure for SAWS (BREfS) | Pending | Covered California | Innovation & Continuous Improvement
(n/a - not an IAP CR for 24 month roadmap) |  | CalHEERS - Efficiency Improvements | Shared | SAWS | Reserve
|  | Development Architecture Tools Enhancements | N/A | Other | Security
|  | Infrastructure Enhancements | Unassigned | Unassigned | Tech Refresh
|  | New Programs |  |  | N/A
Notice Updates
Partner Interface Updates
Partner Reconciliation Improvements
|  | Program Updates |  | State Team Owner
|  | Report a Change (RAC)/Special Enrollment Period (SEP) |  | Technical
|  | Reporting Improvements |  | Functional
|  | Security Software Upgrades and Enhancements |  | PMO
|  | Stability Improvements |  | Unassigned
System Management Tools Software Enhancements
User Experience Updates
Worker Productivity Updates