## CalHEERS CRs
CalHEERS
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
CRs / Initiatives
Last updated: 1/19/23
CR # | TITLE | BRIEF DESCRIPTION | RELEASE
171267 | Notices Updates for R22.12 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 22.12
208859 | Apply Soft Pause to beneficiaries that are placed in Pending eligibility status due to pending verifications following SAWS renewal. | During annual renewal, beneficiaries who are determined no longer eligible to Medi-Cal by the CalHEERS business rules engine must be reviewed by a county eligibility worker to screen for eligibility under another Medi-Cal program prior to taking a negative action. This CR will place the beneficiary into soft pause during the renewal batch when appropriate to ensure beneficiaries' eligibility remains consistent in CalHEERS and SAWS until the county eligibility worker has completed their assessment of other Medi-Cal programs. | 22.12
217645 | Banner Message on Other Health Coverage (ESI Affordability changes) | Covered CA is anticipating changes to the ESI functionality for an individual and their dependents. As a short term solution Covered CA would like to add a banner message to the Other Health Coverage page. | 22.12
200351 | Notices Updates for 23.12 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.12
200349 | Notices CR for 23.2 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.2
214185 | Move Enum to the reference data caching for the screens part of the LW Phase 5 | As part of Technology Refresh initiative roadmap, Enum will be moved to the reference data caching providing easier way to maintain these static values. | 23.2
216713 | Apply Soft Pause for Pending Medi-Cal Eligibility (Phase II) | During annual renewal, beneficiaries who are determined no longer eligible to Medi-Cal by the CalHEERS business rules engine and do not meet the soft pause criteria must have an opportunity to provide update information via a pre-populated renewal form prior to discontinuance in SAWS. This CR will allow CalHEERS to place beneficiaries under "Awaiting Review" to ensure beneficiaries' eligibility remains consistent in CalHEERS and SAWS until the annual renewal process had been completed by the county eligibility worker. | 23.2
219790 | Removal of Soft Pause indicator when a MAGI Medi-Cal beneficiary moves from non-premium MAGI Medi-Cal to premium MAGI Medi-Cal. | CalHEERS will not place beneficiaries into Soft Pause when they are moving from a Non-Premium aid code to a Premium aid code for MAGI Medi-Cal. | 23.2
189474 | Plan Choice and Assister Portal Project (PCAP) | Replace the existing COTS product(s) with a custom solution that is integrated with the HBEX custom solution to produce custom software solution or a combination of a custom/Salesforce solution for the CalHEERS Eligibility and Enrollment functionality. Note that 6 child CRs were created in RTC to support the initiative from an administration perspective: CR 193111 - Plan Choice and Assister Portal Project (PCAP) - Plan Management CR 193114 - Plan Choice and Assister Portal Project (PCAP) - Enrollment & Shopping CR 193115 - Plan Choice and Assister Portal Project (PCAP) - EDI & Enrollment Batches CR 193140 - Plan Choice and Assister Portal Project (PCAP) - Agent & CEC Portal CR 193143 - Plan Choice and Assister Portal Project (PCAP) - Issuer Portal CR 193144 - Plan Choice and Assister Portal Project (PCAP) - Admin Self-Service CR 193145 - Plan Choice and Assister Portal Project (PCAP) - Policy Based Payments & Renewal Batches | 23.4
147420 | Administrator Search Enhancements | Administrator Search Enhancements combines the existing (as of 22.9) Admin Home and Individual Search to put the search functionality on Admin Home, including a navigational header at the top, and including bookmark functionality. | 23.6
190310 | Supplemental Notices Insert and Notices Hold Release | CalHEERs shall create a Notice page on the portal that contains modules for creating a supplemental notice (content previously known as buck slip) with a notice, creating an admin notice, configuring the active/hold/suppress function of the notices, and creating a box snippet in a notice. | 23.6
199836 | Periodic Verifications No Response from Consumers | This CR provides the functionality to withhold selected populations from the Medicare and Deceased PVC process and discontinue consumers from the appropriate program(s) following the no-response process. | 23.6
200350 | Notices Updates for R23.6 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.6
209628 | SB260 - ChatBot | The changes requested in CR 209628 is to extend the existing IVR SB260 Opt In/Opt Out functionality/back end APIs to the Covered CA Chat Bot. | 23.6
219981 | PCAP Enhancements for 23.6 (Renewals) | Replace the CalHEERS annual renewal functions from enrollment standpoint (active & passive) for existing COTS product(s) with a custom solution that is integrated with the HBEX custom solution. This enhancement is a follow on to the CR 189474 PCAP which replaces the other aspects of the COTS product(s). | 23.6
228291 | Access to Historical Enrollment Snapshot Data | COTS Enrollment Snapshot data cannot be easily converted to the new PCAP solution. CCA staff will rely on this data when researching what may have occurred on historical enrollments. Without this data CCA may be required to honor consumer escalations or appeals. It has been agreed that this historical snapshot data will be maintained in a pre-23.4 release environment with special as a short term solution. Access will be restricted to 5 staff members. A long-term solution will be required for permanent storage and access to this data. This solution will allow CCA access to the historical data to support consumer escalations and appeals should they occur. | 23.6
173678 | Medicare Coverage Dates | CalHEERS will persist and read the partial Medicare coverage details from the Medicare response for the benefit year as part of this CR. CalHEERS will only evaluate consumers eligible for a subsidy for months not covered by Medicare.If the response indicates a Medicare Coverage End Date in the future or does not have a Medicare Coverage End Date, the system should be able to determine whether or not the month should be counted as a Medicare covered month. CalHEERS will display the Medicare coverage dates on the Personal Verification Page, and the dates will be consumed by SAWS as a result. | 23.9
180018 | Spanish URLs for CalHEERS Portal Login and Shop & Compare | Covered CA is seeing a high drop rate of Spanish Consumers ending their sessions after landing on the English version of CalHEERS Portal Login (https://apply.coveredca.com/apspahbx/ahbx.portal) and Shop & Compare (https://apply.coveredca.com/lw-shopandcompare/) based on analyzing the stats collected from Google Analytics. Covered CA has determined that most Spanish Consumers are clicking on URLs provided by Covered CA Marketing campaigns and Covered CA partners. Covered CA would like dedicated Spanish URLs to direct Spanish Consumers to CalHEERS Portal Login and Shop & Compare and automatically select Spanish language. Spanish Consumers will land on CalHEERS Portal Login and Shop and Compare pages in Spanish when Consumer clicks on hyperlink provided by Covered CA Marketing campaigns and Covered CA Partners. | 23.9
189273 | Implement Eligibility Functionality for Family Planning, Access, Care and Treatment (Family PACT) Program in CalHEERS | CalHEERS shall add the Family PACT application and eligibility process to the CalHEERS Portal and BRE, automate integration with MEDS, automate referrals for other IAP programs, and provide appropriate notices and messaging to Family PACT clients and Family PACT providers. Family PACT program aid code 8H is not considered MEC and shall not impact current CalHEERS functionality for determining eligibility for IAP programs. | 23.9
200352 | 2024 Renewals | Annual renewals related system enhancements | 23.9
200353 | Notices Updates for R23.9 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.9
210202 | Expansion of full scope Medi-Cal for eligible adults from 26 through 49 years of age, inclusive, regardless of citizenship or immigration status | This CR will program CalHEERS to grant full scope MAGI Medi-Cal eligibility to adults aged 26 to 49 regardless of their immigration status in alignment with the January 1, 2024 implementation of the Adult 26-49 Expansion. | 23.9
216356 | Accelerated Enrollment in SAWS | The functional changes requested in CR 216356 is to extend the Accelerated Enrollment for Children and Adults functionality to the SAWS Access Channel. The changes span across eligibility, MEDS, notices, and reporting. This change is configurable. | 23.9
216717 | BREfS Initiative #7 - Carry Forward Enhancements | BREfS Initiative #7 - Carry Forward Enhancements CR initiative will enhance and streamline the existing Carry Forward process by reducing the number of steps that eligibility workers have to take to lift the Carry Forward and to transition individuals to MAGI Medi-Cal. | 23.9
221893 | Microsite for Aetna | CCA implemented Microsites for all of our QHPs in R21.6. The goal of the Microsites is to transition consumers who enroll for coverage off exchange onto the State Benefit Exchange so that they can take advantage of benefits they are eligible to. Aetna has joined the SBE for the 2023 Enrollment year. A new Microsite will be required for Aetna. | 23.9
223157 | Negative Actions - Updates to Exchange eligibility | Currently CalHEERS uses 3 configurations for a Negative Action to evaluate eligibility for CCP/APTC/CSR/CAPS, when a negative action is received for an individual. Covered CA has not been able to use the configurations fully and turn OFF the configuration for any negative action. Turning OFF the configuration was impacting Covered CA cases where the system was discontinuing individuals to CCA eligibility due to a Negative Action, even though the individual is currently eligible and enrolled. Also, when a foster child has negative action as “on aid on another case" for foster care coverage, they are discontinued for MAGI Medi-Cal and determined eligible for unsibsidized coverage aid code X7 on the original case. This causes dual eligibility and possibility of dual enrollment for the child who has foster care coverage. | 23.9
228982 | Notices Updates CR for 24.12 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.12
82920 | BREfS Initiative #9: Verifications Only Service and Separation of Verifications by Source | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and triggers the eligibility business rules engine (BRE) in CalHEERS. CalHEERS uses VIED to coordinate the verifications responses into the BRE and return an eligibility determination via the Determination of Eligibility Response (DER) operation. The intended outcome of this change is to modify both the CalHEERS portal and the eHIT architecture to add a separate Verifications Only service, while continuing to maintain the existing functionality described above for the combined VIED and BRE service. | 24.2
122183 | Infants Initiative | The objective of this initiative is to provide functionality for Medi-Cal Deemed Infants, provide ability to add Medi-Cal Access Program infants (MCAIP) and renewal functionality in CalHEERS. This CR will allow parents to enroll infants directly through the online portal. This includes Deemed Infants and non-Deemed, as well as infants enrolled in MCAIP. | 24.2
128730 | Automation of Termination Reason Codes due to Fraud and Medi-Cal Eligibility | The objective of this initiative is to automate reason codes in 835 File Transactions between CalHEERS and Qualified Health Plans (QHP) that are conducted manually currently. | 24.2
132464 | CCHIP Enhancements | The purpose of this initiative is to enhance current CCHIP eligibility and renewal functionality in CalHEERS. Adding Pending Eligibility determinations, resulting in update changes to noticing and CCHIP daily extract file. What: The purpose of these changes are to align CCHIP eligibility with the CMS MAGI Medicaid & CHIP Electronic Verification Plan Who: These fixes affect eligibility for CCHIP beneficiaries. Where: CalHEERS currently does not determine a CCHIP child as pending eligible when certain electronic verifications are not reasonably compatible. Conditionally eligible outcomes are not consistent with the approved CMS MAGI Medicaid & CHIP Electronic Verification Plan. Why: If the requested functionality is not added, CCHIP eligibility will not be in compliance with CMS MAGI Medicaid & CHIP Electronic Verification Plan. | 24.2
151332 | MAGI Medi-Cal Income Budget Periods | This initiative enhances the use of three budget periods to properly align with State law and Federal regulations and the budget period options selected in the State Plan Amendment (SPA). As part of this initiative, the Projected Annual Income (PAI) and Reasonably Predictable Future Income budget periods will be separated to allow for better alignment with current policy. | 24.2
165890 | ROP Batch - Phase II | Covered CA has to ensure consumers are held accountable for not providing proof of their attested income. The goal of the CR is to have the verification attribute "Household Income - State Subsidy" as one of the configurable attributes for which Reasonable Opportunity Period (ROP) batch functionality can be turned on. | 24.2
206195 | Alternative Formats | The purpose of this initiative is to add a question to CalHEERS Single Streamline Application for the applicant or representative to indicate any alternative format preferences. | 24.2
227501 | Modernize Adobe Document management solution | Adobe Experience Manager (AEM) forms component is the Document Management System used for generating correspondence notices for CalHEERS. Adobe has notified that they will be changing their licensing model in 2023 from the current core-based licensing. State and Deloitte will need to find a replacement and modernize the document management solution to support the continued functionality of notices in CalHEERS. | 24.2
228977 | Notices Updates CR for 24.2 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.2
TBD | Eligibility Results Page Phase II | Placeholder CR for changes in phase II to the Eligibility Results Page | 24.2
45901 | SB 1341 AB 617 - BREfS Phase B | SB 1341 AB 617 - Notice Improvements - The objective of this initiative is to align CalHEERS with Senate Bill 1341 and Assembly Bill 617 and consolidate and send notices for Mixed Households in SAWS. | 24.6
125938 | EDD Interface - Employer Address Information | The objective of this initiative is to enhance the EDD interface to collect employer addresses. This will reduce the need for consumers to enter employer contact information. This will ensure CCA has accurate information to send the required employer notifications. | 24.6
151861 | Change in MEC Value for Aid Code 01 | Effective November 2019, refugees eligible for Medi-Cal aid code 01 are not entitled to Refugee Medical Assistance (RMA) benefits. Because aid code 01 will no longer include RMA benefits, it must NOT be considered Minimal Essential Coverage (MEC) in CalHEERS when the removal of RMA from aid code 01 takes effect. CalHEERS shall update the MEC table value for aid code 01 from TRUE to FALSE. Impacts to SAWS/Counties: SAWS will need to make noticing updates and potentially other changes per the pending ACWDL. | 24.6
161090 | Value Based Insurance Design | Covered California would like to implement a Value Based Insurance Design (VBID) pilot in select regions. Consumers in select regions will be enrolled in VBID plan designs. All consumers in the region will participate. There will be opportunity to opt in or out of this pilot. | 24.6
173135 | Enhance eHIT to Transmit Verification Documents Uploaded in CalHEERS to SAWS | Problem Statement: Consumers have the ability to upload outstanding verification documents in the CalHEERS portal. Currently the CalHEERS system does not notify counties/SAWS that Medi-Cal recipients have uploaded verification documents in the CalHEERS portal. In addition, the verification document is not transmitted to SAWS for verification by county eligibility workers. This Change Request will provide the functionality for CalHEERS to notify and send verification document/s to SAWS for county eligibility workers to complete verifications. Intended Outcome: Improved experience for business partners/SAWS. | 24.6
183098 | Placeholder for Federal Annual Updates | Placeholder for automation improvements / reminder to improve efficiencies, whether process or system efficiencies | 24.6
183100 | SEP Dropdown and Workflow - Phase 2 | Problem Statement: The Special Enrollment Period (SEP) reasons in the portal is not a comprehensive list that adheres to the federal regulations. The page does not have helpful information and causes confusion to the consumers in the Intake/Report A Change (RAC) flow. Intended Outcome: The SEP reasons in the portal needs to be more intuitive and more helpful to the users: 1. Update and add to the available SEP reasons 2. Update and add to the business rules for each existing and new SEP reason 3. Dynamically display the SEP reasons in the drop down list based on the user role and application mode 4. Update the SEP page language 5. Allow users to capture multiple SEP reasons. System to determine the most advantageous SEP reason. 6. Capture SEP reasons at the household vs individual level. 7. Update eHIT/SAWS accordingly | 24.6
183209 | Eligibility Notice Generation Enhancement – Phase 2 | Phase 2: The purpose of this initiative is to enhance the CalNOD01 noticing system that lives within the business rules engine that will have the ability to effectively, efficiently, and accurately notice consumers about their eligibility determination. | 24.6
220303 | BREfS #5 High Impact Business Validations | This initiative will first require the analysis of the high impact eHIT Business Validations (BVs) to identify potentially redundant or antiquated BVs. Updates to the identified BVs would improve the accuracy and speed of automated eligibility determination results. | 24.6
221896 | eHIT Services suite update to Rest | CalHEERS has taken the undertaking to update our architecture and platforms. Keeping in line with the upgrades to our system, the eHIT interface requires an update to REST to be in alignment with our innovation and keeping up with the latest technologies. | 24.6
224645 | Replace MPLS network between CoveredCA-CalHEERS with Internet/VPN | CoveredCA operates two highly redundant MPLS (AWS-Direct Connect) circuits for their Service Center to CalHEERS connectivity. CoveredCA seeks to optimize the network complexity by decommissioning MPLS circuits. | 24.6
228979 | Notices Updates CR for 24.6 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.6
230828 | Affordable Coverage for dependents of ESI – Family Glitch changes | Adds the ability for users to report the actual lowest cost Employer Sponsored Insurance (ESI) offer for each member that is provided an offer, both at the employee level and at the family level; Adds the calculation of whether the employee's or the family's offer of ESI meets or exceed the federal affordability standard for a given benefit year; Includes a configuration for the affordability threshold by benefit year | 24.6
TBD | 90-Day Cure Period | This initiative will support the automation changes needed to align with CMS policy clarifications regarding the treatment of a submitted renewal during the 90 day cure period as a new application. This 90-day timeframe is referred to as the “cure period”. This initiative will help align the business processes across systems, including SAWS and county business process changes. | 24.6
TBD | Individual Level Eligibility | This initiative is intended to enhance and streamline the individual level eligibility functionality in CalHEERS. | 24.6
61104 | Implement Plan Dependent Rules | The purpose of this CR is to update CalHEERS to implement the enforcement of plan dependent rules. CalHEERS enrollment grouping rules should include plan dependency definitions, by only allowing Married spouses, Registered domestic partners, Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners, Disabled adult children of any age (including 26 or above) and Siblings under the age of 26 to enroll in the same Covered CA plan. CalHEERS should also prevent enrollment of over-age dependents unless they meet the “disabled child” exception. | 24.9
85672 | Medi-Cal Plan Selection | The objective of this initiative is to provide the ability for MAGI Medi-Cal consumers to select a plan within CalHEERS. | 24.9
88353 | Implementation of PCP Selection Module and Provider Map | The objective of this initiative is to add functionality to the existing Provider Directory for physicians designated as Primary Care Providers (PCPs). The new functionalities are part of the GI PCP Module: 1) PCP Assignment for Qualified Health Plans (QHP) 2 ) Network Density Tools: This feature will allows consumers to search an area where they desire coverage and determine in real-time how many providers are active in an area for a health plan issuer. | 24.9
118769 | SAWS Integration with DIVS Solution | The purpose of this initiative is to incorporate the eHIT changes to align with the integration of the document imaging verification solution. | 24.9
170935 | Multiple Primary Tax Filers on the same case/application | Problem Statement: Currently, CalHEERS allows only one primary tax filer on a case/application. CalHEERS does not have the ability to calculate separate APTC amounts for multiple primary tax filer households on one case and also to enroll multiple tax households in one plan. Intended Outcome: Update CalHEERS to allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application/enrollment. Update the system to allow multiple different tax households with multiple different APTC amounts for one enrollment. Update the system to prevent any surplus APTC of one APTC tax household from being applied to another APTC tax household (even if both consumers are enrolled in the same plan). Update the system to generate multiple 1095s for multiple tax households that are enrolled on a single enrollment/plan. | 24.9
224724 | Consent to Contact transmitted to MEDS | DHCS is implementing new consent to contact functionality to allow a beneficiary to consent to receiving auto-dialed calls, text messaging, and email contact by entities such as counties, Covered California, Medi-Cal managed care plans, and DHCS. The consent to contact will be added to the CalHEERS on-line portal in addition to the paper application and SAWS. E-Hit will need to be updated to include the consent to contact information that will be transmitted to SAWS. Additionally, a MEDS transaction from SAWS will be needed to transmit the consent to contact information to MEDS. | 24.9
227448 | BREfS #8 eHIT Enhancement of Data Overlay | This initiative will enable CalHEERS to process eHIT eligibility requests from SAWS without impacting exchange programs by overlaying required data elements. | 24.9
228980 | Notices Updates CR for 24.9 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 24.9
229850 | 2025 Renewals | Annual renewals related system enhancements | 24.9
TBD | Consumer Protection Programs | The objective of this initiative is to determine eligibility for the Consumer Protection Programs (CPPs) in the event the consumer experiences a loss of eligibility in their coverage group. | 24.9
213539 | BPM Workflow Improvements II | The intended outcome of this CR is: 1. To prevent Duplicate MWS cases from being created in Salesforce when multiple household members upload the same document. 2. To ensure that the Annual Document – 1095, document types for Deceased and Incarceration are routed to the correct queues for Service Center processing. 3. Case origin field is populated to identify the origin of the document. | 2023 Q2
203445 | Tax Credit Eligibility Assessment | To effectively administer the income verification activities for the program, Covered California would like to compare the attested income of historical CalHEERS consumers to their filed income at end of the coverage/tax year. This will be accomplished with a Batch job that would fetch the relevant tax related details for consumers using the Existing FTB API. The Data will be persisted in the Data Warehouse for Analysis and Reporting. | 2023 Q4
227922 | Verification Caching Phase IV (VC IV) | CalHEERS continues to improve the verification information displayed on the Personal Verification page as well as correcting issues identified in related SIRs. | 2023/2024 TBD
228956 | Reasonable Compatibility Changes for Exchange program | As per regulation, CalHEERS should evaluate the % difference as the % that the attested income amount is below the income amount received from electronic sources, to evaluate reasonable compatibility test for income when determining eligibility for APTC/CAPS/CSR consumers. Also the threshold for the reasonable compatibility test for income when determining eligibility for APTC/CAPS/CSR consumers should be made configurable, so that it can be modified easily. CalHEERS should also implement the use of a threshold dollar amount to evaluate reasonable compatibility for Exchange eligibility, CalHEERS shall consider a response from IRS of no tax data found as meeting the income compatibility rules. | 2024 Q1
229437 | Enhance SF Partner Portal/Enroller Portal Design | SF Partner Portal and SF Enroller Portal pages will have similar HBX page formatting and will have Covered CA and DHCS branding. | 2024 Q2
40149 | Automation of the Application Missing Information Notice (NOD16) | The objective of this initiative is to allow admin roles to skip required fields and automatically send the consumer notification of missing information. | 2024/2025 TBD
96957 | Remove a Household Member Downstream Functionality | The objective of this initiative is to ensure downstream processes in CalHEERS and SAWS occur when a consumer requests to remove a household member from a case in the CalHEERS portal. | 2024/2025 TBD
114946 | Consumer Document Upload Functionality and Admin Task Management | This CR will allow a consumer to upload their own identity proofing documents as alternative to RIDP or following an RIDP failure. It will also provide verification automation and admin verification capabilities. | 2024/2025 TBD
199832 | Eligibility Determinations after APS (SB 260) Phase 2 | With the current implementation of SB 260 with CR 160531, CalHEERS can only retain the Auto Plan Selection (APS) flag if the APS enrollment is available. If due to a subsequent RAC, the APS enrollment is terminated or canceled, the consumer will not be able to take Opt In/Opt Out actions because the enrollment status for the APS Enrollment is no longer in a “Pending” state for the consumer to take action on. The APS flag is attached to the enrollment for which the consumer is auto plan selected to. It is not attached to any new enrollments which result due to changes in eligibility. This applies to all eligibility determinations including the ones that are not submitted by the consumer. If the subsequent RAC enrolled the consumer in a $0 net premium plan, the consumer no longer has the option to opt-in or opt-out since the APS enrollment is no longer valid. In addition, consumers for whom a change results in the APS enrollment being automatically updated from >$0 to a $0 net premium need to be informed of their new obligation to provide an active Opt-in in order to keep the APS plan. With the initial CR, a simple banner message has been added to the eligibility dashboard, but the message is vague, over-applied, and is only seen by users that did the RAC in CalHEERS versus SAWS transactions. | 2024/2025 TBD
214183 | Eligibility Results page to display the current Eligibility run and Eligibility start date to be determined correctly for prior year application | The purpose of this CR is to have correct Eligibility results displayed on the Eligibility results page. The system should determine correct Eligibility even though the initial application was for a prior year. | 2024/2025 TBD
TBD | Explore Horizontal Integration Improvements | Placeholder CR to Explore Horizontal Integration Improvements | 2024/2025 TBD
190570 | 2023 Annual FPL Updates | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 23.2.1
225474 | RIDP Security Enhancements | The intended outcome of this CR is to prevent the Consumer or Admin or Agent/Assister Users to bypass the RIDP page unless the verification is completed. | 23.2.2
228555 | Income Update in Effective Dating | Currently, when a Consumer tries to make an income change/deduction in the CalHEERS portal and the beginning date is greater than the end date, the CalHEERS portal allows the change and incorrectly determines eligibility. The system should prevent user from entering income begin date greater than end date. | 23.2.2
224268 | AB2530 Subsidies for Strike/Lockout Workers | This CR will have CalHEERS implement a new program based on AB 2530 for Strike/Lockout Benefits, for consumers who specify that their Loss of MEC is due to a labor dispute. | 23.7.X
230526 | 2024 Annual FPL Updates | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 24.2.X (Go-Live: 3/1/24)
186319 | CalWIN Conversion to CalSAWS Wave 6 (Sacramento, San Luis Obispo and San Francisco) | This initiative is the sixth of six waves to support the CalWIN to CalSAWS Migration for Sacramento, San Luis Obispo and San Francisco counties. | Non-Release: 10/30/2023
225741 | Build Data Warehouse infrastructure to store and categorize SAWS batch verification data in retrievable format. | Current data storage infrastructure does not allow DW/audit fulfillment teams to extract SAWS batch verification data for tracking and strategic planning purposes. | Non-Release: 2/18/2023
186216 | CalWIN Conversion to CalSAWS Wave 2 (Santa Clara, Tulare) | This initiative is the second of six waves to support the CalWIN to CalSAWS Migration for Santa Clara, Tulare and Contra Costa counties. | Non-Release: 2/27/2023
215911 | Electronic Record Preservation Management | Establish a secure AWS S-3 infrastructure to maintain cross region copy of the original file to meet the security requirement - Section 5.3.3 of “AIIM ARP1-2009 Analysis, Selection, and Implementation of Electronic Document Management Systems” | Non-Release: 3/25/2023
213633 | BeyondTrust Privileged Access Management (PAM) system implementation | This internal tool which is used to store privileged account credentials and only accessed by Operation team/system administrators. There is no direct impact on business due to this change. | Non-Release: 3/31/2023
186218 | CalWIN Conversion to CalSAWS Wave 3 (Orange, Santa Barbara and Ventura) | This initiative is the third of six waves to support the CalWIN to CalSAWS Migration for Orange, Santa Barbara and Ventura counties. | Non-Release: 4/24/2023
186221 | CalWIN Conversion to CalSAWS Wave 4 (San Diego, San Mateo, Santa Cruz and Solano) | This initiative is the fourth of six waves to support the CalWIN to CalSAWS Migration for (San Diego, San Mateo, Santa Cruz and Solano counties. | Non-Release: 7/3/2023
186317 | CalWIN Conversion to CalSAWS Wave 5 (Alameda, Fresno and Sonoma) | This initiative is the fifth of six waves to support the CalWIN to CalSAWS Migration for Alameda, Fresno and Sonoma counties. | Non-Release: 9/4/2023
202496 | ROP Process for MEC, SSN, and AI/AN | CalHEERS to redetermine consumers with expired ROP for SSN, MEC, and/or AI/AN and update enrollment appropriately via a BOT process. | Non-Release: March 2023
228441 | CalHEERS Network Modernization | #1 The current HA failover event for production firewalls and non-production firewalls is managed by AWS Lambda, and it required downtime to failover the firewall during which services are interrupted. This must be replaced with a vendor solution to eliminate time or configure active-active HA to which provides seamless redundancy or failover. | Non-Release: September 2024