## Open Items
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document. |  |  |  |  | DHCS Consumer-Focused Stakeholder Working-Group
[5 empty] | Updated as of | 2020-03-04 12:53
# | Date Logged | Action Item | Requestor | Owner | Deadline | Status | Notes
1 | 2019-06-07 | SOC Data | Kevin Aslanian / David Kane | Bob Davidson | 2020-02-07 | Complete | 06/07/19 - Kevin asking whether DHCS has SOC data. This population could potentially be eligible for the 250 Percent Working Disabled Program. 07/12/19 - Kevin would like to know the number of people who have a SOC above $200. 08/02/19 - Linda and her team are still researching this issue. 09/06/19 - Harold will forward request to RASD to update their data pull. 10/28/19 - Harold confirmed that RASD is working on the request. Harold provided status to David. 12/05/19 - Harold provided status to David that data is currently being reviewed internally. 01/10/20 - Harold and Bob explained that 2013 RASH data is pre-ACA and any new data pull would reflect ACA. Staff is developing new schema and methodology. 02/07/20 - Harold and Bob provided the SOC data and explained the plan to posts the data on the Open Data Portal. David to reach out to Harold and Bob for off line discussion.
2 | 2019-10-25 | Conlan Problems | David Kane | Michaella "Shelly" Londono (CA-MMIS) | 2020-02-07 | Complete | 10/25/19 - David stated that there are problems with the Conlan process: problems with forms, signature requirements, appropriate contact person, authorized representative duties and rights to communication, etc… MCED will reach out to appropriate division for handling. 10/28/19 - Debbie referred Conlan concerns to Phil Fedler cc to David, Cori, and Alicia. 11/01/19 - Shelly explained the Conlan processes and responded to advocates questions. 11/22/19 - Received additional questions from David. Forward questions to Michaella for research and response. 01/31/20 - Sandie forward Michaella's responses to David, Alicia. 02/07/20 - Shelly and team provided additional background on Conlan process and responded to advocates questions.
3 | 2020-01-10 | CFSW webpage updates | MCED | Debbie Wong-Kochi | 2020-02-25 | Complete | 01/10/20 - Debbie will update CFSW webpage to include inbox for data requests. 02/14/20 - Per Harold and Bob, removed the inbox for data request.
4 | 2020-02-07 | 2020 FPL Updates | David Kane | Theresa Hasbrouck | 2020-02-07 | Complete | 02/07/20 - Theresa provided the following updates: Numbers for the population impacted will be available March 2020. Last year, 163,020 MAGI outreach letters were sent. David asked about including other populations. Theresa indicated that this would be off line discussion with advocates.
5 | 2020-02-07 | SSI Linked Medi-Cal | David Kane | Sandie Williams | 2020-02-07 | Complete | 02/07/20 - Sandied provided the process related to SSI linked Medi-Cal. David to reach out to CDSS for best practice (i.e. updates to addresses). CDSS is the state control agency for SSI/SSP.
6 | 2020-02-07 | SB 75 Open Data Portal | David Kane | Jillian Davis | 2020-02-07 | Complete | 02/07/20 - Jillian stated that SB 75 is experiencing data issues. SB 75 data will be posted retroactive once problems are resolved.
7 | 2020-02-27 | NMT Application Data | Alicia Emanuel | Cynthia Smiley/ Jonathan Ring (Benefits) | 2020-03-06 | Complete | 02/27/20 - NMT Application Data: Total - 307 Approved – 51 Denied – 204 Withdrawn – 2 In process with A&I - 15 Returned to provider as incomplete – 35

## Completed Action Items
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document. |  |  |  |  | DHCS Consumer-Focused Stakeholder Working-Group
[5 empty] | Updated as of | 2020-03-04 12:53
# | Date Logged | Action Item | Requestor | Owner | Deadline | Status | Notes
1 | 2019-04-05 | MEDS Modernization - Timeline | Cori Racela | Christine Boynton | 2019-06-07 | Complete | 04/05/19 - Cori is requesting a timeline of MEDS Modernization. 05/03/19 - Christine stated that the timeline is being reviewed by management. 06/07/19 - Christine provided the MEDS timeline and explained the phases.
2 | 2019-06-07 | Enrollment Data for Individuals Under 21 - Open Data Portal |  | May Engstom | 2019-06-07 | Complete | https://data.chhs.ca.gov/dataset/eligible-individuals-under-age-21-enrolled-in-medi-cal-by-county
3 | 2019-06-07 | SB 75 Data - Open Data Portal |  | May Engstom | 2019-06-07 | Complete | https://data.chhs.ca.gov/dataset/sb-75-full-scope-medi-cal-for-all-children-enrollment
4 | 2019-06-07 | NOA SOC MC 350 | Kevin Aslanian | Brooke Hennessy | TPD | Complete | 06/07/19 - Kevin provided a copy of NOA MC 350. Is this a current version? What is the policy for sending out the MC 350? 07/12/19 - Linda & staff will call Kevin to discuss his concerns about SOC NOA. This will be handled outside of CFSW.
5 | 2019-07-12 | Asset Verification Program (AVP) | Cori Racela | Sandie Williams | 2019-07-25 | Complete | 07/12/19 - Sandie provided an update on AVP. Cori requested CMS guidance. Forward to Cori & Alicia the federal legislation and ACWDL 17-37 implementing AVP.
6 | 2019-07-26 | NOA with Immigration Status | Alicia Kauk | pending | TPD | Complete | 07/26/19 - Alicia will send Contra Costa NOAs dealing with immigration status to Debbie. Forward NOAs to appropriate managers for review and research. 08/02/19 - Linda & staff will call Alicia about NOA. This will be handled outside of CFSW.
7 | 2019-07-26 | Asset Verification Program (AVP) - County Operations | Cori Racela | Sandie Williams | 2019-08-02 | Complete | 08/02/19 - Sandie provided an update on AVP county operations.
8 | 2019-10-04 | Children's Preventative Care Outreach | Mike Odeh | Mitchelle Retke (Managed Care Operations) | 2019-10-04 | Complete | 10/04/19 - Debbie provided the update for Managed Care: Question: When will stakeholders be able to review the general outreach notice to all beneficiaries under 21 about preventive services benefits?- Response: We are targeting to provide Stakeholders with a DRAFT notice for review and feedback in October 2019. The exact date is to be determined, but we are targeting mid-October. Question: What’s the status of the consultant’s outreach efforts and engagement with stakeholders? Response: An update on the consultant outreach efforts and engagement with stakeholders is targeted to be shared out in the first quarter of 2020. We can provide an update at one of the next Advisory Group meetings. Additional update: We were actually able to get the draft letter finalized. It will go out to the Advisory Group for feedback this week. It went to our Plans today (10/01/19) and is set to to go out to the Advisory group as well, if it hasn’t already been sent.
9 | 2019-09-06 | Aged & Disabled FPL Expansion Update | David Kane | Brooke Hennessy | 2019-09-06 | Complete | 09/06/19 - Brooke provided update: waiting for CMS approval, pending timeline for guidance to county (ACWDL), SAWS implementation. David and team would like to discuss further. Conference call will be set up. 09/24/19 - Conference call with Sandie and David. 10/04/19 - Sandie provided the update: waiting for CMS approval, ACWDL is being drafted and will be shared with stakeholders around February 2020. David stated that implementation should be more timely. Rene explained that policy and system automation are not in sync. Rene stated there are multiple systems being coordinated including migration, CalFresh, and CalWORKs.
10 | 2019-10-25 | R1 Aid Code Data Request | Alicia Emanuel | Sandie Williams | 2019-10-28 | Complete | 10/25/2019 - Since DHCS policy changed in February 2019, permitting R1 aid code enrollees to voluntarily enroll in managed care, we are looking for data that shows FFS v. MCP enrollments from Feb. 2019 to now. 10/28/2019 - Sandie e-mailed David, Alicia, Corni and provided R1 aid code data found on the Open Data Portal.
11 | 2019-10-04 | Medicare Saving Program "Over Property" Update | David Kane | Brooke Hennessy | 2019-10-04 | Complete | 10/04/19 - David raised concerns regarding the timing of when SAWS programs the Medicare Savings program property limits in relation to when DHCS releases the annual ACWDL (typically March). The questions were about: lists created by SAWS, noticing to consumers, and guidance to counties. • 2019 property limits were not programed in SAWS until September release. • 2018 limits are used until SAWS programs the 2019 limits. • The lists are of individuals known to SAWS whose countable property exceeds the 2018 limit and is under the 2019 limit. The purpose of the list is for eligibility workers to run eligibility back to January 1. • The consortia share the lists with the counties with instructions on how to process the list. • Upon release of the annual ACWDL eligibility workers may override the eligibility result (following normal business process). 11/01/19 - Brooke provided update that the counties are working on the list of 31-80 cases.
12 | 2019-10-04 | SAWS Notices | David Kane | Yingjia Huang and Theresa Hasbrouck | 2019-11-01 | Complete | 10/04/19 - Yingjia explained the SAWS NOA process: 1) MCED provide language snippets to SAWS in template format. 2) MAGI snippets are stored in tables 3) SAWS programming creates the NOA utilizing snippets and different tables and trigger mechanisms. David stated that NOAs are confusing because of design, readability, and translation problems. Rene asked David to provide background on the NOA problem. 10/22/19 - MCED received David's write up on the NOA problems. David also provided a NOA issues related to medically indigent adult (MIA). Next steps will be discussed at the pre-meeting. 11/01/19 - Theresa stated that the SAWS Notices issues will be handled under CalSAWS.
13 | 2019-10-04 | Governor Budget Update - Initiatives |  | Sandie Williams | 2019-11-01 | Complete | 10/04/19 - Sandie suggested dedicating a block of time outside of CFSW to discuss initiatives (Health Navigator, Provisional Postpartum Care Extension ("PPCE", Maternal Mental Health), ABD Expansion, Medicare Buy-In Disregard (AB 1088). Advocates to respond back for the best approach moving forward. 10/23/19 - Sandie received feedback from Lynn Kersey and David Kane for the workgroup meeting times for the intitiatives. Workgroups to meet the third Friday of each month, starting November 15th. Stakeholders will identify the appropriate core group of stakeholders for these meetings. 11/01/19 - Debbie provided the Inititatives Workgroup meeting schedule: Starting the third Friday of each month… the first meeting would be November 15th: 10:00-10:30am - Health Navigator’s Project 10:30-11:00am - Provisional Postpartum Care Extension (Maternal Mental Health) 11:00-11:30am - ABD Expansion 11:30-12:00pm - Medicare Buy-In Disregard (AB 1088-Flippers) Lynn and David are the stakeholder leads (Lynn handling first two while David is handling the second two). MCED will send out the meeting invites. High level updates will be provided at the monthy CFSW meetings.
14 | 2019-10-25 | TAR Beneficiary Notices | David Kane | Cynthia Smiley (Benefits) and Aloni Jackson (Dental) | 2019-11-01 | Complete | 10/25/19 - David requested policy related to TAR noticing. Issues seem to be related to Dental. David to provide sample TAR notices. MCED will reach out to appropriate division for handling. 10/28/19 - Debbie referred TAR/dental issue to Cynthia Smiley and Aloni Jackson cc David, Alicia, Cori. 11/01/19 - Jim provided the TAR process: 1) the manual has the current TAR process; 2) A NOA is sent to beneficiary if the TARs are deferred.
15 | 2019-10-25 | Natural Disaster Income and Asset Policies | David Kane | Bonnie Tran | 2019-11-22 | Complete | 10/25/19 - David to provide cases 11/01/19 - 11/01/19 - Bonnie provided an overview of how different types of payments for natural disasters are counted for MAGI and Non-MAGI and the ACWDL/MEDIL numbers that relate to natural disasters. • ACWDL 92-08 Disaster Assistance • ACWDL 15-36 Guidance to Counties on Treatment of Applications/Redeterminations in Disaster Areas and Treatment of Disaster Assistance for Modified Adjusted Gross Income and Related Information • ACWDL 19-01 Exceptions due to Public Health Crisis or Disaster • MEDIL 17-16 Processing Applications from Individuals Affected by Disasters Pending advocates to send case examples of CEWs incorrectly calculating income. Advocates requested to add the nine-month exemption (up to 30-months) for cash payments to be treated as exempt property as an agenda item for CWDA. 11/22/19 - Per David, advocate is not able to provide cases. Ok to close item.
16 | 2019-10-25 | Restricted-Scope Emergency Services Coverage/Denials | David Kane | CAASD | 2020-01-02 | Complete | 10/25/19 - David stated that patients with emergencies are being treated by providers/hospitals and then denied coverage. David to provide cases. MCED will reach out to appropriate division for handling. 11/20/19 - Debbie received cases and conducting research. 01/02/20 - Debbie shared DHCS findings related to beneficiaries bills with advocate.
17 | 2019-11-22 | Asset Verification Program (AVP) | David Kane | Harold Higgins | 2019-12-06 | Complete | 12/06/19 - Harold provided an update on AVP. System changes to MEDS are pending. Full implementation is not targeted yet because all stages related to application, annual review, and report a change need to be done. Cori would like DHCS to implement a simple verfication process.
18 | 2018-10-26 | FFS Non-Medi-Cal Transport and Medil 18-05 | Alicia Kauk | Cynthia Smiley (Benefits) | TPD | Complete | 01/30- an update will be provided during the 02/01 meeting. 02/01/19 - Cynthia provided data on applications and the status denied/approved. Benefits reviewed advocates' comments to MEDIL 18-05. A new MEDIL will be issued to address the comments. 03/01/19 - Cynthia provided update on applications data. Benefits will be drafting and sharing new MEDIL by the end of the month. 03/07/19 - Lucy Q question: Can counties enroll as NMT providers? Response: Cynthia Smiley reached out to Provider Enrollment Division (PED) and confirmed that counties can enroll as NMT providers. 04/05/19 - Cynthia provided data on applications and status denied/approved. The new MEDIL will be shared with the group once the system is ready (target date end of April). 05/03/19 - Jim stated that the new MEDIL is ready. Advocates are requesting to review first before it's released. Advocates would like to know if there will be additional outreach to providers on this subject. 06/07/19 - Cynthia provided data on application and status denied/approved. The Approved NMT Providers list is posted to the Benefits webpage. Advocates requested additional outreach to providers on this new benefit. MEDIL is ready to be shared. 06/24/19 - Cynthia shared MEDIL with Alicia and Cory. Requested feedback by 07/08/19. 07/12/19 - Benefits staff (Jim, Rachel, etc...) provided data on application and status denied/approved. Cynthia will discuss advocates' feedback on the MEDIL next time. Advocates requested additional outreach to providers. Advocates would like telephone script to include additional help to consumers calling. 08/02/19 - Cynthia will e-mail DHCS' responses to advocates feedback on the MEDIL to the advocates. Cynthia discussed the outreach to providers. Advocates requesting the telephone script to include information for additional help. Lynn K. stated that drivers are telling customer that they don't service a particular area. Per Lynn, drivers are not providing any additional help of what to do next. 09/06/19 - Cynthia provided data on application and status denied/approved. MEDIL and telephone scripts are in review and will not be released until procurement is completed. Advocates would like to confirm that outreach is occuring through the provider bulletin. 10/04/19 - Cynthia provided data on application and status denied/approved. Information is posted on the website. MEDIL has been finalized - contact Cynthia for questions. 11/01/19 - Jim provided updates on application and status denied/approved. 12/06/19 - Cynthia provided data on application and status denied/approved. 12/18/19 - Cynthia received comments on MEDIL from advocates. 01/10/20 - Jim provided data on application and status deniedl/approved. Jim confirmed feedback on MEDIL. MEDIL will be released soon.
19 | 2019-09-06 | FFS Non-Medi-Cal Transport - Outreach | Alicia Kauk | Cynthia Smiley (Benefits) | TPD | Complete | 09/06/19 - Advocates would like to confirm that outreach is occurring through the provider bulletin. 10/04/19 - Cynthia confirmed that outreach will be handled directly through the providers instead of a bulletin. 11/01/19 - Alicia clarified that the outreach should still include a bulletin to providers. Jim will check with Cynthia and respond back to the group. 12/06/19 - Cynthia confirmed that outreach will be a news flash to providers. Also beneficiaries will received a 5x7 postcard in the JVR mailers. 01/10/20 - Jim confirmed provider news flash in February bulletin. Also, shared 5x7 postcard pending the JVR mailers.
20 | 2020-02-04 | NMT Application Data | Alicia Emanuel | Cynthia Smiley (Benefits) | 2020-02-07 | Complete | 02/04/20 - Per Alicia's request, NMT Application Data will be documented in the action item log only: Total - 292 Approved – 36 Denied – 186 Withdrawn – 2 In process with A&I - 27 In process with PED – 5 Returned to provider as incomplete – 37