## Go-Live
Acronyms are defined on the Acronyms sheet. Use Control + page down to navigate to the new sheet. Bold Cells indicate changes from prior version. | DHCS Major Program Initiatives - Go-Live Dates (pending readiness and federal approvals) | [10 empty] | Updated: 7/18/2025
Category | Activity | 1/25 | 2025-03-25 | 2025-04-25 | 2024-05-25 | 7/25 | 2025-09-25 | 2025-10-25 | 12/25 | 1/26 | 2024-03-26 | 2024-07-26 | 2025-10-26 | 2025-12-26 | 2025-01-27 | 2025-07-27 | 2025-10-27 | 2028 | 2029
Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment (BH-CONNECT) | Access, Reform, and Outcomes Incentive Program | X
| Adult Evidence Base Practices (Opt-In) |  |  | X (Phase In)
| Short-term IMD (Opt-In) |  |  | X (Phase In)
| Centers of Excellence |  |  |  |  | X
| Workforce Initiative |  |  |  |  | X (Phase-In)
| Youth Evidence Based Practices |  |  |  |  | X
| Activity Funds | [6 empty] | X
| Community Transition In-Reach (Opt-In) | [6 empty] | X (Phase In)
| High Fidelity Wraparound | [10 empty] | X
Behavioral Health Transformation | Bond BHCIP Round 1 |  |  |  | Awards
| Bond BHCIP Round 2 |  |  |  | RFA Released | [5 empty] | Awards
| Behavioral Health Services Act | [10 empty] | X
CalAIM | Administrative Integration of SMH and SUD | Phase II Voluntary Behavioral Health Contract Integration (County Option) | [12 empty] | Fully Integrated
| PATH Initiatives (to support ECM, Community Supports, Justice-Involved) | CITED Round 4 Opens | [6 empty] | CITED Round 4 Awards | Technical Assistance Marketplace Closes |  |  |  | PATH Initiative Ends
| Regional Capitation Rates and Shared Savings/Risk | SPD & LTC Blend Non-COHS | [7 empty] | Regional Rates (Phase-In) |  |  |  |  | Prospective Shared Savings
| DMC-ODS Traditional Healers and Natural Helpers |  | X
| Population Health Management Service (Medi-Cal Connect) |  | Release 2 |  |  | Release 3.0 | Release 3.1 |  | Release 4 Late 2025 | Release 5 Early 2026
| County CCS Oversight |  |  |  |  | Voluntary Participation Begins
| CalAIM Renewal |  |  |  |  | Release Concept for Public Comment |  |  |  | Submit to CMS
| Transitional Rent |  |  |  |  | X (Optional) |  |  |  | X (Mandatory, Phase In)
| Medi-Medi Plans (D-SNP) Expansion Statewide | [8 empty] | Most Non-CCI Counties |  |  |  |  | Remaining Non-CCI Counties (Phase-in)
| NCQA Accreditation | [8 empty] | X
| Transition to Statewide MLTSS | [16 empty] | No Sooner Than 2028
Children and Youth Behavioral Health Initiative (CYBHI) | Certified Wellness Coaches | X
Benefits | Eliminate Glucagon-Like Peptide-1 (GLP-1) Coverage for Weight Loss | [8 empty] | X
| Eliminate State-Only Dental Benefits, Adults 19 and Older with Unsatisfactory Immigration Status | [10 empty] | X
Eligibility | Enrollment Freeze for Full-Scope State-Only Medi-Cal Expansion, Adults 19 and Older | [8 empty] | X
| Reinstate Medi-Cal Asset Test Limits | [8 empty] | X
| H.R. 1 Work Requirements for Medi-Cal Expansion Adults 19 to 64 | [13 empty] | X1
| H.R. 1 Redetermine Eligibility for Medi-Cal Expansion Adults Every Six Months | [13 empty] | X
| State-Only Medi-Cal Premiums, Adults 19 Through 59 with Unsatisfactory Immigration Status | [14 empty] | X
| H.R 1 Copayments for Specified Expansion Adults | [16 empty] | X
Financial | H.R. 1 One-Year Ban on Federal Medicaid Funding by Certain Providers of Abortion Services |  |  |  |  | X (7/4/25)
| H.R. 1 Provider Tax Changes |  |  |  |  | X (7/4/25) | [10 empty] | X (Multiyear Phase-Down)
| Pharmacy Drug State Rebates for Individuals with Unsatisfactory Immigration Status | [6 empty] | X
| Eliminate State-Only Prospective Payment System Rates to Federally Qualified Health Centers and Rural Health Clinics for Individuals with Unsatisfactory Immigration Status | [10 empty] | X
| H.R. 1 Regular FMAP for Emergency Medi-Cal for Individuals with Unsatisfactory Immigration Status | [11 empty] | X
| H.R. 1 State Directed Payment Restrictions | [16 empty] | X (Multiyear Phase-Down)
| H.R. 1 Federal Funding Repayment Penalties | [17 empty] | X
Bold cells indicate change from prior version
Quarters (Q) are based on calendar year
1 State option to delay implementation until 12/31/2028 with US HHS Secretary approval.

## Acronyms
Acronyms | Definition
BHCIP | Behavioral Health Continuum Infrastructure Program
BH-CONNECT | Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment
CalAIM | California Advancing and Innovating Medi-Cal
CCI | Coordinated Care Initiative
CCS | California Children's Services
CITED | Capacity and Infrastructure Transition, Expansion, and Development
COHS | County Organized Health Systems
CMS | Centers for Medicare and Medicaid Services (Federal Agency)
CYBHI | Children and Youth Behavioral Health Initiative
DMC-ODS | Drug Medi-Cal Organized Delivery System
D-SNP | Dual Eligible Special Needs Plan
ECM | Enhanced Care Management
FMAP | Federal Medical Assistance Percentage
FQHC | Federally Qualified Health Center
H.R. | House Resolution (Federal Legislation)
ILOS | In Lieu of Services (renamed Community Supports)
IMD | Institution for Mental Diseases
LTC | Long-Term Care
MLTSS | Managed Long-Term Services and Supports
NCQA | National Committee for Quality Assurance
PATH | Providing Access and Transforming Health
RFA | Request for Application
SMH | Specialty Mental Health
SPD | Seniors and Persons with Disabilities
SUD | Substance Use Disorder
TBD | To Be Determined

## Go-Live ( updated 0725) (hidden)
Acronyms are defined on the Acronyms sheet. Use Control + page down to navigate to the new sheet. Bold Cells indicate changes from prior version. | DHCS Major Program Initiatives - Go-Live Dates (pending readiness and federal approvals) | [19 empty] | 2025-07-02
Category | Activity | 7/24 | 8/24 | 10/24 | 11/24 | 12/24 | 1/25 | 2/25 | 3/25 | 4/25 | 2024-05-25 | 2025-06-25 | 7/25 | 8/25 | 10/25 | 11/25 | 12/25 | 1/26 | 4/26 | 2024-05-26 | 2024-07-26 | 2025-12-26 | 2027
Behavioral Health Transformation | Bond BHCIP Round 1 | RFA Released | [8 empty] | Awards
| Bond BHCIP Round 2 | [9 empty] | RFA Released | [8 empty] | Awards
| Behavioral Health Services Act | [19 empty] | X
CalAIM/Waiver | Administrative Integration of SMH and SUD | [5 empty] | Phase II Voluntary Behavioral Health Contract Integration (County Option) | [15 empty] | Fully Integrated
| Enhanced Care Management (ECM)/Community Supports (ILOS) |  | ECM CS Q2 2024 data |  | ECM CS Q3 2024 data |  |  | ECM CS Q4 2024 data |  |  | ECM CS Q1 2025 data |  |  | ECM CS Q2 2025 data
| PATH Initiatives (ECM, Community Supports, Justice-Involved) |  | Develop CalAIM DSAG 3.0 toolkit for Justice-Involved Populations |  |  |  | CITED Round 4 Opens | [8 empty] | Pre-Release & Reentry Health Services – Justice-Involved Data Enablement |  | SDN 24033 Phase III – System Update for Justice-Involved BH Provider Claim Adjudication
| Regional Capitation Rates and Shared Savings/Risk | [5 empty] | SPD & LTC Blend Non-COHS | [10 empty] | Regional Rates1 | Justice-Involved Advisory Group Meetings |  |  | CalAIM 1115 waiver demonstration Re-entry | Prospective Shared Savings
| Behavioral Health Community-Based Organized Networks of Equitable Care and Treatment (BH-CONNECT) | [6 empty] | Content/Page updated on DHCS site
| Medi-Medi Plans (D-SNP) Expansion Statewide | [8 empty] | Invoice Approved | [7 empty] | Most Non-CCI Counties |  |  |  |  | Remaining Non-CCI Counties
| Justice-Involved Initiative |  |  | Pre-Release Medi-Cal Services (24-month phase-in period begins) | [7 empty] | X
| Population Health Management Service (Medi-Cal Connect) | Release 1 |  |  |  | Release 2 Late 2024 / Early 2025 | [6 empty] | Release 3 Mid 2025 |  |  |  | Release 4 Late 2025 | Release 5 Early 2026
| NCQA Accreditation |  |  |  | Assessment Review & Follow-Up | [12 empty] | X
| County Eligibility and Oversight | [9 empty] | Report published to requester
| DMC-ODS Traditional Healers and Natural Helpers |  |  |  | Informative video published
| Transitional Rent | [7 empty] | Updated Transitional Rent Fact Sheets | [8 empty] | X (Mandatory, Phase In)
Children and Youth Behavioral Health (BH) Initiative | Wellness Coaches |  |  |  | Establish the Wellness Coach as a new distinct provider type
| Mobile Crisis Services | Services Begin (Remaining 12 Counties) | [12 empty] | Data Reporting Project
Financial | FQHC Alternative Payment Methodology | Cohort 1 | [15 empty] | Cohort 2
Equity and Practice Transformation Payments
Other | Medi-Cal Managed Care New Contract
| Health Equity Roadmap |  |  |  |  | Phase 2: Co-design
| Community Assistance, Recovery and Empowerment (CARE) Court |  |  |  |  | Cohort II
Bold cells indicate change from prior version
Quarters (Q) are based on calendar year
1 Potential phase in through 2026, as applicable
2 Subject to appropriation, federal approval, and state readiness