## IAP 24 month Roadmap CR Listing
RE-LEASE | CR NUMBER | TITLE | REQUESTOR | BRIEF DESCRIPTION | Advocate Comments 3/20/2015 | STATUS UPDATES for 6/24/2015 AB 1296 MEETING
R15.7 - (Planned Deployment Date 7/27/2015)
R15.7 | 4920 | Reconciliation: IRS, CMS, Carrier, Consumer, Financial | CovCA | The original design of the Carrier reconciliation process was reviewed by the carriers. At that time, changes were recommended to account for terminations and cancelations during the month. Since that time, CMS has issued an updated reconcilaiton format, which includes second 834 file that includes terminations and cancelations. The design and documentation for the reconciliation needs to be modified to include both an active enrollment 834 and termination and cancelations 834 files. This is needed by December for testing so that the first reconciliation can be done in January.
R15.7 | 7098 | Enhance Eligibility Transaction History Table to Display All Consumer Eligibility Transactions | DHCS & CovCA | The purpose of this change request is to expand the Transaction History Table in the CalHEERS system to accurate show ALL Eligiblity transactions with sufficient detail to support the eligibllity determined by the BRE. It is intended that this transaction history end with the action that initiates Plan Selection. Plan Selection results and Enrollment History (including carrier transactions) will be developed using CR 29022 "Add Automation, Monitoring, and Alerting to the Inbound and Outbound 834/820/GI Batch Processes" (see immediate below for brief description). | Advocates would like to know who will have this admin access at the counties and will Covered CA R&R and appeals unit be able to view the Med-Cal eligibility transactions even if the case is with the county. | On scheduled for R15.7 implementation.
R15.7 | 7169 | Expedited/Flexible Application Entry for Service Center Representatives (SCRs) | DHCS & CovCA | Covered CA discovered that during the process of entering Paper Applications, SCRs had to revisit applications multiple times because the Consumer failed to enter needed information. In an effort to reduce the time it takes to complete the paper application process, Covered CA would like for Service Center Representatives (SCRs) and/or any designated role, to be able to skip required fields and continue entering the information provided by the Consumer. The system must be able to notify the Consumer of needed missing information and task the Service Center Representative when the missing information is received via mail, fax, or document upload. Covered California and DHCS reviewed and approved options from the initial JAD (Option 2 plus Add On's) as detailed CR supporting documents. Confirmation of option have been received from both Sponsors. | How will the system notify paper applicants of missing info? Will a notice be generated from CalHEEERS or will they need to create an online account to get notifications? Also need to make it easy for SCRs to scan and identify additional paper documents that come in from paper applicants so that it can be easily connected to the consumer's case. | CR is delayed and scheduled for implementation in R15.9.
R15.7 | 7536 | MEDS Error Handling | DHCS | Modify CalHEERS to send MEDS SOAP Faults from Online HX18 and HX20 transactions to a user friendly console. CalHEERS submits in real time HX18 Create Application and HX20 Create Eligibility transactions to MEDS. MEDS processes the transactions and returns SOAP faults if they error out. The SOAP faults fall into two broad categories. The first is the transaction submitted to MEDS does not adhere to the XML contract agreement between CalHEERS and MEDS. The second is that the data submitted in the transactions do not meet MEDS business rules (e.g., There is a discrepancy on the birthdate and SSN being sent in these applicants that is conflicting with the data that exists in MEDS, there is a discrepancy between the CIN and SSN that is being sent by CalHEERS in the HX18 and the record with the same CIN in MEDS). While CalHEERS is able to handle both types, the expectation from DHCS is that CalHEERS treat the data/business rule errors as Alerts and submit them directly to the CalHEERS tool, similar to the Alerts that are identified as part of the CalHEERS batch transactions (HX12, HX20, HX34, HX40). | This CR will be very helpful in fixing wrong eligibilty determinations. Please ensure access to this new screen is provided to both SCRs as well as counties. | CR is on hold. This CR will be re-prioritized for a 2016 release after R16.2.
R15.7 | 8754 | Plan Portal Presentation Changes (deductibles, benefits, and hover text) | CovCA | Feedback from Covered CA, carriers and advocates would like the deductible display made clearer, and some benefits need the description to be changed and added clarification for the Bronze and Catastrophic plans. Several plans have voiced their concerns for misleading hover text as well as misleading benefit display. | We are concerned about the hover text and would appreciate having a chance to review the hover text in context - perhaps even pointing out the ones where others have raised concern - and the misleading benefit display. Please share those concerns with advocates.
R15.7 | 10974 (New) | Add My Profile Link to Administration Home Page & New Verbiage on Portal for Password Policy Change | CovCA | This CR is to allow Admin User to have access to their My Profile page from the Administration Home Page. Currently, the Admin role does not have access to the My Profile Page. This page allos the user to create new passwords, reset Security Questions and Answers, update personal information, and reset the PIN on their User Account. This CR will also add new verbiage to help clearly articulate Password Policy and to roll out the non-consumer password expiration reset. Non-consumer passwords must be reset prior to the start of Open Enrollment. |  | CR was not originally on roadmap for R15.7 implementation. It is scheduled to be implemented in R15.7.
R15.7 | 28702 | Long Term Negative Action | DHCS | This CR is enabling negative action functionality for the long term and identifying system requirements for CalHEERS implementation in addition to those referenced in CR 7900 "Negative Action". | We know this critical functionality needs to be done as soon as possible. | On scheduled for R15.7 implementation.
R15.7 | 29022 | Add Automation, Monitoring, and Alerting to the Inbound and Outbound 834/820/GI Batch processes | CovCA | 1) Implement AUTOSYS to automate both Inbound and Outbound processes, including notifications to the Accenture Ops team, CalHEERS Plan Management and Technical teams in order to address issues in a timely manner and avoid downstream issues with the Carriers. a. Define all the reasons why the failure can occur and log them in the database; b. Implement error logging at the file validation and business validation level; c. Report the errors (Inbound and Outbound) via the application portal and the BI reports; d. Make the carrier-specific errors available to the carriers. e. Send a daily 8AM email notification to Carriers detailing exceptions that have occurred during Inbound file processing and include the Carrier File Control number on this notification. f. Add the Carrier File Control number to the 999 files that are sent to the Carriers. 2) Implement an Incident Reporting process and a daily touch-base meeting with the Plan Management and Technical team. 3) A Batch Schedule report should be produced daily. 4) Provide Incident Reports detailing data quality, file integrity, and reconciliation issues. 5) Review existing SLA's to ensure proper severity is applied to the 834 processes. |  | CR is delayed and planned for implementation in R15.9.
R15.7 | 32297 | Reduce NOAs sent to the Consumer | DHCS | Determine the business solution to reduce the number of notices sent to the consumer. | Appreciate CalHEERS investigation into the cause of multiple notes and fixing the problem, eliminating some of the consumer confusion. We are anxious to hear if the fix has eliminated 100% of the problem or if there are still some multiple notices produced. | On scheduled for R15.7 implementation.
R15.7 | 33625 | Leader Replacement System (LRS) Integration with CalHEERS Planning and Execution | CalHEERS | In order to successfully implement the LEADER Replacement System (LRS) in Los Angeles County, the LRS Project must successfully test its interface with the CalHEERS and ensure that an implementation plan is mutually agreed upon and in place prior to LRS pilot and the five waves of LRS roll out in Los Angeles County. Following the stabilization of the 3.0 schema updates at C-IV and CalHEERS, and after the open enrollment period is complete, LRS will integrate the 3.0 schema and related changes made by C-IV. It is anticipated that this integration will be completed by late February. When LRS completes the integration of the C-IV 3.0 schema and related changes, LRS will require a testing environment at CalHEERS with the 3.0 schema functionality to complete its LRS/CalHEERS interface testing. This effort is in addition to and it does not replace the existing SAWS (C-IV, CalWIN and LEADER)/CalHEERS interface/integration testing. The LRS Project has provided to CalHEERS a list of detailed scope of work including testing requirements, and testing time frames for all planned test phases (e.g. System Test, UAT, Converted Data test) so that CalHEERS can determine the level of effort and testing environments necessary to support LRS testing, and to determine additional funding that is required to support the LRS rollout and integration with CalHEERS. CalHEERs needs to plan the LRS eHIT interface partner integration. The plan needs to include all aspects of implementation with the new SAWS eHIT interfacing partner: - Planning the effort (approach, testing strategy and scope, LRS rollout and conversion from LEADER to LRS testing, timeline, environments and infrastructure and support) - OTech network connectivity establishment and testing - Testing environments procurement and set up - Interface Code Updates/Development - Integrated System Test execution - Pre-Production environment and code deployment support - LEADER to LRS Conversion and interaction with CalHEERS test execution - Performance Test execution - Coordination of LRS production rollout (August 24. 2015 - September 2016) with CalHEERS - Post Production support (monitoring, reporting, triaging, troubleshooting) OSI has prepared a document outlining basic system testing and utilization as supporting documentation to this Change Request. LRS and CalHEERS teams have prepared the list of requirements that will be used as a basis of the estimate. |  | On scheduled for R15.7 implementation.
R15.7 | 34164 (New) | Retore link and ability to procdess 2014 RAC that does not contain an SEP reason |  | This CR is to restore the 2014 Report a Change link as required to support the completion of RAC. |  | CR was not originally on roadmap for R15.7 implementation. It is scheduled to be implemented in R15.7.
R15.7 | 36110 | Add APTC Effective Date to 834 Transactions | CovCA | APTC Changes are not being uniformly applied by the carriers. In order for these transactions to be applied the same across all partners a date needs to be added to the 834 transaction. This Change Request is cross-functional and requires input from both Eligibility and Carrier management teams. This CR also includes correct APTC proration across months when a change in APTC occurs. | We are concerned about this and hope the changes approved will ensure that consumers are obtaining the correct APTCs through the plans. Troubling that the changes were not being applied uniformly across plans. Is there a reason this change is limited to APTC calculations during the year? Are all carrier transactions for APTC calculations at initial app and renewals now accurate? Has testing been done to make sure APTC pro-rating and sharing with carriers is accurate? Advocates also request that these transactions to carriers are correct when appeals staff need to change the APTC amount to resolve the appeal or comply with a hearing decision. | CR is delayed and scheduled for implementation in R15.9.
R15.7 | 44504 (New) | Remove Negative Action Flag | DHCS | As a preventive measure, this CR is to request the CalHEERS system to performa a database batch update to remove the negative action indicators for 660,000 individuals in the CalHEERS system prior to implementing the Long Term Negative Action change request (#28702). |  | CR was not originally on roadmap for R15.7 implementation. It is scheduled to be implemented in R15.7.
R15.9 - (Planned Deployment Date 10/12/2015)
R16.2 R15.9 | 3066 | Former Foster Care | DHCS | Current CalHEERS design is to mandatorily refer to counties for eligibility evaluation, all attested Former Foster Care (FFC) individuals. The ACA FFC coverage group is mandatory categorically needy. All ACA-related mandatory categorically needy coverage groups eligibility rules must be programmed in CalHEERS. Eligibility criteria to be programmed into CalHEERS includes: 1. Under age 26 2. Were enrolled in foster care under the responsibility of the State (any state) or tribe and enrolled in Medicaid under the State’s Medicaid State Plan or 1115 demonstration waiver upon obtaining age 18, or at such higher age at which the State’s or Tribes foster care assistance ends under title IV-E of the Act. 3. No income test The system must verify enrollment in foster care and Medicaid in accordance with the CMS verification plan, which is to verify foster care and Medicaid enrollment through the county social services offices, post-eligibility determination and enrollment. | Advocates are pleased that this critical eligibility functionality has been moved up, but it’s critical that this be implemented ASAP and sooner than 15.9 given the erroneous eligibility determinations. Also, advocates want to be part of the design and to understand the verification procedures. | CR will be implemented in two phases. Phase 1 is scheduled for implementation in R15.9. Phase 2 will have a new CR number and is planned for R16.2.
R16.4 R15.9 | 4497 | MAGI 5% Income Disregard | DHCS | This Change Request is submitted to program the MAGI 5% income disregard when determining eligibility under the ACA Parent/Caretaker Relative coverage group for certain non-pregnant adults who are not eligible for enrollment in the ACA New Adult coverage group. Current CalHEERS programming does not apply the 5% MAGI disregard when determining income eligibility under the ACA Parent/Caretaker Relative coverage group. In accordance with 42 CFR, Section 435.603(d)(4), the 5% MAGI disregard applies when determining income eligibility under the ACA eligibility group with the highest income standard under which the individual may be determined eligible using the MAGI methodology. Non-pregnant parents and caretaker relatives not eligible for enrollment in the ACA New Adult group shall have the 5% MAGI disregard applied when determining their eligibility under the ACA Parent/Caretaker Relative group. For pregnant parents and caretaker relatives, the 5% disregard applies when determining eligibility under the ACA Pregnant Women coverage group and therefore does not apply when determining eligibility under the Parent/Caretaker Relative group. The likely scenarios in which the MAGI 5% disregard applies to determining eligibility under the ACA Parent/Caretaker Relative group is when the non-pregnant parent or caretaker relative is: · Enrolled for coverage under Medicare Parts A or B · 65 years-old or older · When the child linking the individual is not enrolled in minimum essential coverage (MEC). | Advocates strongly support moving up this CR as it is needed to implement a basic eligibilty rule and without it some adults eliglble for MC are being wrongly determined eligible for APTCs instead. As a result, low-income adults are paying for health insurance that they should be getting for free. | CR is scheduled for implementation in R15.9
R16.9 R15.9 | 4846 | CCHIP Interface and Integration (3 counties) | DHCS | This CR is to develop a long term solution for the CalHEERS MAGI business logic to allow MAGI elibiiity determinations an fully integrate CCHIP elibility for participating counties. CCHIP are state & federal funded public programs that are required to use MAGI rules for eligibiloity pusuant to the ACA. Per federal guidance, children eligible for CCHIP are NOT eligible for APTC; therefore, this change request is critical. | What have we been doing for this population up until now? | CR is delayed and planned for implementation in R16.2.
R16.9 R15.9 | 8415 | Servicing County and Case Management County | DHCS | This change request is for functionality to support Servicing Counties and Case Management Counties when a consumer is placed in one county and case management is the responsibility of another county. | Advocates support prioritizing this CR. | CR is delayed and planned for implementation in R16.2.
R16.9 R15.9 | 8517 | Medi-Cal Access Program Integration | DHCS | Through the Assembly Bill 1296 forum, this CR will integrate MAGI rules into CalHEERS. | This is fundamental eligibility programming that should be implemented ASAP. Advocates request to be part of the design process. | CR will be implemented in two phases. Phase 1 is scheduled for implementation in R15.9. Phase 2 will have a new CR number and is planned for R16.2.
R15.9 | 10804 | Use Administration Verification from SAWS to Grant Full Eligibility Determination | DHCS | Per federal regulations, a full eligibility determination cannot be granted at the first call to the Federal Data Services Hub if all data elements are “administratively verified” by the eligibility worker at the county level. The only data element that CalHEERS accepts, process, and stores in the first run is the California residency verification. This change request will allow the following verification elements, if administratively verified, to be granted a full eligibility determination at the first call to the BRE. These administrative verifications include the following verification elements: California Residency Verification, Social Security Verification, Citizenship Verification, Lawful Presence Verification, Not Receiving Minimal Essential Coverage Verification, Not Dead Verification, Not Incarcerated Verification, Income Verification, and Authorized Representative. |  | CR is delayed and planned for implementation in R16.2.
R15.9 | 11708 | Do Not Display non-MAGI Screen and Citizenship/Immigration Questions For Non-Applying Household Members | DHCS | Update CalHEERS functionality to ensure the following questions will not appear for household members not seeking benefits: · The non-MAGI screening question related to disability, long-term care and Medicare; · All Citizenship and immigration questions. | Advocates strongly support prioritizing this CR and thought this had already been programmed in CalHEERS. Non-applicants should also not be asked for SSN until income section of application and should be marked as optional. Advocates would like to see test screen shots of this fix. | CR is scheduled for implementation in R15.9
R15.9 | 28807 | Add Dental Health Services | CovCA | Covered California has contracted with a new Dental Carrier (Dental Health Services) for 2015. This change will enable code, file transfer, table updates, etc., required to support this new carrier. |  | CR is planned for implementation in R15.9.
R15.9 | 29911 | Employer Notification of Employee APTC | CovCA | This change will require consumers to answer questions about their employer (name and address). It will generate a notice to be sent to any employer when an employee has been determined eligible for APTC. | Advocates would support a delayed release, as this would not be a priority as compared to other eligibility and enrollment issues. Advocates would like input on design. These questions should be asked but it is not clear why they must be required. We recommend not desginating these fields as mandatory in order for consumer to complete the application and if fields left blank, add a pop up reminder to consumer that they will need to provide this info later (if it is required). | CR has been replaced by CR # 44322, which is scheduled for implementation in R15.9.
R16.9 R15.9 | 33378 | Data Extract for MAGI for C-CCHIP | DHCS | Children applying for coverage through Covered CA and eligible for the CCHIP are currently not being informed or enrolled into the program. CCHIP is administered by the local counties and enrolled into a county contracted health plan. Eligibility is not being determined using the CalHEERS MAGI rules as required by federal regulations under 42 CFR, Section 457.315. CCHIP counties do not have direct interface with CalHEERS. Until CCHIP is fully integrated into CalHEERS, under a separate Change Request (CR4846 "CCHIP Interface & integration into CalHEERS"), this workaround would be for Covered CA to provide counties with a data file of children who are determined eligible for APTC/CSR within the established CCHIP income range for counties to inform families of their children’s eligibility for CCHIP. CCHIP counties will use Certified Enrollment Counselors (CEC) to assist families with their applications using the Covered CA’s online application portal and the applications will be processed by CalHEERS. Requirements: 1. Counties: San Francisco, San Mateo and Santa Clara 2. Children ages 0 to up to age 19 3. Household income above 266% and up to 317% of Federal Poverty Level Weekly county eligible file will be transferred via secured FTP. | Advocates support the effort to program it into CalHEERS at an earlier release date so as not to require a work-around. How many children are impacted by the programming error at this time? Until permanent fix in place, recommend that this CR also ensure that eligibility results for these children indicate they may be eligible for lower-cost health insurance and that they may be contacted by the CCHIP program in the county. Recommend a snippet be added in the NOA for these children regarding potential eligibility in another program and a contact for more info. Advocates would like to review language. | Due to the delay of the full integration of CCHIP (CR 4846), this CR which will be a data extract is scheduled for implementation in R15.9.
R15.9 | 34345 | Fed Hub Renewal | CalHEERS | The Renewal and Redetermination Verification (RRV) Composite (bulk) Service (RRV) provides a method for Medicaid/CHIP annual renewals and Requester annual APTC/CSR redeterminations for verification of the following information: * Indication of death * Disability indication * Income (i.e., IRS annual, SSA Title II annual, SSA Title II monthly, and current) * Medicare Part A eligibility This document addresses responsibilities and interactions between Requesters (Federally Facilitated Marketplace (FFM), State-Based Marketplace (SBM), and State Medicaid/CHIP agencies) through the Federal DSH, or the Hub, to and from Equifax, Medicare, the Internal Revenue Service (IRS) and SSA. Equifax provides current income (Tier 1 - current within 45 days of request/query). IRS provides annual household income. Federal DSH RRV Composite BSD - Draft April 2014 3 Use or disclosure of data in this document is subject to restriction. Medicare provides a Medicare Part A eligibility indicator and effective start and end dates. SSA provides Title II income (monthly/annual), indication of death, and a disability indicator. Requesters may find it useful to reference the following synchronous service BSDs for any additional details about any TDS-specific details not described in this document: * Federal DSH Verify Annual Household Income and Family Size Business Service Definition (BSD) * Federal DSH Social Security Administration (SSA) Composite Business Service Definition (BSD) * Federal DSH Verify Current Income Business Service Definition (BSD) * Federal DSH Verify Non-Employer Sponsored Insurance Minimal Essential Coverage (Verify Non-ESI MEC) Business Service Definition (BSD) | Advocates would like to understand better what this new requirement means and the impact of it on eligibility and programming. Will this CR allow verification via the FDSH when consumers report a change of circumstance during the year as well or is this only for renewals? What NOAs will be generated to consumer about the verification results or if info is not reasonably compatible? | CR is scheduled for implementation in R15.9.
R15.9 | 34757 | Family Dental Plans | CovCA | Covered California would like to explore alternate solutions for the implementation of Family Dental Plan Selection for the 2015 Open Enrollment Period. |  | CR is planned for implementation in R15.9.
R16.4 R15.9 | 35331 | Update Income Hourly, daily frequency to mandatory | DHCS | Update portal pages for instances when a consumer enters "HOURLY" and / or "DAILY" Income types the Frequency must be mandatory eHit updates. Conversion of existing data when the value is missing for Frequency. | Advocates support expediting this CR. | CR is scheduled for implementation in R15.9.
R15.9 | 35910 (New) | Short Term Admin Functionality for Soft Pause Indicator | DHCS | The purpose of this CR is to define and deploy short term administrative function available through the ADMIN screen to lift the Soft Pause indicator. |  | CR is scheduled for implementation in R15.9.
R15.9 | 37032 | Refine BRE Change Reporting Rules | CovCA & DHCS | This Change Request is a placeholder and will be updated to support the changes to the BRE being evaluated by Covered California. | We look forward to understanding more about this CR when it is defined. Unless someone is no longer eligible for a particular CSR plan, it is unlawful to terminate enrollment in a QHP due solely to reported changes in income. | CR is planned for implementation in R15.9.
R15.9 | 37033 | Enhancement Income for Open Enrollment | DHCS | Enhancement Income for Open Enrollment - County issues. Place holder CR for income related issues reported by Counties. |  | CR is postponed and planned for implementation in R16.2.
R15.9 | 37034 | UI (User Interface) Improvements | CovCA & DHCS | This CR is to enhance the user interface to improve transition and capture of information in the CalHEERS Portal. | There is insufficient information to analyze; advocates would like to be part of making sure the interface is user-friendly, to review what messaging is available for self-service channels, and to ensure that superfluous and unnecessary information or requests are removed. | CR is planned for implementation in R15.9.
R15.9 | 37095 | Super User Role for Admin Capacity to Modify/Correct Records | CovCA | This CR is to define Super Admin User functionality (Manual Eligibilty) that will allow for overriding business rules in order to provide access to care for consumers. | Advocates support prioritizing this CR. | CR has been replaced by CR # 44290, which is scheduled for implementation in R15.9.
R15.9 | 39912 | Modify PMPM Invoicing Criteria for 2016 Enrollment Period | CovCA | This CR is to modify the logic used to invoice carriers per member per month from enrolled net cancellations to ENROLLED for 2016 Coverage. |  | CR is scheduled for implementation in R15.9.
R16.4 R15.9 | 40758 | Use lower income | DHCS | As part of the Single Streamlined Application (CR 6933, implemented in release 15.3 on March 2, 2015), CR 3161 "SSA - Add Projected Annual Income and Reasonably Predicted Future Changes to income" provides the following functionality for determining MAGI individual household monthly income: * The sum of projected annual income amount (PAI) for each person in the MAGI household, divided by 12 (if PAI is available). * If PAI is unavailable, all countable income minus the 5% income disregard amount if applicable (California opted to add the disregard to the FPL), and minus any deductions. In accordance with W&I Code, Section 14005.65, the intent of this request is to implement the following additional MAGI individual household monthly income functionality when both current monthly income and PAI are available: * If current monthly income and PAI are both available, divide PAI by 12, compare PAI divided by 12 with currently monthly income, then use the lower of the two (PAI divided by 12 or current monthly income). | Advocates strongly support prioritizing this CR which implements income rules that were supposed to be effective Jan 2014 | CR is delayed and planned for implementation in R16.2.
R15.9 | 43925 (New) | Snippet Changes for NOD01 | CovCA | This CR is to revised existing snippets for NOD01; these snippets were deferred from CR 9963. |  | CR was not originally on roadmap for R15.9 implementation; it was deferred from CR # 9963. It is scheduled to be implemented in R15.9.
R15.9 | 44290 (Replaced by 37095) | Super User Role for Admin Capacity to Modify/Correct Records | CovCA | This CR is to define Super Admin User functionality (Manual Eligibilty) that will allow for overriding business rules in order to provide access to care for consumers. | Advocates support prioritizing this CR. | CR is planned for implementation in R15.9.
R15.9 | 44322 (Replaced by 29911) | Collect Employer Name and Address | CovCA | CalHEERS will collect Employer contact information when an applicant indicates they are employed. |  | CR is scheduled for implementation in R15.9.
R16.2 - (Planned Deployment Date 2/22/2016)
R15.9 R16.2 | 2967 | Continuous Eligibility for Children (CEC) | DHCS | The CEC program protects children from negative actions based on a change in circumstance. For example, if a child would be found ineligible for Medi-Cal based on a change in circumstance, the CEC program would keep the child in his or her existing aid code until the child’s next annual redetermination. When information about a change in circumstances is reported to CalHEERS, CalHEERS will run the business rules engine to see if the reported change affects eligibility. If eligibility is affected, CalHEERS will process the resulting change. The only way to ensure that CalHEERS does not act on a negative change to a child’s Medi-Cal eligibility is to ensure that the CEC business rules are built into CalHEERS. Changes in circumstance can be reported to CalHEERS as early as January 1, 2014; therefore, the CEC programming must be implemented prior to January 1, 2014. | Advocates had understood that CEC could continue to function in SAWS and want to understand how this is working today.
R16.2 | 2968 | DMV State Residency Verification | DHCS | The March 23, 2012, Medicaid final rule grants states the option to require verification for state residency. If a state requires verification, it must verify through electronic means unless the state can prove that such information cannot be electronically verified. DHCS has concluded that it will elect to verify state residency for all Medi-Cal applicants through an electronic interface with the DMV. CalHEERS shall work the DMV to establish a secure electronic interface that will share information between the two systems on a real-time basis. CalHEERS shall send information to DMV requesting state residency verification from the DMV and the DMV shall send information back to CalHEERS stating whether the information was “verified” or “un-verified”. CalHEERS shall also update their verification procedures to ensure that all applications are checked against the DMV for state residency verification. | Advocates support a change in policy to continue the current policy of suspending residency verifications and not building this interface. We oppose any additional CalHEERS programming resources used to enable this functionality while there are more pressing eligibility and enrollment issues not functioning. If implemented, advocates would like to a) know what other databases can be checked if consumer's state residency can't be verified via the DMV and b) review text of eligibility results screen or NOA snippet informing individuals their state residency could not be electronically verified.
R15.9 R16.2 | 2972 | Transition Medi-Cal (TMC) | DHCS | The TMC program protects families terminated from Medi-Cal because of increased earnings or hours of employment, loss of earned income. The TMC program consists of two six month periods. Beneficiaries who earn TMC for the first six month period are granted a second six month period if their income is below 185% FPL at the conclusion of the first six month period. When information about a change in circumstances is reported to CalHEERS, CalHEERS will run the business rules engine to see if the reported change affects eligibility. If eligibility is affected, CalHEERS will process the resulting change. Families that qualify for TMC are protected from any negative changes through the TMC program. The only way to ensure that CalHEERS does not act on a negative change is to ensure that the TMC business rules are built into CalHEERS. Changes in circumstance can be reported to CalHEERS as early as January 1, 2014; therefore, the TMC programming must be implemented prior to January 1, 2014. | Advocates support postponing this CR as TMC rules exists in SAWS today and other CRs are more critical.
R15.9 R16.2 | 3043 | Soft Pause - Create Pending Status for MAGI-Medi-Cal Adverse Action | DHCS | This CR is update CalHEERS BRE to make MAGI Medi-Cal Discontinuance or MAGI Medi-Cal no Premium to Premium Status of "Pending" and make updates to eHIT DER transaction to pass Pended MAGI Medi-Cal Discontinuances/ no Premium to Premium changes to SAWS. It will also have updates to include specific individuals to include (Parents, Caretakers, Pregnant Women and Children). The implementation will create the ability for CEW's/SAWS to lift the Soft Pause and create a flag that identifies a case that is being protected by Soft Pause for CEW's / SAWS to view. NOTE: Part 1: Soft Pause for Parents and Children has been implemented. NOTE: Part 2: Soft Pause for Caretakers Relatives and Pregnant Women has NOT been implemented, as well as adds the ability to lift the soft pause. | This is important eligibilty functionality that should not be postponed any further and should be retained in 15.9 release or earlier. Advocates would like to review NOA snippets that explain this soft pause to consumers at the eligibility results screen. Note that this CR should not prevent a consumer from getting APTCs if they are over 65 as there are consumers who should remain eligible for APTC even if they are over 65 and categorically eligible for non-MAGI but will be over income or over resources for non-MAGI eligiibility.
R15.9 R16.2 | 3065 | Continuous Eligibility (CE) for Pregnant Women | DHCS | This CR will implement CE for Pregnant Women. Those eligible are: • Medi-Cal eligible pregnant women enrolled under the 185 or 200 percent program with no SOC who with the increase in income would otherwise have eligibility to the pregnancy program. • Pregnant women in the Medically Needy or Medically Indigent program who with an increase in income have a SOC or a higher SOC. • Pregnant women on public assistance (PA) or other PA (SSI/SSP) who due to an increase in income lose PA eligibility and zero SOC cash-based Medi-Cal. Qualification requirements: To qualify for CE a pregnant woman must be “eligible for and receiving” Medicaid benefits at the time of the income increase. This means that the pregnant woman must have met her share-of-cost (SOC)(been certified) at least once during her pregnancy, prior to or in the same month of the income increase in order for her (and later her infant) to qualify for CE/DE. DE is for infants, CE for pregnant women. | We understand CE for Pregnant Women is continuing to function in the SAWS.
R15.9 R16.2 | 3067 | 4-Month Continuing MAGI based Medi-Cal for Parent/Caretaker Relatives | DHCS | This CR is to design Four-Month Continuing MAGI-Based M/C for parent/caretaker relatives that become MAGI-Based M/C ineligible due to increased alimony. If this change request is not prioritized for R3 then a workaround will need to be established. | Advocates would like to understand what the workaround is for this.
R16.2 | 3068 | PRUCOL | DHCS | PRUCOL statuses cannot be verified through the FDSH Step 1 process. An applicant does not currently have the ability to self-attest to a PRUCOL category on the single streamlined application. CalHEERS needs to add up to two additional PRUCOL questions, to be determined later by DHCS, to collect PRUCOL data. The applicant(s) will get a conditional determination for the specific MC category, provided all other required data and verifications qualify them for Medi-Cal. Step 2 or Step 3 lawful presence verification will process the PRUCOL cases offline. The CMS Frequently Asked Questions indicates that any status can be verified using the G-845 Supplement-PRUCOL form. What we do not know is what the responses will look like. When the Step 2 or Step 3 responses are sent back in an offline manor, including the potential processing of the G845 Supplement-PRUCOL form, the rules will run again with the verification results, and the eligibility will be updated accordingly. CalHEERS needs to add two (2) additional questions to the single streamlined application: 1. Is this applicant a PRUCOL Alien? Y/N if yes - 2. Which category _________(drop-down) Administrative verification process when returned. SAWS will update and send to CalHEERS BRE. If this change request is not prioritized CalHEERS will not be able to accurately determine eligibility for this population and a workaround will need to be established. | Advocates agree that individuals eligible for full-scope Medi-Cal as PRUCOL are properly screened by CalHEERS. But advocates are OPPOSED to adding the 2 additional questions in this CR to identify PRUCOL individuals. PRUCOL applicants are able to self-attest to PRUCOL when they answer Yes to the questions "Do you have satisfactory immigration status?" or "Are you an eligible immigrant?" Most consumers will not know what PRUCOL is to correctly answer such a question. To help identify potential PRUCOL individuals, recommend adding additional categories in the drop down menu of lawfully present individuals. Currently the list is limited to those who are lawfully present for purposes of APTC but the list should include those lawfully present for purposes of Medi-Cal as well. In addition, there should be a "catch all" category listed in the drop down menu indicating "I am known to Department of Homeland Security (DHS) but it is not taking steps to deport me." Also, DACA should be added to the drop down menu as an additional PRUCOL category. Consumers in the ‘catch all’ category will have a variety of statuses and circumstances that need to be evaluated by a DHCS specialist. IF an applicant indicates that they are in this category, their information should be transmitted directly to DHCS.
R16.2 | 3123 | Pregnancy Wrap | DHCS | Welfare & Institutions Code 14148.65 and 14148.67 creates an affordability and benefit program for pregnant women with incomes above 139 percent and up to 213 percent of the Federal Poverty Level (FPL) who are currently enrolled in a Qualified Health Plan (QHP) through Covered California. This program would provide pregnant women with no share of cost health benefits so that pregnant women may receive a benefit package equal to full-scope, comprehensive benefits that are provided for Medi-Cal beneficiaries who are pregnant. Under proposed statute, DHCS will pay for both the premiums and the cost sharing components of the beneficiary’s QHP coverage if the pregnant woman is eligible for pregnancy-related and postpartum services and is currently enrolled in a QHP. The CalHEERS system will determine potential eligibles for the pregnant women affordability program. Similar to the affordability wrap program for Newly Qualified Immigrants (NQIs), pregnant women eligible for the affordability wrap will be assigned two aid codes: (1) Exchange aid code reflecting APTC/CSR coverage; and (2) a limited-scope Medi-Cal aid code to serve as an indicator for wrap coverage. CalHEERS will maintain case management for the APTC/CSR components of the case and the SAWS will maintain case management of the Medi-Cal aid code. Infants born to mothers within the pregnant women affordability program shall be deemed as Medi-Cal infants at birth by the SAWS system. The affordability program shall be made available at November 2014 Covered California open enrollment with eligibility coverage to commence January 1, 2015. | Advocates agree this should be a priority if CMS determines pregnancy Medi-Cal is not MEC. Advocates would like to review text notifying women of their potential dual eligibility and choices.
R16.2 | 3124 | Non-Qualifying Immigrants (NQI) Medi-Cal Affordability Wrap | DHCS | Welfare & Institutions Code 14102 establishes an affordability program to cover the premium and cost-sharing charges for any individual who is 21 years of age or older, who does not have minor children eligible for Medi-Cal benefits and would be eligible for Medi-Cal benefits but for the five-year eligibility limitation under Section 1613 of Title 8 of the United States Code. This population is referred to as non-qualifying immigrants (NQI). Per this statute, DHCS will pay for both the cost sharing and the premium costs for the individual’s Qualified Health Plan (QHP) in the Exchange. This program becomes operative January 1, 2014. NQI adults subject to the five-year bar will be identified by the federal hub since the Verify Lawful Presence (VLP) interface (version 33), CR 6933, was installed in R15.3 on March 2, 2015. CalHEERS functionality is needed to identify these individuals at Covered California open enrollment and place them, if eligible, into the Medi-Cal Benefits and Affordability Wrap program. NQI adults eligible for the affordability wrap are provided two aid codes: (1) Exchange aid code reflecting APTC/CSR coverage; and (2) a state-only, full-scope Medi-Cal aid code to serve as an indicator for wrap coverage. CalHEERS will maintain case management for the APTC/CSR components of the case and the SAWS will maintain case management of the Medi-Cal aid code. The affordability program shall be made available at November 2014 Covered California open enrollment with eligibility coverage to commence January 1, 2015. | Advocates support delaying implementation of the NQI wrap to ensure other programming priorities are inputed first.
R16.9 R16.2 | 4180 | Begin/End Dates on eHIT | DHCS | Enhance CalHEERS to track begin and end dates for data elements like income, expenses, addresses, etc. This additional changes to the portal to capture and then send with the system interfaces with SAWS. | Advocates support earlier release if possible as this functionality is important for accurate eligibility determinations
R16.4 R16.2 | 4304 | Modify Income Limit for Children Ages 6-19 for Aid Code P5 & P6 | DHCS | The income limit for children age 6-19 enrolling for mandatory categorically needy coverage under the ACA children’s group, aid codes P5 and P6, is 133% of the federal poverty level as referenced in 42 CFR 435.118(b)(2)(i). The MCED ACA Aid code list incorrectly identifies the income limit for ACA aid codes P5 and P6 as 108% FPL. This CR request CalHEERS to program income eligibility standard for enrollment in ACA aid codes P5 and P6 from 0% FPL up to 133% FPL. Implementing this system functionality will create an income eligibility overlap in the income range of 108% -133% FPL between aid codes P5/P6 and M5/M6. Aid codes P5/P6 follow the Medicaid rules and do not consider other health coverage as eligibility criteria. M5/M6 follow CHIP rules and do consider other health coverage as eligibility criteria. Therefore, children with income between 108%-133% FPL who are uninsured, do not have other health coverage, are aided in the CHIP aid codes M5/M6, while children who do have other health coverage are aided in the Medicaid aid codes P5/P6. | Shouldn't the MAGI 5% disregard apply to these children? Thus, the income levels should change to 138% not 133%? Or is the 5% disregard applied after?
R16.2 | 4469 | State Inmate Program | DHCS | First Level Request: Implement the State Inmate Program in CalHEERS. DHCS Staff will enter the application(s) into CalHEERS access channel. DHCS will be responsible for case management. If the “First Level Request” is not viable for Release 3 then please see “Second Level Request” below. (Based on discussion 4/24/2014 change request development will be first request implementation). Second Level Request: - Add the Inmate Program Aid Codes to the “Manual” drop-down list in the admin environment so DHCS Staff can override the CalHEERS Eligibility Determination Aid Code with the appropriate “Inmate Program Aid Codes” via a manual work-around process. DHCS would be responsible for case management. Add the ability to suppress Notices of Action. | What NOAs are currently being generated that this CR will help suppress?
R16.2 | 4920 | Reconciliation: IRS, CMS, Carrier, Consumer, Financial | CovCA | The original design of the Carrier reconciliation process was reviewed by the carriers. At that time, changes were recommended to account for terminations and cancelations during the month. Since that time, CMS has issued an updated reconcilaiton format, which includes second 834 file that includes terminations and cancelations. The design and documentation for the reconciliation needs to be modified to include both an active enrollment 834 and termination and cancelations 834 files. This is needed by December for testing so that the first reconciliation can be done in January.
R16.2 | 6614 | Automatically Discontinue Members/Cases Based on Defined Conditions | CovCA & DHCS | Functionality is needed in CalHEERS to automatically discontinue members/cases in the MAGI-Based M/C and Covered California programs/plans based on defined conditions. This will include updates to Business Rules Engine, Discontinue snippets for NOAs, HX40 transaction to MEDS, eHIT updates, and updates to case transaction history. | Advocates would like to understand what the "defined conditions" for automatic MAGI discontinuance are. There is insufficient information here to analyze.
R15.9 R16.2 | 8703 | Medi-Cal Plan Selection Changes | DHCS | This CR is based on advocate feedback subsequent to design approval. Medi-Cal plan selection will enable consumers to use either the CalHEERS portal or existing county / HCO processes to make Medi-Cal Plan selection. Those plan selections will then be available on the CalHEERS portal. Changes and plan updates reported at either source will also appear throught he CalHEERS portal. | Advocates support moving eligibility determinations before online plan selection. We gave design input in Spring 2014 and request the opportunity to reivew changes before design is finalized.
R16.2 | 9428 | County Inmate Program | DHCS | The CalHEERS System shall have the County Inmate program indicator and said indicator will also be in the eHIT interface and will drive the county inmate aid code determination. 19 - 64 - N7 (Limited Scope) N8 (Restricted Scope) ACWDL 13-18 page 8, generate the MAGI-MC NOA with county inmate snippet language. The CalHEERS System shall treat county inmate application indicator as self attestation for Covered California programs eligibility determination purposes. The CalHEERS System shall generate the CALNOD01 Notice for County Inmate applications. The CalHEERS System will deny eligibility to APTC/CSR for an individual that attests to being incarcerated.
R16.2 | 10020 | Enhance CalHEERS/SAWS SFTP Process to Volume | DHCS | The approved design of the eHIT Interface #7 Document and Image file transfer process follows a legacy SAWS implementation from the Electronic Inter-County Transfer Interface (e.g. eICT). On a per case basis, the current implementation creates a single zip for transfer among the SAWS consortia. The current implementation needs to be enhanced as the volumes of NOA and Imaged documents are larger than anticipated. This change request adds functionality to bundle daily case zips transfer, also known as Zip of zips. This change request enhances the process as the volumes of needed transfers is not satisfied by singleton transfers. From a technological perspective, it also provides a more compliant approach to existing systems that may not be able to support hundreds of simulataneous file transfer connections in order to meet the exisiting volumes and implementation. | Advocates consider this a priority as it is a function that is also useful for consumers who would no longer have to send paper documents to the county. Recommend moving to 15.9 release if possible but ensuring it is a priority in the 16.2 release.
R16.2 | 27819 | Discontinue/Disenrollment failed citizenship/lawful presence/MEC/SSN/Income over 90 days | CovCA | The CalHEERS System shall run a Batch and discontinue program eligibility and disenroll (sending 834s) for consumers in a Covered California Plan (CCP) that were Re-Run through the FDSH and failed for citizenship, lawful presence, invalid SSN, or MEC (pending specific policy decisions) in an Insurance Affordability Program or an Unsubsidized application that had verification pending over 90 days. As appropriate, CalHEERS shall generate NOD01s. The CalHEERS System shall run a Batch and disenroll (sending 834s) for consumers in a CCP that were Re-Run through the FDSH and failed eligibility with a status of ineligible (for example, transition to MAGI-Medi-Cal) and generate appropriate NOD01s if not generated previously when ineligible status determined. The CalHEERS System shall repeat this Batch run for all re-run cases through the FDSH until all conditional eligibility failed for verification over 90 days have been discontinued/disenrolled (834)/noticed. | Advocates request to see notices that were sent to consumers to inform them that they needed to submit additional evidence of their citizenship or immigration status. We also want additional information about any additional efforts being made to reach out to these people including the opportunity to review Service Center Scripts. Additionally we would like confirmation that the notices will be translated into threshold languages.H12
R16.2 | 35243 | SB 1341- Scope and estimate costs to transfer NOA generation to SAWS | DHCS | This CR is a request for Accenture’s support to help define and cost estimate the CalHEERS’ solution for movement NOA functionality from CalHEERS to SAWS. A “SB 1341 Medi-Cal Notices Solutions Concepts” document has been drafted that contains alternative approaches for changing the CalHEERS notice functionality. Each of the SAWS Consortia and Accenture will review the alternatives, modify if appropriate, and then provide a cost estimate of the alternatives for budgeting purposes. When budget and approach decisions are made, the CR will be used to move forward with a solution design. From SB 1341: "This bill would require the Statewide Automated Welfare System to be the system of record for Medi-Cal and to contain all Medi-Cal eligibility rules and case management functionality. The bill would, notwithstanding this provision, authorize the California Healthcare Eligibility, Enrollment, and Retention System (CalHEERS) to house the business rules necessary for an eligibility determination to be made, as specified, pursuant to the federal Patient Protection and Affordable Care Act. The bill would, if that authority is exercised, require CalHEERS to make the business rules available to the Statewide Automated Welfare System consortia to determine Medi-Cal eligibility. The bill would specify the manner, effective January 1, 2016, in which the functionality to create and send notices of action for the Medi-Cal and premium tax credit programs would be implemented, including a requirement that the Statewide Automated Welfare System be used to generate noticing language and notice of action documents." | Advocates urge that implementation of AB 617 occur concurrently with SB 1314 so that design accounts for these statutory requirements including a consolidated notice. Implementing separately would be more costly and consumers are confused by the current multiple notices.
R16.2 | 37037 | eHIT Schema 4.0 | DHCS & CovCA | This change is opened as a place holder to capture and enhance the functionality post deployment of schema 3.0. The purpose of this CR is develop the Design Artifacts (e.g. BSD), and Build Artifacts (e.g. IDD) for the requested 4.0 eHIT updates.
R16.2 | 40149 (New) | Create NOD16 for Expedited Application (CR7169) | CovCA | Covered CA discovered that during the process of entering Paper Applications, SCRs had to revisit applications multiple times because the Consumer failed to enter needed information. In an effort to reduce the time it takes to complete the paper application process, Covered CA would like for Service Center Representatives (SCRs) and/or any Covered CA designated role, to be able to skip required fields and continue entering the information provided by the Consumer. The system must be able to notify the Consumer of needed missing information and task the Service Center Representative when the missing information is received via mail, fax, or document upload.
R16.2 | 45507 (New) | Former Foster Youth Phase 2 | DHCS | Phase 2 of CR 3066. Please see CR 3066 (R15.9) for description.
R16.2 | 45543 (New) | Allow authorized user functionality for overriding APTC | CovCA | Allow authorized users to override the APTC amount calculated by the Business Rules Engine (BRE) without exceeding the monthly premium amount and without triggering the BRE. The overridden APTC eligible amount will be stored instead of the original system-generated APTC amount. Cases with an overridden APTC shall automatically have an indicator put on the case for reporting purposes. When an authorized user overrides the system-generated APTC amount for a case the original or amended 834s will be sent to the carriers and transaction to HHS with the overridden APTC amount. Allow linked case numbers to be displayed and updated on an admin user page associated to the case. Allow authorized users to upload documents viewable only to authorized user
R16.2 | 45700 (New) | New NACK Response Code (HX005005) for IRS files EOM | CovCA | The Federal Data Services Hub (FDSH) is planning on creating a new NACK Response Code (HX005005) for situations involving submission issues between the FDSH and the IRS. This new NACK Response Code would be added to IRS services EOM H36, EOY H41, RRV H79 and APTC H19B bulk services. It would be defined as “Unexpected Exception Occurred While Transmitting to Trusted Data Source”. It would be similar to the existing codes HX009000 and HX005001 which involve system exceptions from the FDSH or the IRS.
R16.2 | 45778 (New) | Modify CMS Interim Payment Report to Use 1095 Query for benefit year 2014 and forward | CovCA | Modify CMS Interim Payment Report to Use 1095 Query. Currently both queries submit information to IRS, 1095 for consumer, the Interim Payment Report for carriers. This change request is to make both reports match.
R16.2 | 45851 (New) | Data Extract for Potential Reevaluation of Medi-Cal Eligibility with Updated 2015 FPLs | DHCS | This Change Request is for CalHEERS to provide a data extract identifying Medi-Cal beneficiaries whose 2015 eligibility determinations may potentially have been impacted by the updated 2015 FPLs (with implementation of CR 33930).
R16.2 | 46047 (New) | IAP Transition - APTC to MC and MC to APTC | CovCA & DHCS | This CR is intended to address current gaps in functional and technical design by: 1) enhancing the timing by which APTC//QHP eligbility and enrollment is terminated, 2) implementing a new notice to inform consumers about the transition from Coveed CA to Medi-Cal and Medi-Cal to Covered CA, 3) enahncing reports available to Covered CA, DHCS, and Counties to monitor individuals / cases who have been found Medi-Cal eligibile by CalHEERS.
R16.2 | 46147 (New) | DOB Field Enhancement | DHCS | The functionality of the Date Of Birth (DOB) field in CalHEERS will default to current year if not selected by the user. This is causing an issue with the identify member process, with further impacts to eligibility. In order to prevent incorrect eligibility, the Date of Birth field in CalHEERS should not default to any year. This must be a required field for entry by the consumer. A pop-up note indicating how important it is to verify the correct year was entered is also advisable to ensure correct data entry of this critical field.
R16.2 | 46383 (New) | Address Enrollment Business Rules for RAC with Eligibility Updates | CovCA | To meet federal and state regulation, Covered California must redetermine eligibility and implement the new eligibility if an enrollee reports a change that affects their eligibility for APTC / CSR or enrollment in a QHP.
R16.2 | 46973 (New) | Specialty Drug Cap | CovCA
R16.2 | 47011 (New) | Minimum Liabiity Protection Language | CovCA | Plan shopping page requires a blanket statement informing consumers to read additional details about their health and dental plan coverage. It is expected that this would be static text on the Plan Selection Page, either at the top or bottom. Language expected to state, though this may be finalized in design: “This is a summary of commonly used benefits and the applicable copayments, coinsurance, and deductibles. Before making a plan selection, please download and review the plans’ Summary of Benefits and Coverage (SBC) and Evidence of Coverage (EOC) found on the Plan Details page.
R16.2 | 47370 (New) | Add Automation, Monitoring, and Alerting to the Inbound and Outbound 834/820/GI Batch processes - CR 36110 Phase 2 | CovCA | This CR is Phase II of CR36110 and will include the following based on CalHEERS recommendation: * APTC Recalculation & benchmark premium recalculation * APTC recalculation when coverage start date changed during Carrier effectuation * Flexible application changes * Map default provider information on 834
R16.2 | 47371 (New) | Add Automation, Monitoring, and Alerting to the Inbound and Outbound 834/820/GI Batch processes - CR 29022 Phase 2 | CovCA | This CR is Phase II of CR29022 and will include the following based on CalHEERS recommendation: * SCR specific Enrollment Transaction Details page * Reports
R16.2 | 47399 (New) | Update Business Rules for Mailing Address Changes (Portal) | CovCA | Modify CalHEERS business rules to NOT redetermination when a change to mailing address is reported through the portal.
R16.2 | TBD (New) | Medi-Cal Access Program Integration Phase 2 | DHCS | Phase 2 of CR 8517. Please see CR 8517 (R15.9) for description.
R16.2 | TBD (New) | Update 2016 Annual FPLs in CalHEERS | DHCS | This CR requests the annual update to the FPL Table in OPA with the actual 2016 FPL values in the 16.2 system release. In January 2016, the Federal Health and Human Services Agency will publish the 2016 Federal Poverty Levels (FPLs) in the Federal Register (FR). 2016 FPLs will be effective on the date published in the FR, and must be implemented by CalHEERS in the 16.2 release in order to minimize the population of beneficiaries that may be incorrectly determined not eligible for Medi-Cal based on 2015 FPLs between January 1, 2016, to the date of implementation by CalHEERS.

## Status Def
Status | Definition
Accenture Access Impact | Once CCB approves the CR to move from "Proposed" to "Accenture Assess Impact", Accenture will analyze based on business requirements and identify initial Rough Order of Magnatitude (ROM) cost. In parallel track, the State also conducts its analysis (see State Assess Impact). Once CCB reviews and approves the requirements and cost estimation, the CR status becomes "Approved for Design".
Approved for Design | Once CCB approves for Design, the CR status becomes "Approved for Design". This authorizes Joint Application Design (JAD) sessions to begin where requirements are reviewed and designs of the system functionalities are documented. The output from the JADs is the final design document for the CR.
Approved for Implementation | Once the design artifacts are signed off by the sponsor(s), the CalHEERS State staff will verified and updated cost information and present to CCB for final approval. Once CCB approves, the CR status becomes "Approved for Implementation".
CCB Review | The Change Control Board (CCB) consists of three voting members; they are the Project Director of CalHEERS, the Chief Tecnology Officer of Covered CA, ad the Chief Information Officer of Department of Health Care Services). As CRs enter each phase of the Software Development Life Cycle (up to Build), they are presented to the voting members for review and approval. When a CR are presented to the Change Control Board (CCB) for approval, any actions items related to the CR are captured and mitigated prior to CCB determining approval/non-approval.
Closed | All work completed, verified, and invoiced.
Mitigated | This status identifies items that are reported as ‘in the system’; however, there were no requirements or artifacts that reference the solution. As such, until the State receives documentation and the resolution is reviewed and approved, the changes remain in "Mitigation" status.
New | After following internal governance process, the sponsor (DHCS or Covered CA) or CalHEERS initates the Change Request (CR). The CR is created and recorded in the CalHEERS Project's change request tracking system. The CR status becomes "New".
Proposed | After creating and recording the CR, additional details are added to the CR by the CalHEERS business analyst(s), and an email is sent to the CalHEERS' State Change Control Lead. The CR status is changed to "Proposed" where the next step is for the Change Control Board to review and approve.
State Access Impact | Once CCB approves the CR to move from "Proposed" to "State Assess Impact", the State will analyze impact and determine readability. In parallel track, Accenture also conducts their analysis (see Accenture Assess Impact). Once CCB reviews and approves the requirements and cost estimation from Accenture, the CR status becomes "Approved for Design".

## Acronyms
Acronym | Definition
ACA | Affordable Care Act
ACWDL | All County Welfare Directors' Letter
AE | Accelerated Enrollment
AIM | Access for Infants and Mothers (now know as Medi-Cal Access Program)
APTC | Advanced Premium Tax Credit
AR | Authorized Representative
ASHS | Applicable State Health Subsidy
BDA | Beginning Date of Aid
BI | Business Intelligence
BPEL | Business Process Execution Language
BRE | Business Rules Engine
BSD | Business Service Definition
CalHEERS | California Healthcare Eligibility, Enrollment, and Retention System
CalHSMI | CalHEERS / SAWS / MEDS Interface
CalWIN | One of the three SAWS, provides service to 18 counties
CalWORKS | California Work Opportunities and Responsibility for Kids
CCHIP | California Children's Health Insurance Programs
CDSS | California Department of Social Services
CE | Continuous Eligibility
CEC | Continuous Eligibility for Children
CEE | Certified Enrollment Entity
CEW | Certified Eligibiilty Worker
CFR | Code of Federal Regulations
CIA | Certified Insurance Agent
CIN | Client Index Number
C-IV | One of the three SAWS, provides service to 39 counties
CMS | Centers for Medicare & Medicaid Services
CPP | Consumer Protection Programs
CSR | Cost Sharing Reduction
CWDA | (CA) County Welfare Directors Association
DE | Deemed Eligibility
DER | Determination Eligibility Response
DHCS | Department of Health Care Services
DMV | Department of Motor Vehicles
DSH | (Federal) Data Services Hub
ECM | Enterprise Content Management
EDR | Eligibility Determination Request
eHIT | Electronic Health Information Transfer
eICT | Electronic Inter-County Transfer Interface
ESB | Enterprise Service Bus
EW | Eligibility Worker
FFC | Former Foster Care
FFM | Federally Facilitated Marketplace
FPL | Federal Proverty Level
GI | General Inquiry
HCO | Health Care Options
HTTP | HyperText Transfer Protocol
HTTPs | HyperText Transfer Protocol Secure
HX | Health Exchange and Medi-Cal Interface (HEMI) Transaction
IAP | Insurance Affordability Program
ICD | Interface Control Document
ICT | Inter County Transfer
IDD | Interface Design Document
IFSV | Income and Family Size Verification
INS | Immigration and Naturalization Service
IRS | Internal Revenue Service
JAD | Joint Application Design
LEADER | One of the three SAWS, provides service to Los Angeles county
LP | Lawful Presence
LRS | Leader Replacement System
M/C | Medi-Cal
MAGI | Modified Adjusted Gross Income
MEC | Minimum Essential Coverage
MEDS | Medi-Cal Eligibility Data System
MOE | Maintenance Of Effort
NA Back 9 | A universal back page to be used on all NOAs for Medi-Cal, CalWORKS, and/or CalFresh.
NOA | Notice of Action
NOD | Notice of Deficiency | Notice of Decision?
NQI | Newly Qualified Immigrants
OBIEE | Oracle Business Intelligence Enterprise Edition
OPA | Oracle Policy Administration
OTech | Office of Technology Services (under California Department of Technology)
PA | Public Assistance
PAI | Projected Annual Income
PBE | Plan-Based Enroller
PII | Personally Identifiable Information
PMPM | Per Member Per Month
PRUCOL | Permanently Residing Under Color of Law
QHP | Qualified Health Plan
QNC | Qualified Non-Citizen
RIDP | Remote Identify Proofing
RRV | Renewal and Redetermination Verification
SAWS | Statewide Automated Welfare System
SBM | State-Based Marketplace
SCR | Service Center Representative
SFTP | Secure File Transfer Protocol
SLA | Service Level Agreement
SOAP | Simple Object Access Protocol
SOC | Share of Cost
SSA | Single Statewide Application
SSI/SSP | Supplemental Security Income/State Supplementary Payment
SSL | Secure Sockets Layer
SSN | Social Security Number
TBD | To Be Determined
TMC | Transition Medi-Cal
UAT | User Acceptance Testing
UI | User Interface
VLP | Very Lawful Presence
XML | Extensible Markup Language