## IAP 24 month Roadmap CR Listing
RE-LEASE | CR NUMBER | TITLE | RE- QUESTOR | BRIEF DESCRIPTION | STATUS UPDATES for 08/30/2018 AB 1296 MEETING
R18.9 | 122459 | Updates to Former Foster Youth Language (UCD) | DHCS | The change request is part of the UCD Feature Stream to update the FFY language. The FFY referral question and text will be streamlined and simplified across all modes: Intake, Report a Change (RAC) and Renewals. | CR is scheduled for R18.9 implementation.
R18.9 | 109700 | Verification Caching Rules Updates | DHCS & CovCA | The intended outcome of this change request is to update FDSH verification triggers and caching rules to be in compliance with CMS guidance. On March 10, 2017, CalHEERS received comments from Centers For Medicare & Medicaid Services (CMS) on CalHEERS design artifact DVF01.16 – Verification Caching regarding these triggering conditions. With regard to the Social Security Administration (SSA) Composite Service, CMS guidance regarding its interpretation of 42 CFR §§ 435.916(a) and 435.916.(d)(1) is that only a change to Social Security Number (SSN) should trigger an electronic re-verification, and that such verification at the time of the reported change should only include verification of the SSN (ie, call to SSA Composite Service for an SSN change should not include reverification of citizenship, deceased or incarcerated, as is current CalHEERS functionality). With regard to the income verification services through Internal Revenue Service (IRS) (which also includes FTB and EDD in California), CMS has further advised that per 42 CFR §§ 435.91(a), 435.916(d)(1) and 435.916(d)(1)(i), only a change to attested income should trigger re-verification of income at the time a change is reported. With regard to FDSH calls to the Department of Homeland Security (DHS) for verification of immigration status, CMS has advised that triggering conditions for verification of immigration status should also be based only on changes to data elements impacting immigration status. | CR is scheduled for R18.9 implementation.
R18.9 | 122438 | Display Income Start & End Dates Across All Modes of the Application (UCD) | DHCS & CovCA | This CR is for the implementation of displaying the income start and end dates acress all modes of the application as part of on-going UI updates. | CR is scheduled for R18.9 implementation.
R18.9 | 121556 | Implementation of Updates to Editing Income & Deductions, Income History for Renewals (UCD) | DHCS & CovCA | The purpose of this CR is to implement updates to the editing of income and deductions for the Renewals flow based on the consumer testing performed in early 2018 and to align the Renewals and RAC flow. It aslo includes the addition of the income history section. | CR is scheduled for R18.9 implementation.
R18.9 | 122440 | Account Home Messaging during Renewals (UCD) | DHCS & CovCA | The purpose of this CR is to ensure the messaging on the consumer's home page includes information about completing the renewal application if they have reported a change to their current year application. | CR is scheduled for R18.9 implementation.
R18.9 | 115338 | 2019 Renewals CR | CovCA & DHCS | The purpose of this CR is to update the Fair Share percentage and make updates to improve the Renewals and Open Enrollment process for all users. | CR is scheduled for R18.9 implementation.
R18.9 | 90113 | User Interface Updates for Renewals | CovCA & DHCS | The purpose of this CR is to continue the User Interface upgrades on the CalHEERS consumer portal. The focus of the changes is creating a simplified and user friendly experience for renewals. | CR is scheduled for R18.9 implementation.
R18.9 | 116755 | 2018 18.9 Notices | CovCA & DHCS | The purpose of this CR is to update notices based on the CRs implemented in the 18.9 Release. The NOD12 is being updated in this release. | CR is scheduled for R18.9 implementation.
R18.9 | 124918 | DIVS Verification and Mixed Households | CovCA & DHCS | The purpose of this CR is to extend the usability of the DIVS solution to Covered CA individuals in Mixed Households. | CR is scheduled for R18.9 implementation.
R18.9 | 117094 | Enhancement to Fax Cover Page on NOD01 and NOD03 | CovCA | The purpose of this CR is to move the Fax Cover Page from the back of the notice to the front of the notice to better inform Covered CA consumers that are Conditionally Eligible that they need to provide documentation or more information | CR is scheduled for R18.9 implementation.
R18.9 | 112835 | Section 508 Refresh ADA Changes | CalHEERS, CovCA & DHCS | The purpose of this CR is to make updates to the CalHEERS website in order to meet the Americans with Disabilities Act regulations and to be ADA compliant. | CR is scheduled for R18.9 implementation.
R18.9 | 115166 | Convert Remaining Consumer Pages to React Framework | CalHEERS, CovCA & DHCS | This change request will update consumer facing pages to Facebook React framework. | CR is scheduled for R18.9 implementation.
2019 Q1 19.2 | 109927 | Immigration Phase III | DHCS | With the implementation of CR 69974, new data elements previously unavailable in the CalHEERS system were made available and are now utilized to make eligibility determinations. CalHEERS receives the citizenship verification information Verify Lawful Presence (VLP) interface, but cannot currently transmit the information to MEDS and/or SAWS. Also with the implementation of CR 69974, the VLP will not be called for immigrants who are in a state-funded immigration status. Currently based solely on a document the county eligibility worker is not able to provide full scope Medi-Cal to these immigrants. | CR is planned for 2019 implementation.
2018 Q3/ 2019 Q1 R18.9 R19.2 | 92298 | SSA Title II Income and Disability Indicator Verification | DHCS | This CR has two separate, primary purposes: 1) to implement electronic verification of Title II Income through the Federal Data Services hub. 2) to implement use of the SSA disability indicator to assign disabled individuals with incomes at or below 128% FPL to new aid codes L6 and L7 instead of M1 and M2. This reduces manual verifications and aligns functionality with federal funding requirements for the New Adult Group regarding populations that were Medicaid eligibility before the implementation of the ACA. | CR is planned for 2019 Q1 implementation.
R19.2 | 126279 | Update Treatment of a Tax Dependent's MAGI-Based Income in the Individual MAGI Medi-Cal Budget | DHCS | This CR addresses a system gap to ensure MAGI based income is counted in the eligibility determination when a dependent is claimed by someone other than individuals parent and the parent is not included in the individuals MAGI household composition. | CR is planned for 2019 Q1 implementation.
R19.2 | 92295 | FDSH VLP Interface Update to version 37 with Steps 2 and 3 | DHCS & CovCA | The California Healthcare Eligibility, Enrollment, and Retention System (CalHEERS) currently uses the H59-Verify Lawful Presence (VLP) version 33 service to verify immigration status. The Centers for Medicare & Medicaid Services (CMS) has indicated that the VLP version 33 service will be retired on April 26, 2019. It is being replaced with H104-VLP version 37 service. CalHEERS will need to upgrade from VLP version 33 to VLP version 37 as well as implement VLP steps 1a, 1b, 2 and3, making this a full version upgrade. With this upgrade, functionality will be needed so that a call to the VLP from either access channel (CalHEERS or SAWS) for all steps can be performed. | CR is planned for 2019 Q1 implementation.
R19.2 | 123315 | 2019 R19.2 Notice Changes | CovCA & DHCS | The purpose of this CR is to update notices based on the CRs implemented in the 19.2 Release. | CR is planned for R19.2 implementation.
R19.2 | 119170 | Account Transfer Phase I | CovCA | The intended outcome and output of this CR is the cross-vendor coordination between Accenture and GI to develop: 1) 1. A set of Use Case scenarios that focus on the eligibility processing interactions related to implementation of Account Transfer(AT) API for Medi-Cal, mixed household and CC (APTC or QHP only) eligible households, 2) A set of screen transition diagrams that illustrate the user experience post Account Transfer implementation for multiple scenarios for a consumers or other end users, and 3) A set of technical documents outlining the impacts. | CR is planned for 2019 Q1 implementation.
R19.2 | 124966 | Convert Remaining Pages to React (part 2) | CalHEERS, CovCA & DHCS | This change request will update Admin facing pages to Facebook React framework. | CR is planned for R19.2 implementation.
R19.4 | 98352 | SEP Electronic Verification Vendor Integration | CovCA | Covered California will be procuring a SEP Electronic Verification Vendor to automate the verification of SEP reasons. The anticipated SEP Electronic Verification Vendor solution will receive data from CalHEERS needed to perform SEP eligibility verification for loss of health insurance coverage. The result of the eligibility verification performed electronically by the vendor solution, with no manual intervention, will be returned to CalHEERS. CalHEERS will need to successfully integrate with the Vendor which will include updates to existing application pages to collect additional data as well as sending and receiving data between CalHEERS and the Vendor. | CR is planned for 2019 Q2 implementation.
R19.6 | 106890 | Income Data Quality Enhancements | DHCS | This CR enhances the following: 1) adding validation requirements for individuals to include their spouse on the application when indicating that they file their taxes as 'Married Filing Jointly.' 2) changed the validation requirements for contact information to allow individuals to report tax dependent addresses out of the state and country 2) aligns the treatment of $0 income revised from the federal data hub for both the CalHEERS and SAWS access channel 3) addressing small defects identified post deployment of CR 70497. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 122183 | Medi-Cal Deemed Infant and Medi-Cal Access Infant Program Functionality | DHCS | The purpose of this CR is to: 1) Program the functionality into CalHEERS for the Deemed Eligibility for Infants program, including SAWS requirements. To allow Deemed Infants to be added to the case of a MAGI Medi-Cal mother while bypassing all tax household information. 2) Provide full functionality to register infants in CalHEERS for Medi-Cal Access Infant Program (MCAIP) allowing infant(s) (E6/E7) to be added to the case of a Medi-Cal Access Program (MCAP) mother while requiring a MAGI determination at infant registration. 3) Add MCAIP E6/E7 infants eligibility and renewal functinality to CalHEERS. 4) Enhance CCHIP electronic verifications to align with the CMS electronic verification plan. 5) Enhance current CCHIP eligibility and renewal functionality in CalHEERS. Adding Pending Eligibility determinations, resulting in update changes to noticing and the CCHIP daily extract file. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 119408 | Non-Compliance Reasons | DHCS | The purpose of this CR is to have CalHEERS provide more detail to SAWS, in the form of eligibility evaluation reasons, when a person is denied or discontinued from MAGI Medi-Cal for existing non-compliance reasons (e.g. failure to apply for Medicare). The additional detail will allow SAWS to automate NOAs and will reduce county workload. The non-compliance reasons were originally included in CR 81756, Ineligibility Reason Codes for SAWS Notices, before being moved into the new CR 119408. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 119301 | BREfS Phase C - Technical Updates to separate post-eligibility business logic | DHCS & CovCA | This is a technical change request and it is part 1 of the changes. Part 2 is CR#119303. Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS to return an eligibility determination via the Determination of Eligibility Response (DER) operation. The CalHEERS eligibility determination results must be accepted by counties, since neither the existing eHIT interface, nor the BRE functionality on the CalHEERS portal currently provide a “preview” of eligibility or the ability to override a CalHEERS eligibility determination. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 119303 | BREfS Phase C - Technical Updates to separate Eligibility and Verification processing | DHCS & CovCA | This is a technical change request and is part 2 to CR#119301. | CR is planned for 2019 Q2 implementation.
2017 Q3 2018 Q2 2019 Q2 | 83286 109744 | BREfS Phase C - Part 1: Same Day Eligibility Remediation | DHCS & CovCA | Currently, County Eligibility Workers(CEWs) processing eligibility may receive unexpected results from CalHEERS based on the incorrect case data input. In many of these occurrences the CEW’s may be able to update the case data within the same day and request for re-determination of eligibility; however, current actions require additional steps across systems and the possible use of overrides. While subsequent evaluations can remediate a consumer’s eligibility, this is not so in all cases. For instance, when eligibility of the consumer is determined outside of the expected program (i.e. MAGI Medi-Cal, APTC, etc), subsequent evaluations are ineffective when the consumer protection protocols (i.e. Soft Pause) and transition rules (i.e. Carry Forward) are factors in the same day on-going eligibility. Steps to remediate these occurrences cannot be done immediately. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 126224 | 2019 19.6 Notice Changes | CovCA & DHCS | The purpose of this CR is to update notices based on the CRs implemented in the 19.6 Release | CR is planned for 2019 Q2 implementation.
2019 Q2 | 125678 | Updates for Agency and Agent Portals | CovCA | The purpose of this CR is to enable the user to view Agent delegation history in CalHEERS, and perform partial Book of Business transfers with either Agencies or Agents. It will also automate various reports and notifications within CalHEERS for Agency functions. | CR is planned for 2019 Q2 implementation.
2019 | 82978 | County Inmate Program | DHCS | The purpose of this CR is to allow CalHEERS to accept applications for County MCIEP from the SAWS access channel. County staff will be able to process eligibility for County Inmate Program (Aid Code N7 and N8) and County Compassionate Release/Medical Probation Program (Aid Code K6, K7, K8, and K9). | CR is planned for 2019 implementation.
2019 | 109747 | BREfS Phase C - Part 2: Override Eligibility Determination Functionality | DHCS & CovCA | Currently, Counties have the ability to override SAWS and MEDS eligibility but CalHEERS was not programmed to consume that information and apply the updated information in CalHEERS. Under MEDIL I 14-11, DHCS provided “updated guidance on workarounds and system overrides within Statewide Automated Welfare Systems (SAWS) and the California Healthcare Eligibility, Enrollment and Retention System (CalHEERS) that are approved by the Department of Health Care Services (DHCS) for use by county eligibility workers for Medi-Cal eligibility determinations. The purpose of a workaround or override is to ensure implementation and recording of the appropriate eligibility determination when one or more automation system may not accurately implement, record, or display that information.” | CR is planned for 2019 implementation.
2019 | 82920 | BREfS Phase D - Separating Verification Service | DHCS & CovCA | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS. CalHEERS uses VIED to coordinate the verifications responses into the BRE and return an eligibility determination via the Determination of Eligibility Response (DER) operation. | CR is planned for 2019 implementation.
2019 | 61104 | Plan Dependency Definition | CovCA | The CalHEERS System shall allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application. The CalHEERS system shall only allow the following individuals to enroll in the same Covered CA enrollment group/plan: Married spouses; Registered domestic partners; Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners; Disabled adult children of any age (including 26 or above); Siblings under the age of 19. | CR is planned for 2019 implementation.
2020 Q1 | 95185 | SEP Pre-Enrollment Verification | CovCA | Add verification to verify SEP Reasons before consumers are effectuated in a QHP/QDP. | CR is planned for 2020 Q1 implementation.
2020 Q2 | 95184 | SEP Dropdown and Workflow | CovCA | The intended outcome is: 1. Update and add to the available SEP reasons, 2. Update and add to the business rules for each existing and new SEP reason and coverage date category, 3. Dynamically display the SEP reasons in the dropdown list based on the user role and application mode, and 4. Update eHIT/SAWS accordingly | CR is planned for 2020 Q2 implementation.

## Status Def
Status | Definition
Accenture Access Impact | Once CCB approves the CR to move from "Proposed" to "Accenture Assess Impact", Accenture will analyze based on business requirements and identify initial Rough Order of Magnatitude (ROM) cost. In parallel track, the State also conducts its analysis (see State Assess Impact). Once CCB reviews and approves the requirements and cost estimation, the CR status becomes "Approved for Design".
Approved for Design | Once CCB approves for Design, the CR status becomes "Approved for Design". This authorizes Joint Application Design (JAD) sessions to begin where requirements are reviewed and designs of the system functionalities are documented. The output from the JADs is the final design document for the CR.
Approved for Implementation | Once the design artifacts are signed off by the sponsor(s), the CalHEERS State staff will verified and updated cost information and present to CCB for final approval. Once CCB approves, the CR status becomes "Approved for Implementation".
CCB Review | The Change Control Board (CCB) consists of three voting members; they are the Project Director of CalHEERS, the Chief Tecnology Officer of Covered CA, ad the Chief Information Officer of Department of Health Care Services). As CRs enter each phase of the Software Development Life Cycle (up to Build), they are presented to the voting members for review and approval. When a CR are presented to the Change Control Board (CCB) for approval, any actions items related to the CR are captured and mitigated prior to CCB determining approval/non-approval.
Closed | All work completed, verified, and invoiced.
Mitigated | This status identifies items that are reported as ‘in the system’; however, there were no requirements or artifacts that reference the solution. As such, until the State receives documentation and the resolution is reviewed and approved, the changes remain in "Mitigation" status.
New | After following internal governance process, the sponsor (DHCS or Covered CA) or CalHEERS initates the Change Request (CR). The CR is created and recorded in the CalHEERS Project's change request tracking system. The CR status becomes "New".
Proposed | After creating and recording the CR, additional details are added to the CR by the CalHEERS business analyst(s), and an email is sent to the CalHEERS' State Change Control Lead. The CR status is changed to "Proposed" where the next step is for the Change Control Board to review and approve.
State Access Impact | Once CCB approves the CR to move from "Proposed" to "State Assess Impact", the State will analyze impact and determine readability. In parallel track, Accenture also conducts their analysis (see Accenture Assess Impact). Once CCB reviews and approves the requirements and cost estimation from Accenture, the CR status becomes "Approved for Design".

## Acronyms
Acronym | Definition
ACA | Affordable Care Act
ACWDL | All County Welfare Directors' Letter
AE | Accelerated Enrollment
AIM | Access for Infants and Mothers (now know as Medi-Cal Access Program)
APTC | Advanced Premium Tax Credit
AR | Authorized Representative
ASHS | Applicable State Health Subsidy
BDA | Beginning Date of Aid
BI | Business Intelligence
BPEL | Business Process Execution Language
BRE | Business Rules Engine
BSD | Business Service Definition
CalHEERS | California Healthcare Eligibility, Enrollment, and Retention System
CalHSMI | CalHEERS / SAWS / MEDS Interface
CalWIN | One of the three SAWS, provides service to 18 counties
CalWORKS | California Work Opportunities and Responsibility for Kids
CCHIP | California Children's Health Insurance Programs
CDSS | California Department of Social Services
CE | Continuous Eligibility
CEC | Continuous Eligibility for Children
CEE | Certified Enrollment Entity
CEW | Certified Eligibiilty Worker
CFR | Code of Federal Regulations
CIA | Certified Insurance Agent
CIN | Client Index Number
C-IV | One of the three SAWS, provides service to 39 counties
CMS | Centers for Medicare & Medicaid Services
CPP | Consumer Protection Programs
CSR | Cost Sharing Reduction
CWDA | (CA) County Welfare Directors Association
DE | Deemed Eligibility
DER | Determination Eligibility Response
DHCS | Department of Health Care Services
DMV | Department of Motor Vehicles
DSH | (Federal) Data Services Hub
ECM | Enterprise Content Management
EDR | Eligibility Determination Request
eHIT | Electronic Health Information Transfer
eICT | Electronic Inter-County Transfer Interface
ESB | Enterprise Service Bus
EW | Eligibility Worker
FFC | Former Foster Care
FFM | Federally Facilitated Marketplace
FPL | Federal Proverty Level
GI | General Inquiry
HCO | Health Care Options
HTTP | HyperText Transfer Protocol
HTTPs | HyperText Transfer Protocol Secure
HX | Health Exchange and Medi-Cal Interface (HEMI) Transaction
IAP | Insurance Affordability Program
ICD | Interface Control Document
ICT | Inter County Transfer
IDD | Interface Design Document
IFSV | Income and Family Size Verification
INS | Immigration and Naturalization Service
IRS | Internal Revenue Service
JAD | Joint Application Design
LEADER | One of the three SAWS, provides service to Los Angeles county
LP | Lawful Presence
LRS | Leader Replacement System
M/C | Medi-Cal
MAGI | Modified Adjusted Gross Income
MEC | Minimum Essential Coverage
MEDS | Medi-Cal Eligibility Data System
MOE | Maintenance Of Effort
NA Back 9 | A universal back page to be used on all NOAs for Medi-Cal, CalWORKS, and/or CalFresh.
NOA | Notice of Action
NOD | Notice of Deficiency | Notice of Decision?
NQI | Newly Qualified Immigrants
OBIEE | Oracle Business Intelligence Enterprise Edition
OPA | Oracle Policy Administration
OTech | Office of Technology Services (under California Department of Technology)
PA | Public Assistance
PAI | Projected Annual Income
PBE | Plan-Based Enroller
PII | Personally Identifiable Information
PMPM | Per Member Per Month
PRUCOL | Permanently Residing Under Color of Law
QHP | Qualified Health Plan
QNC | Qualified Non-Citizen
RIDP | Remote Identify Proofing
RRV | Renewal and Redetermination Verification
SAWS | Statewide Automated Welfare System
SBM | State-Based Marketplace
SCR | Service Center Representative
SFTP | Secure File Transfer Protocol
SLA | Service Level Agreement
SOAP | Simple Object Access Protocol
SOC | Share of Cost
SSA | Single Statewide Application
SSI/SSP | Supplemental Security Income/State Supplementary Payment
SSL | Secure Sockets Layer
SSN | Social Security Number
TBD | To Be Determined
TMC | Transition Medi-Cal
UAT | User Acceptance Testing
UI | User Interface
VLP | Very Lawful Presence
XML | Extensible Markup Language