## IAP 24 month Roadmap CR Listing
RE-LEASE | CR NUMBER | TITLE | REQUESTOR | BRIEF DESCRIPTION | Advocate Comments | STATUS UPDATES for 01/12/2018 AB 1296 MEETING
R18.2 - (Scheduled Deployment Date 02/12/2018)
R16.2 2017 Q3 R18.2 | 4469 82977 | State Inmate Program | DHCS | The purpose of this CR is to automate State MCIEP in CalHEERS. The CalHEERS application for State Inmates will be dynamic based on user type and MCIEP staff will be able to process eligibility for State Inmate Program (Aid Code N5 and N6) and State Medical Parole Program (Aid Code K2, K3, K4, and K5) and generate the MAGI-MC NOA with State MCIEP snippet language. DHCS MCIEP staff will also have the ability to enter negative action reasons for State MCIEP for denial or discontinuance. DHCS MCIEP staff will be responsible for case management. | (3/20/15) What NOAs are currently being generated that this CR will help suppress? DHCS> No current CalHEERS notices would be suppressed. This CR implements state inmate eligibility in CalHEERS. NOAs currently generated by state staff will continue to be generated by state staff until this CR is implemented. | CR is scheduled for R18.2 implementation.
2017 Q3 R18.2 | 81432 | Update to Income Service Request and Income Caching Rules | DHCS | CalHEERS leverages three income verification services (IRS, FTB, EDD). With R16.9, a new income type (MAGI PAI) was added and incorporated into the income verification caching rules. Currently if at least one of the income types is not cached, all three income verification services are invoked again to re-verify the income data attested by the consumer. The intended outcome is for CalHEERS to enhance the income verification caching rules to reduce the frequency of the income verification services being called. |  | CR is scheduled for R18.2 implementation.
R18.2 | 90492 | Cases Stuck in Medi-Cal Renewal Mode | DHCS & CovCA | When an action taken by the county results in ineligibility or when a negative action is conducted for one or all individuals in the MAGI Medi-Cal case and there is no MAGI Medi-Cal Renewal ‘Disposition’ sent for the case by SAWS, the case becomes "stuck" in Renewal Mode. This creates a manual workload so Covered California eligible consumers on the case are able to change or select a plan. This CR creates automation and eliminates the need for the current manual process. Known actions that cause this problem include: • Negative Action is sent without a Renewal Disposition • Report A Change is sent without a Renewal Disposition • Case going through the Short Term Negative Action Process |  | CR is scheduled for R18.2 implementation.
R18.2 | 92697 | Update Version of FDSH RIDP | CalHEERS | The Federal Data Services Hub (FDSH) Remote Identify Proofing (RIDP) Service v1 (Service ID: H1 and H66) will be retired effective February 25, 2018. CalHEERS must migrate to RIDP v2 prior to this date. The purpose of this CR will ensure CalHEERS comply with the federal updates and move to H1.1 FDSH RIDP v2. The CR will also include align new response codes and add/update current portal messaging. RIDP v2 (H1.1) provides enhancements to help consumers pass through RIDP and reduce the instances when consumers need to call the Fraud Archiving Reporting System (FARS). If Experian is down, the Requester (CalHEERS) must retry sending the request. CalHEERS will implement a mechanism to determine if Experian is down, and then notify consumers that CalHEERS is unavailable. |  | CR is scheduled for R18.2 implementation.
R17.9 R18.2 | 92588 | Implement Agency Module Phase 1 - Part 2 | CovCA | This CR is implementing the hierarchy to support the Agency to Agent relationship in the CalHEERS system to mirror the Covered California policy change for Open Enrollment. With implementation of this CR, Agencies will be able to establish an account in CalHEERS, build their Agent roster, and manage their Agents. |  | CR is scheduled for R18.2 implementation.
R18.2 | 108405 | Remove Optional Text From Immigration Document Data Collection Fields | CovCA | The purpose of this CR is to reduce conditional eligibility by encouraging consumers to enter their immigration document infornation in the CalHEERS portal. The immigration document information fileds will remain optional but the word "Optional" will be removed from the screen. |  | CR is scheduled for R18.2 implementation.
R18.3 - (Scheduled Deployment Date 03/12/2018)
R18.3 | N/A | Annual FPL/COLA Updates | DHCS | The purpose of this Annual FPL update is to implement the FPLs released by the Federal Register in January each year into CalHEERS. |  | CR is scheduled for R18.3 implementation.
R17.6 & R17.7 R18.3 | 70497 | Modify the online single streamline application (SSApp) for: *Eligibility Results *Enrollment | DHCS & CovCA | The purpose of this CR is to complete the modifications for the online single streamline application (SSApp) that have not deployed. This release focuses on updates to the Eligibility Results Page and Health Care Enrollment pages. |  | CR is scheduled for R18.3 implementation.
R18.3 | 107740 | Upgrade Employer Sponsored Insurance (ESI) Minimum Essential Coverage (MEC) Hub Service to Version 2 | DHCS & CovCA / CalHEERS | The ESI MEC service provided by the Federal Data Services Hub (FDSH) allows state requesters to verify eligibility of Office of Personnel Management (OPM) health coverage for applicants. Due to the release of an updated version of the interface schema, CalHEERS must upgrade to Version 2 and make necessary coding changes to ensure proper endpoint connection. |  | CR is planned for R18.3 implementation.
R18.3 | 82347 | Allow Counties and Service Centers to Create and Manage Users for their own Organizations | DHCS & CovCA | This CR will create an internal page in the CalHEERS system where Counties and Services Centers can directly upload a provisioning worksheet to create users for their own organizations. Counties and Service Centers will also be able to reinstate users from their own organization and disable users from their own organization by users with the correct security privileges. |  | CR is planned for R18.3 implementation.
R18.3 | 83522 | Refactor Secure Mailbox Functionality | CovCA | In order to improve consumer experience of the Secure Mailbox's User Interface on the consumer portal, the Secure Mailbox Pages will be re-designed using REACT framework to be Mobile Responsive and in sync with SSApp as per UX standards. There will be no changes to the functionality of the Secure Mailbox, just the look and feel will be changed. |  | CR is scheduled for R18.3 implementation.
R18.4 - (Scheduled Deployment Date 04/09/2018)
R18.4 | 98639 | Household Re-Rating Logic | CovCA | The purpose of this CR is to enhance the CalHEERS system to not rerate the household in the following circumstances: a. If the non- AI/AN consumer selects the same Product (same 14 digit HIOS) or Plan (same 14 digit HIOS) but moves between CSR tiers (change in last 2 digits of same 14 digit HIOS) within a Silver product (e.g. moving between Silver 94, Silver 87, Silver 73, Silver 70 or no CSR). b. If the consumer selects the same Plan (same 16 digit HIOS) The household should be re-rated in the following scenarios: a. The consumer selects a new Product or metal tier (change of 14 digit HIOS) *Note: Product is EPO, PPO, HMO b. The consumer selects a new Issuer c. If the subscriber changes d. If a subscriber stays in the same QHP, but reports a move to a new rating area, all policy members will retain their age at the time of original Plan Year start date, but with the new rating area rates taking effect on the new effective date. • If there is a gap in coverage then the above rules do not apply and the household should be re-rated. |  | CR is planned for R18.4 implementation.
R18.6 - (Planned Deployment Date 06/04/2018)
R16.2 2017 Q3 2018 Q2 | 9428 82978 | County Inmate Program | DHCS | The purpose of this CR is to allow CalHEERS to accept applications for County MCIEP from the SAWS access channel. County staff will be able to process eligibility for County Inmate Program (Aid Code N7 and N8) and County Compassionate Release/Medical Probation Program (Aid Code K6, K7, K8, and K9). |  | CR is planned for 2018 implementation.
2018 Q2 | 101091 | Update Primary Contact Match to Permit Last Name Only Change | DHCS | With the implementation of eHIT Business Validation (BV) 145 in CR 10021 to prevent overlay of primary contact data, a series of demographic data points are used to identify person mismatches at the primary contact level. One of the top-tier matching criteria for BV145 is Last Name. However, due to the high volume of Last Name-only changes made by SAWS, this has caused BV145 to become the highest cause of EDR failures and is impacting county workloads. CalHEERS needs to enhance the matching criteria in order to allow last name-only changes without triggering BV 145. |  | CR is planned for 2018 Q2 implementation.
R18.6 | 87156 | Ineligbility Reason Codes for SAWS Notices | DHCS | The purpose of this CR is to have CalHEERS provide more detail to SAWS, in the form of eligibility evaluation reasons, when a person is denied or discontinued from MAGI Medi-Cal for existing reasons. The additional detail will allow SAWS to automate NOAs and will reduce county workload. |  | CR is planned for 2018 Q2 implementation.
2017 Q3 2018 Q2 | 83286 | BREfS Phase C - Standby Eligibility Service and Overrides: * Same Day Eligibility Remediation | DHCS & CovCA | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS to return an eligibility determination via the Determination of Eligibility Response (DER) operation. The CalHEERS eligibility determination results must be accepted by counties, since neither the existing eHIT interface, nor the BRE functionality on the CalHEERS portal currently provide a “preview” of eligibility or the ability to override a CalHEERS eligibility determination. |  | CR is planned for 2018 implementation.
2018 Q2 | 99895 | CalHEERS Update of FDSH FARS to Version 2.0 | DHCS & CovCA / CalHEERS | The current version of the Fraud Archiving Reporting System (FARS) service provided through the Federal Data Services Hub (FDSH) will be retired July 8, 2018. CalHEERS must upgrade to FARS Version 2, align new request and response codes and add/update current CalHEERS portal messaging for consumers. |  | CR is planned for 2018 Q2 implementation.
2018 Q1 2018 Q2 | 94030 | Immigration Document Data Collection | CovCA | The purpose of this CR is to reduce conditional eligibility for immigration status by implementing business validations for Alien# and Reciept/Card# fields to avoid VLP failures. |  | CR is planned for 2018 Q2 implementation.
2018 Q2 | 106572 | Implement Agency Roadmap Features | CovCA | Incorporate additional GI features to the Agency Portal and associated functionality. |  | CR is planned for 2018 Q2 implementation.
2018 Q2 | 108752 | Proration of APTC in GI | CovCA | The purpose of this CR is to modify the Get Insured system logic to allow proration of APTC for months in which the premium amount is prorated. Get Insured currently follows IRS rules of capping the APTC in months of proration. CMS accepts both capping and proration of APTC. |  | CR is planned for 2018 Q2 implementation.
2018 Q1 2018 Q2 2019Q1 | 95184 | SEP Dropdown and Workflow | CovCA | The intended outcome is: 1. Update and add to the available SEP reasons, 2. Update and add to the business rules for each existing and new SEP reason and coverage date category, 3. Dynamically display the SEP reasons in the dropdown list based on the user role and application mode, and 4. Update eHIT/SAWS accordingly |  | CR is planned for 2019 Q1 implementation.
2018 Q2 2019 Q1 | 95185 | SEP Pre-Enrollment Verification | CovCA | Add verification to verify SEP Reasons before consumers are effectuated in a QHP/QDP |  | CR is planned for 2019 Q1 implementation.
2018 Q2 | 98251 | Document Imaging and Verification Solution Integration | CovCA | Covered California has procured a solution that will automate the verification of documents such as immigration, citizenship, income, and identity. The solution will send and receive data that is needed to perform the verification with CalHEERS. The new solution is anticipated to: · Reduce manual verifications by as much as 75 percent · Speed up the overall conditional eligibility verification process · Allow Service Center staff to focus on complex customer inquiries and other tasks |  | CR is planned for 2018 Q2 implementation.
2018 2019 | 61104 | Plan Dependency Definition | CovCA | The CalHEERS System shall allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application. The CalHEERS system shall only allow the following individuals to enroll in the same Covered CA enrollment group/plan: Married spouses; Registered domestic partners; Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners; Disabled adult children of any age (including 26 or above); Siblings under the age of 19. |  | CR is planned for 2019 implementation.
2018 - Quarter 2 & Beyond (Planned Deployment Date TBD)
2018 Q2/Q3 | 90113 | User Interface Updates for Renewals | CovCA & DHCS | The purpose of this CR is to continue the User Interface upgrades on the CalHEERS consumer portal. The focus of the changes is creating a simplified and user friendly experience for renewals. |  | CR is planned for 2018 implementation.
2018 Q2/Q3 | 92204 | User Interface Updates for Managed Verification | CovCA & DHCS | The purpose of this CR is to continue the User Interface upgrades on the CalHEERS consumer portal. The focus of the changes is on the eligibility verification document upload functionality. |  | CR is planned for 2018 implementation.
2018 Q3/ 2019 Q1 | 106890 | Income Data Quality Enhancements | DHCS | This CR enhances the following: 1) adding messaging and instructions for applicants and beneficiaries who are married, filing jointly, and victims of domestic violence. 2) addresses a system gap to ensure MAGI based income of people who are claimed as a dependent by someone other than the parent of the individual is counted during the eligibility determination. 3) addressing small defects identified post deployment of CR 70497. |  | CR is planned for 2018 Q3 / 2019 Q1 implementation.
2018 Q3/ 2019 Q1 | 92298 | SSA Title II Income and Disability Indicator Verification | DHCS | This CR has two separate, primary purposes: 1) to implement electronic verification of Title II Income through the Federal Data Services hub. 2) to implement use of the SSA disability indicator to assign disabled individuals with incomes at or below 128% FPL to new aid codes L6 and L7 instead of M1 and M2. This reduces manual verifications and aligns functionality with federal funding requirements for the New Adult Group regarding populations that were Medicaid eligibility before the implementation of the ACA. |  | CR is planned for 2018 Q3 / 2019 Q1 implementation.
2017 Q3 2018 2019 | 82920 | BREfS Phase D - Separating Verification Service | DHCS & CovCA | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS. CalHEERS uses VIED to coordinate the verifications responses into the BRE and return an eligibility determination via the Determination of Eligibility Response (DER) operation. |  | CR is delayed and planned for 2019 implementation.

## Status Def
Status | Definition
Accenture Access Impact | Once CCB approves the CR to move from "Proposed" to "Accenture Assess Impact", Accenture will analyze based on business requirements and identify initial Rough Order of Magnatitude (ROM) cost. In parallel track, the State also conducts its analysis (see State Assess Impact). Once CCB reviews and approves the requirements and cost estimation, the CR status becomes "Approved for Design".
Approved for Design | Once CCB approves for Design, the CR status becomes "Approved for Design". This authorizes Joint Application Design (JAD) sessions to begin where requirements are reviewed and designs of the system functionalities are documented. The output from the JADs is the final design document for the CR.
Approved for Implementation | Once the design artifacts are signed off by the sponsor(s), the CalHEERS State staff will verified and updated cost information and present to CCB for final approval. Once CCB approves, the CR status becomes "Approved for Implementation".
CCB Review | The Change Control Board (CCB) consists of three voting members; they are the Project Director of CalHEERS, the Chief Tecnology Officer of Covered CA, ad the Chief Information Officer of Department of Health Care Services). As CRs enter each phase of the Software Development Life Cycle (up to Build), they are presented to the voting members for review and approval. When a CR are presented to the Change Control Board (CCB) for approval, any actions items related to the CR are captured and mitigated prior to CCB determining approval/non-approval.
Closed | All work completed, verified, and invoiced.
Mitigated | This status identifies items that are reported as ‘in the system’; however, there were no requirements or artifacts that reference the solution. As such, until the State receives documentation and the resolution is reviewed and approved, the changes remain in "Mitigation" status.
New | After following internal governance process, the sponsor (DHCS or Covered CA) or CalHEERS initates the Change Request (CR). The CR is created and recorded in the CalHEERS Project's change request tracking system. The CR status becomes "New".
Proposed | After creating and recording the CR, additional details are added to the CR by the CalHEERS business analyst(s), and an email is sent to the CalHEERS' State Change Control Lead. The CR status is changed to "Proposed" where the next step is for the Change Control Board to review and approve.
State Access Impact | Once CCB approves the CR to move from "Proposed" to "State Assess Impact", the State will analyze impact and determine readability. In parallel track, Accenture also conducts their analysis (see Accenture Assess Impact). Once CCB reviews and approves the requirements and cost estimation from Accenture, the CR status becomes "Approved for Design".

## Acronyms
Acronym | Definition
ACA | Affordable Care Act
ACWDL | All County Welfare Directors' Letter
AE | Accelerated Enrollment
AIM | Access for Infants and Mothers (now know as Medi-Cal Access Program)
APTC | Advanced Premium Tax Credit
AR | Authorized Representative
ASHS | Applicable State Health Subsidy
BDA | Beginning Date of Aid
BI | Business Intelligence
BPEL | Business Process Execution Language
BRE | Business Rules Engine
BSD | Business Service Definition
CalHEERS | California Healthcare Eligibility, Enrollment, and Retention System
CalHSMI | CalHEERS / SAWS / MEDS Interface
CalWIN | One of the three SAWS, provides service to 18 counties
CalWORKS | California Work Opportunities and Responsibility for Kids
CCHIP | California Children's Health Insurance Programs
CDSS | California Department of Social Services
CE | Continuous Eligibility
CEC | Continuous Eligibility for Children
CEE | Certified Enrollment Entity
CEW | Certified Eligibiilty Worker
CFR | Code of Federal Regulations
CIA | Certified Insurance Agent
CIN | Client Index Number
C-IV | One of the three SAWS, provides service to 39 counties
CMS | Centers for Medicare & Medicaid Services
CPP | Consumer Protection Programs
CSR | Cost Sharing Reduction
CWDA | (CA) County Welfare Directors Association
DE | Deemed Eligibility
DER | Determination Eligibility Response
DHCS | Department of Health Care Services
DMV | Department of Motor Vehicles
DSH | (Federal) Data Services Hub
ECM | Enterprise Content Management
EDR | Eligibility Determination Request
eHIT | Electronic Health Information Transfer
eICT | Electronic Inter-County Transfer Interface
ESB | Enterprise Service Bus
EW | Eligibility Worker
FFC | Former Foster Care
FFM | Federally Facilitated Marketplace
FPL | Federal Proverty Level
GI | General Inquiry
HCO | Health Care Options
HTTP | HyperText Transfer Protocol
HTTPs | HyperText Transfer Protocol Secure
HX | Health Exchange and Medi-Cal Interface (HEMI) Transaction
IAP | Insurance Affordability Program
ICD | Interface Control Document
ICT | Inter County Transfer
IDD | Interface Design Document
IFSV | Income and Family Size Verification
INS | Immigration and Naturalization Service
IRS | Internal Revenue Service
JAD | Joint Application Design
LEADER | One of the three SAWS, provides service to Los Angeles county
LP | Lawful Presence
LRS | Leader Replacement System
M/C | Medi-Cal
MAGI | Modified Adjusted Gross Income
MEC | Minimum Essential Coverage
MEDS | Medi-Cal Eligibility Data System
MOE | Maintenance Of Effort
NA Back 9 | A universal back page to be used on all NOAs for Medi-Cal, CalWORKS, and/or CalFresh.
NOA | Notice of Action
NOD | Notice of Deficiency
NQI | Newly Qualified Immigrants
OBIEE | Oracle Business Intelligence Enterprise Edition
OPA | Oracle Policy Administration
OTech | Office of Technology Services (under California Department of Technology)
PA | Public Assistance
PAI | Projected Annual Income
PBE | Plan-Based Enroller
PII | Personally Identifiable Information
PMPM | Per Member Per Month
PRUCOL | Permanently Residing Under Color of Law
QHP | Qualified Health Plan
QNC | Qualified Non-Citizen
RIDP | Remote Identify Proofing
RRV | Renewal and Redetermination Verification
SAWS | Statewide Automated Welfare System
SBM | State-Based Marketplace
SCR | Service Center Representative
SFTP | Secure File Transfer Protocol
SLA | Service Level Agreement
SOAP | Simple Object Access Protocol
SOC | Share of Cost
SSA | Single Statewide Application
SSI/SSP | Supplemental Security Income/State Supplementary Payment
SSL | Secure Sockets Layer
SSN | Social Security Number
TBD | To Be Determined
TMC | Transition Medi-Cal
UAT | User Acceptance Testing
UI | User Interface
VLP | Very Lawful Presence
XML | Extensible Markup Language