## IAP 24 month Roadmap CR Listing
RE-LEASE | CR NUMBER | TITLE | REQUESTOR | BRIEF DESCRIPTION | Advocate Comments | STATUS UPDATES for 8/24/2017 AB 1296 MEETING
R16.9 R17.2 | 52314 | Duplicate Applications | DHCS | This CR allows counties and SCRs to close out duplicate applications in CalHEERS and keep them from being modified or accessed again. It originally also allowed counties to delink a SAWS case from a CalHEERS case. The linking/delinking functionality was removed for later implementation. |  | This CR is scheduled for implementation in February 2017.
R17.9 - Quarter 3 - (Planned Deployment Date 9/25/2017)
R17.6 & R17.7 R17.9 | 70497 | Modify the online single streamline application (SSApp), except for: *Eligibility Results *Enrollment | DHCS & CovCA | The purpose of this CR is to modify the online single streamline application (SSApp) to meet regulatory and statutory requirements, be consistent with the paper SSApp, and ensure accurate eligibility determinations. The change request includes multiple changes needed to the online SSApp, including changes based on the Centers for Medicare and Medicaid Services (CMS) requirement, changes based on new legislation, updated messaging for improved consumer experience, and changes initially requested with CR 6933 that were deprioritized. Update - implementation of the following in R17.9 includes: • Phase 2.1: App. Start • Phase 2.2: Household / Primary Contact, Tax • Phase 2.3: Health Eligibility • Phase 2.4: Citizenship / Final Review / Signature • Phase 2.5: Spanish Translations • Phase 2.8: Home Special note - the implementation date for the following is to-be-determined: • Phase 2.6: Eligibility Results • Phase 2.7: Enrollment |  | CR is scheduled for implementation in R17.9.
R17.7 R17.9 | 76084 | Dynamic App | DHCS & CovCA | The purpose of this CR is to work in conjunction with CR 70497 (Modify the online single streamline application (SSApp)) and Chaotic Moon/Fjord to display to the consumer the minimum set of applicable questions necessary to determine eligibility. Currently, all consumers are asked the same set of questions and have to navigate through the full application. With the implementation of this CR, checkpoints will be performed throughout the application process to determine what questions to display (i.e. applicants vs. non-applicants). |  | CR is scheduled for implementation in R17.9.
2017 Q1 2017 Q3 R17.9 | 69974 | Eligibility for IAP Based on Immigration Status - Phase 2 | DHCS | This CR will add additional refinements to the CalHEERS system related to immigrant eligibility. This CR will make immigration document information fields optional and will refine what individuals to request the grant date and when to call the federal hub for immigration status verification. CR 69974 will update the immigration status drop down menus to include a detailed list of lawfully present immigration statuses add will add functionality related to the eligibility of lawfully present pregnant women and children. This CR will also add the functionality necessary to identify immigrants who are eligible for the Affordability and Benefit program which is scheduled for 2018 implementation. |  | CR is scheduled for implementation in R17.9.
R17.9 | 83395 | MCAP/CCHIP Transition to Medi-Cal | DHCS | The purpose of this CR is to add functionality in CalHEERS allowing MCAP subscribers to retain their current IAP, and ensuring the necessary transactions are being sent to MEDS to avoid gaps in coverage when subscribers transition to Medi-Cal from MCAP or CCHIP. |  | CR is scheduled for implementation in R17.9.
R17.9 | 91521 | County of Responsibility (COR) Release Update- Part C | DHCS | Following implementation of eICT/County of Responsibility CR 52600 and subsequent CR 87324 to correct a design gap in County of Responsibility this CR provides further enhancement to CalHEERS’ referral processing and County of Responsibility Release Enablement batch sweep functionality to complete full integration of automated case management features in CalHEERS for the release of County of Responsibility. This Change Request will further enhance the CalHEERS’ referral processing and COR Release Enablement batch sweep functionality to complete full integration of automated case management features in CalHEERS for the release of County of Responsibility (COR). Intended Outcome: 1. CalHEERS will enable the reassignment of COR (County of Responsibility) for the Medi-Cal program. 2. The CalHEERS SAWS Interface will not release the COR (County of Responsibility) prematurely for cases that did not receive a MAGI Medi-Cal aid code. 3. The CalHEERS SAWS Interface COR Enablement sweep shall no longer consider a 90 day cure period as part of the evaluation criteria. 4. The CalHEERS SAWS Interface COR Enablement sweep shall no longer consider the referral ID as part of the evaluation criteria to close Disposition. 5. CalHEERS will maintain the County of Responsibility for CalHEERS referrals until a disposition is received for the Medi-Cal program and a program eligibility status is provided. |  | CR is scheduled for implementation in R17.9
2017 Q3 R17.9 | 82343 | CalHEERS-MEDS Reconciliation | DHCS | CalHEERS is the system of record for COVCA/Exchange, MCAP, CCHIP, and State Inmate program eligibility. MEDS must be reconciled periodically with CalHEERS for consumers eligible to these programs (excludes Medi-Cal eligibility records). The process should mirror the SAWS-MEDS reconciliation. CalHEERS must send a full set of all current month eligibility records for consumers active in these programs to MEDS. The data will be sent using a MEDS transaction (e.g., RX20) which has the same format as the existing HX transactions. MEDS will generate the necessary transactions (e.g. RX20, RX40, RX12, etc.) based on the comparison between the MEDS records and the CalHEERS records. As a result, consumer’s eligibility in MEDS will be updated or terminated, and/or client or case information will be updated, accordingly. MEDS will also generate and send to CalHEERS reconciliation alerts and reports. CalHEERS must process and analyze the reconciliation alerts and reports to identify and remediate the issues/errors identified. CalHEERS is the system of record for COVCA/Exchange, MCAP, CCHIP, and State Inmate program eligibility. MEDS must be reconciled periodically with CalHEERS for consumers eligible to these programs (excludes Medi-Cal eligibility records). The process should mirror the SAWS-MEDS reconciliation. CalHEERS must send a full set of all current month eligibility records for consumers active in these programs to MEDS. The data will be sent using a MEDS transaction (e.g., RX20) which has the same format as the existing HX transactions. MEDS will generate the necessary transactions (e.g. RX20, RX40, RX12, etc.) based on the comparison between the MEDS records and the CalHEERS records. As a result, consumer’s eligibility in MEDS will be updated or terminated, and/or client or case information will be updated, accordingly. MEDS will also generate and send to CalHEERS reconciliation alerts and reports. CalHEERS must process and analyze the reconciliation alerts and reports to identify and remediate the issues/errors identified. |  | CR is scheduled for implementation in R17.9.
R17.9 | 7536 | Send Web Service responses and batch transaction Alerts | DHCS | CalHEERS receives Web Service responses and batch alerts from MEDS for Web Service requests sent by CalHEERS, Currently, the batch Alerts and Web Service responses received by CalHEERS are not visible to any Covered CA business areas. Web Service responses and Alerts sent by MEDS indicate data issues that may result in record mismatches between CalHEERS and MEDS. |  | CR is scheduled for implementation in R17.9.
2017 Q3 R17.9 | 90113 | User Interface Updates for Renewals and Report a Change | CovCA & DHCS | The purpose of this CR is to continue the User Interface upgrades on the CalHEERS consumer portal. The focus of the changes included in this CR are the minimal flow for Renewals. |  | CR is scheduled for implementation in R17.9.
R17.9 TBD | 92588 | Implement Agency Module Phase 1 - Part 2 | CovCA | This CR is implementing the hierarchy to support the Agency to Agent relationship in the CalHEERS system to mirror the Covered California policy change for Open Enrollment. With implementation of this CR, Agencies will be able to establish an account in CalHEERS, build their Agent roster, and manage their Agents. |  | CR is scheduled for implementation in 2018.
2017 Q3 R17.9 | 6614 | Auto Discontinue Members/Cases | CovCA | This CR continues the automation begun with CR 27819. It automates the eligibility discontinuance/redetermination for consumers that fail to provide valid documentation to verify an inconsistency for Income. |  | CR is scheduled for implementation in R17.9.
R17.9 | 82949 | Renewals 2018 | CovCA | This CR is to implement additional CalHEERS optimizations for consumers who participate in renewals for 2018. This CR will include multiple enhancements to improve the consumer experience during renewals in areas including, but not limited to: Notices, consumer portal functionality, batches, and portal content. |  | CR is scheduled for implementation in R17.9.
2018 - Quarter 1 - (Planned Deployment Date 2/12/2018)
R17.6 & R17.7 2018 Q1 | 70497 | Modify the online single streamline application (SSApp): *Eligibility Results *Enrollment | DHCS & CovCA | The purpose of this CR is to complete the modifications of this CR for the online single streamline application (SSApp) to meet regulatory and statutory requirements, be consistent with the paper SSApp, and ensure accurate eligibility determinations. The change request includes multiple changes needed to the online SSApp, including changes based on the Centers for Medicare and Medicaid Services (CMS) requirement, changes based on new legislation, updated messaging for improved consumer experience, and changes initially requested with CR 6933 that were deprioritized. |  | CR is planned for implementation in 2018 Q1.
R16.2 2017 Q3 R18.2 | 4469 82977 | State Inmate Program | DHCS | The purpose of this CR is to enhance the CalHEERS system by: 1) Implement the State Inmate Program in CalHEERS. DHCS Staff will enter the application(s) into CalHEERS access channel. DHCS will be responsible for case management. If the “First Level Request” is not viable for Release 3 then please see “Second Level Request” below. (Based on discussion 4/24/2014 change request development will be first request implementation). 2) Add the Inmate Program Aid Codes to the “Manual” drop-down list in the admin environment so DHCS Staff can override the CalHEERS Eligibility Determination Aid Code with the appropriate “Inmate Program Aid Codes” via a manual work-around process. DHCS would be responsible for case management. Add the ability to suppress Notices of Action. | (3/20/15) What NOAs are currently being generated that this CR will help suppress? DHCS> No current CalHEERS notices would be suppressed. This CR implements state inmate eligibility in CalHEERS. NOAs currently generated by state staff will continue to be generated by state staff until this CR is implemented. | CR is planned for R18.2 implementation.
R16.2 2017 Q3 2018 | 9428 82978 | County Inmate Program | DHCS | The CalHEERS System shall have the County Inmate program indicator and said indicator will also be in the eHIT interface and will drive the county inmate aid code determination. 19 - 64 - N7 (Limited Scope) N8 (Restricted Scope) ACWDL 13-18 page 8, generate the MAGI-MC NOA with county inmate snippet language. The CalHEERS System shall treat county inmate application indicator as self attestation for Covered California programs eligibility determination purposes. The CalHEERS System shall generate the CALNOD01 Notice for County Inmate applications. The CalHEERS System will deny eligibility to APTC/CSR for an individual that attests to being incarcerated. |  | CR is delayed and planned for 2018 implementation.
2017 Q3 2018 | 83286 | BREfS Phase C - Standby Eligibility Service and Overrides | DHCS & CovCA | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS to return an eligibility determination via the Determination of Eligibility Response (DER) operation. The CalHEERS eligibility determination results must be accepted by counties, since neither the existing eHIT interface, nor the BRE functionality on the CalHEERS portal currently provide a “preview” of eligibility or the ability to override a CalHEERS eligibility determination. |  | CR is planned for 2018 implementation.
2017 Q3 2018 | 82920 | BREfS Phase D - Separating Verification Service | DHCS & CovCA | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS. CalHEERS uses VIED to coordinate the verifications responses into the BRE and return an eligibility determination via the Determination of Eligibility Response (DER) operation. |  | CR is delayed and planned for 2018 implementation.
2017 Q3 2018 Q1 | 81432 | Update to Income Service Request and Income Caching Rules | DHCS | CalHEERS leverages three income verification services (IRS, FTB, EDD). With R16.9, a new income type (MAGI PAI) was added and incorporated into the income verification caching rules. Currently if at least one of the income types is not cached, all three income verification services are invoked again to re-verify the income data attested by the consumer. The intended outcome is for CalHEERS to enhance the income verification caching rules to reduce the frequency of the income verification services being called. |  | CR is delayed and planned for 2018 Q1 implementation.
2018 Q1 | 90492 | Cases Stuck in Medi-Cal Renewal Mode | DHCS & CovCA | When an action taken by the county results in ineligibility or when a negative action is conducted for one or all individuals in the MAGI Medi-Cal case and there is no MAGI Medi-Cal Renewal ‘Disposition’ sent for the case by SAWS, the case becomes "stuck" in Renewal Mode. As a result, any Covered California eligible consumers on the case are unable to change or select a plan. Known actions that cause this problem include: • Negative Action is sent without a Renewal Disposition • Report A Change is sent without a Renewal Disposition • Case going through the Short Term Negative Action Process |  | CR is planned for implementation in Q1 of 2018.
2018 Q1 | 92697 | Update Version of FDSH RIDP | CalHEERS | The Federal Data Services Hub (FDSH) Remote Identify Proofing (RIDP) Service v1 (Service ID: H1 and H66) will be retired effective February 25, 2018. CalHEERS must migrate to RIDP v2 prior to this date. Also, consumers currently cannot upload identity documents into CalHEERS, as specified in BR430 and MEDIL 15-10. The purpose of this CR will ensure CalHEERS comply with the federal updates and move to H1.1 FDSH RIDP v2. The CR will also include align new response codes and add/update current portal messaging. RIDP v2 (H1.1) provides enhancements to help consumers pass through RIDP and reduce the instances when consumers need to call the Fraud Archiving Reporting System (FARS). If Experian is down, the Requester (CalHEERS) must retry sending the request. CalHEERS will implement a mechanism to determine if Experian is down, and then notify consumers that CalHEERS is unavailable. |  | CR is planned for implementation in Q1 of 2018.
2018 | 90113 | User Interface Updates for Renewals and Report a Change | CovCA & DHCS | The purpose of this CR is to continue the User Interface upgrades on the CalHEERS consumer portal. The focus of the changes included in this CR are the remaining flow for Renewals and Report a Change. |  | CR is planned for 2018 implementation.
2018 | 92204 | User Interface Updates for Managed Verification | CovCA & DHCS | The purpose of this CR is to continue the User Interface upgrades on the CalHEERS consumer portal. The focus of the changes included in this CR are the remaining flow for Renewals. |  | CR is planned for 2018 implementation.
2018 Q1 | 94030 | Immigration Document Data Collection | CovCA | This CR reduces conditional eligibility for immigration status for Covered California consumers by requiring entry of sufficient document information required to call VLP. |  | CR is planned for 2018 Q1 implementation.
2018 Q1 | 95184 | SEP Dropdown and Workflow | CovCA | The intended outcome is: 1. Update and add to the available SEP reasons, 2. Update and add to the business rules for each existing and new SEP reason and coverage date category, 3. Dynamically display the SEP reasons in the dropdown list based on the user role and application mode, and 4. Update eHIT/SAWS accordingly |  | CR is planned for 2018 Q1 implementation.
2018 - Quarter 2 & Beyond (Planned Deployment Date TBD)
R15.9 R16.2 R16.4 2018 | 3067 | 4-Month Continuing MAGI based Medi-Cal for Parent/Caretaker Relatives | DHCS | • Create a simple and distinct electronic verification service, decoupled from the eligibility business rules, that is accessible both via the CalHEERS portal and to SAWS via eHIT. | (3/20/15) Advocates would like to understand what the workaround is for this. DHCS> Discussed this CR at 4/17/15 AB 1296 meeting. DHCS/MCED stated these consumer protection programs (CPP) had been postponed to 2016 release. | CR is planned for 2018.
R15.9 R16.2 R16.4 2018 | 2967 | Continuous Eligibility for Children (CEC) | DHCS | • Provide the ability to request separate verifications by verification source both via the CalHEERS portal and to SAWS via eHIT. | (3/20/15) Advocates had understood that CEC could continue to function in SAWS and want to understand how this is working today. DHCS> Discussed this CR at 4/17/15 AB 1296 meeting. DHCS/MCED stated these consumer protection programs (CPP) had been postponed to 2016 release. | CR is planned for 2018.
R15.9 R16.2 R16.4 2018 | 2972 | Transition Medi-Cal (TMC) | DHCS | • Provide an electronic verification service that can be leveraged for potential use with Non-MAGI and/or other non-health programs in the future. | (3/20/15) Advocates support postponing this CR as TMC rules exists in SAWS today and other CRs are more critical. DHCS> Discussed this CR at 4/17/15 AB 1296 meeting. DHCS/MCED stated these consumer protection programs (CPP) had been postponed to 2016 release. | CR is planned for 2018.
R15.9 R16.2 R16.4 2018 | 3065 | Continuous Eligibility (CE) for Pregnant Women | DHCS |  | (3/20/15) We understand CE for Pregnant Women is continuing to function in the SAWS. DHCS> Discussed this CR at 4/17/15 AB 1296 meeting. DHCS/MCED stated these consumer protection programs (CPP) had been postponed to 2016 release. | CR is planned for 2018.
R15.9 R16.2 R16.7+ TBD | 8703 | Medi-Cal Plan Selection Changes | DHCS | This CR is based on advocate feedback subsequent to design approval. Medi-Cal plan selection will enable consumers to use either the CalHEERS portal or existing county / HCO processes to make Medi-Cal Plan selection. Those plan selections will then be available on the CalHEERS portal. Changes and plan updates reported at either source will also appear through the CalHEERS portal. | (3/20/15) Advocates support moving eligibility determinations before online plan selection. We gave design input in Spring 2014 and request the opportunity to review changes before design is finalized. | The implementation timeframe for this initiative is TBD.
R16.2 TBD | 2968 | DMV State Residency Verification | DHCS |  | (3/20/15) Advocates support a change in policy to continue the current policy of suspending residency verifications and not building this interface. We oppose any additional CalHEERS programming resources used to enable this functionality while there are more pressing eligibility and enrollment issues not functioning. If implemented, advocates would like to a) know what other databases can be checked if consumer's state residency can't be verified via the DMV and b) review text of eligibility results screen or NOA snippet informing individuals their state residency could not be electronically verified. | The implementation timeframe for this initiative is TBD.
2018 Q2 | 95185 | SEP Pre-Enrollment Verification | CovCA | Add verification to verify SEP Reasons before consumers are effectuated in a QHP/QDP |  | CR is planned for 2018 Q2 implementation.
2018 | 61104 | Plan Dependency Definition | CovCA | The CalHEERS System shall allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application. The CalHEERS system shall only allow the following individuals to enroll in the same Covered CA enrollment group/plan: Married spouses; Registered domestic partners; Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners; Disabled adult children of any age (including 26 or above); Siblings under the age of 19. |  | CR is planned for 2018 implementation.
TBD | TBD | Changes to BRE for tax questions | CovCA | Consumers are found ineligible for APTC/CSR due to the tax filing question for the Primary Tax Filer (Are you planning to file taxes?) being unanswered/skipped in SAWS. This question is optional in SAWS, and when SAWS sends the answer to this question as “NULL” via eHIT, it is translated to “No” in CalHEERS. |  | The implementation timeframe for this initiative is TBD.

## Status Def
Status | Definition
Accenture Access Impact | Once CCB approves the CR to move from "Proposed" to "Accenture Assess Impact", Accenture will analyze based on business requirements and identify initial Rough Order of Magnatitude (ROM) cost. In parallel track, the State also conducts its analysis (see State Assess Impact). Once CCB reviews and approves the requirements and cost estimation, the CR status becomes "Approved for Design".
Approved for Design | Once CCB approves for Design, the CR status becomes "Approved for Design". This authorizes Joint Application Design (JAD) sessions to begin where requirements are reviewed and designs of the system functionalities are documented. The output from the JADs is the final design document for the CR.
Approved for Implementation | Once the design artifacts are signed off by the sponsor(s), the CalHEERS State staff will verified and updated cost information and present to CCB for final approval. Once CCB approves, the CR status becomes "Approved for Implementation".
CCB Review | The Change Control Board (CCB) consists of three voting members; they are the Project Director of CalHEERS, the Chief Tecnology Officer of Covered CA, ad the Chief Information Officer of Department of Health Care Services). As CRs enter each phase of the Software Development Life Cycle (up to Build), they are presented to the voting members for review and approval. When a CR are presented to the Change Control Board (CCB) for approval, any actions items related to the CR are captured and mitigated prior to CCB determining approval/non-approval.
Closed | All work completed, verified, and invoiced.
Mitigated | This status identifies items that are reported as ‘in the system’; however, there were no requirements or artifacts that reference the solution. As such, until the State receives documentation and the resolution is reviewed and approved, the changes remain in "Mitigation" status.
New | After following internal governance process, the sponsor (DHCS or Covered CA) or CalHEERS initates the Change Request (CR). The CR is created and recorded in the CalHEERS Project's change request tracking system. The CR status becomes "New".
Proposed | After creating and recording the CR, additional details are added to the CR by the CalHEERS business analyst(s), and an email is sent to the CalHEERS' State Change Control Lead. The CR status is changed to "Proposed" where the next step is for the Change Control Board to review and approve.
State Access Impact | Once CCB approves the CR to move from "Proposed" to "State Assess Impact", the State will analyze impact and determine readability. In parallel track, Accenture also conducts their analysis (see Accenture Assess Impact). Once CCB reviews and approves the requirements and cost estimation from Accenture, the CR status becomes "Approved for Design".

## Acronyms
Acronym | Definition
ACA | Affordable Care Act
ACWDL | All County Welfare Directors' Letter
AE | Accelerated Enrollment
AIM | Access for Infants and Mothers (now know as Medi-Cal Access Program)
APTC | Advanced Premium Tax Credit
AR | Authorized Representative
ASHS | Applicable State Health Subsidy
BDA | Beginning Date of Aid
BI | Business Intelligence
BPEL | Business Process Execution Language
BRE | Business Rules Engine
BSD | Business Service Definition
CalHEERS | California Healthcare Eligibility, Enrollment, and Retention System
CalHSMI | CalHEERS / SAWS / MEDS Interface
CalWIN | One of the three SAWS, provides service to 18 counties
CalWORKS | California Work Opportunities and Responsibility for Kids
CCHIP | California Children's Health Insurance Programs
CDSS | California Department of Social Services
CE | Continuous Eligibility
CEC | Continuous Eligibility for Children
CEE | Certified Enrollment Entity
CEW | Certified Eligibiilty Worker
CFR | Code of Federal Regulations
CIA | Certified Insurance Agent
CIN | Client Index Number
C-IV | One of the three SAWS, provides service to 39 counties
CMS | Centers for Medicare & Medicaid Services
CPP | Consumer Protection Programs
CSR | Cost Sharing Reduction
CWDA | (CA) County Welfare Directors Association
DE | Deemed Eligibility
DER | Determination Eligibility Response
DHCS | Department of Health Care Services
DMV | Department of Motor Vehicles
DSH | (Federal) Data Services Hub
ECM | Enterprise Content Management
EDR | Eligibility Determination Request
eHIT | Electronic Health Information Transfer
eICT | Electronic Inter-County Transfer Interface
ESB | Enterprise Service Bus
EW | Eligibility Worker
FFC | Former Foster Care
FFM | Federally Facilitated Marketplace
FPL | Federal Proverty Level
GI | General Inquiry
HCO | Health Care Options
HTTP | HyperText Transfer Protocol
HTTPs | HyperText Transfer Protocol Secure
HX | Health Exchange and Medi-Cal Interface (HEMI) Transaction
IAP | Insurance Affordability Program
ICD | Interface Control Document
ICT | Inter County Transfer
IDD | Interface Design Document
IFSV | Income and Family Size Verification
INS | Immigration and Naturalization Service
IRS | Internal Revenue Service
JAD | Joint Application Design
LEADER | One of the three SAWS, provides service to Los Angeles county
LP | Lawful Presence
LRS | Leader Replacement System
M/C | Medi-Cal
MAGI | Modified Adjusted Gross Income
MEC | Minimum Essential Coverage
MEDS | Medi-Cal Eligibility Data System
MOE | Maintenance Of Effort
NA Back 9 | A universal back page to be used on all NOAs for Medi-Cal, CalWORKS, and/or CalFresh.
NOA | Notice of Action
NOD | Notice of Deficiency | Notice of Decision?
NQI | Newly Qualified Immigrants
OBIEE | Oracle Business Intelligence Enterprise Edition
OPA | Oracle Policy Administration
OTech | Office of Technology Services (under California Department of Technology)
PA | Public Assistance
PAI | Projected Annual Income
PBE | Plan-Based Enroller
PII | Personally Identifiable Information
PMPM | Per Member Per Month
PRUCOL | Permanently Residing Under Color of Law
QHP | Qualified Health Plan
QNC | Qualified Non-Citizen
RIDP | Remote Identify Proofing
RRV | Renewal and Redetermination Verification
SAWS | Statewide Automated Welfare System
SBM | State-Based Marketplace
SCR | Service Center Representative
SFTP | Secure File Transfer Protocol
SLA | Service Level Agreement
SOAP | Simple Object Access Protocol
SOC | Share of Cost
SSA | Single Statewide Application
SSI/SSP | Supplemental Security Income/State Supplementary Payment
SSL | Secure Sockets Layer
SSN | Social Security Number
TBD | To Be Determined
TMC | Transition Medi-Cal
UAT | User Acceptance Testing
UI | User Interface
VLP | Very Lawful Presence
XML | Extensible Markup Language