## AB 1296 Meetings - Action Items
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
Date Logged | Policy Topic | Requestor | Action Item | Responding Organization | Owner | Deadline | Status | Notes
No Action Items at this time.

## 2021 Initiatives Action Items
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
Date Logged | Initiative # | Initiative Name | Requestor | Action Item | State Organization | Owner | Status | Notes
2020-02-11 | 24 | Former Foster Youth: Hide Verifications for Former Foster Youth (UCD) | Stakeholder | Cori R. and Alicia E. to provide screen shots of Eligibility Page; Advocates to include their questions. | DHCS | Cori/Alicia, Lucy | Open
2020-02-11 | 55 | Explore Horizontal Integration Improvements | Stakeholder | DHCS will reach out to Agency for updated status. | DHCS | Yingjia Huang | Open | 5/14/20: On Hold for now
2020-02-11 | 57 | Non-immigrant visa holders + Covered CA enrollment | Stakeholder | Advocates to provide case examples and additional information. | DHCS | Alicia/Cori | Open | 5/14/20: On Hold for now

## AB 1296 Meetings - Closed Items
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
Date Logged | Policy Topic | Requestor | Action Item | Responding Organization | Owner | Deadline | Status | Notes
2016-09-07 | Renewal Language | Stakeholder | Covered CA to provide final notices with renewal languages based on CR# 59948. | Covered CA | Valerie York |  | Completed & Closed | Action item closed at the 1/13/17 meeting.
2016-09-07 | SAWS | Stakeholder | CWDA to check with SAWS to determine if the SAWS have the functionality to provide text messages and/or automatic phone calls. | CWDA | Assmaa Elayyat |  | Completed & Closed | 5/31/17 - CWDA/Cathy provided the response at the meeting.
2016-09-07 | Report a Change | Stakeholder | In a meeting with CWDA, the advocates understood from counties that for report a change of income, whole family will be re-evaluated. How will this impact those on APTC? | Covered CA | Thien Lam |  | Completed & Closed | 9/7/16 - Thien will circle back with Cori R. to clarify and respond. 1/13/17 - CC/Thien provided responses to question at the meeting.
2017-01-13 | n/a | Stakeholder | In addition to .pdf versions for the agenda and the CR Update document, post the Microsoft version. It will enable stakeholders to make necessary notes. | DHCS | Fei Collier/ Doina Culiuc |  | Completed & Closed | 8/24/17 - Update -- Due DHCS website publication standards, the Microsoft version of the documents will be posted on the AB 1296 website wherever possible instead of the including the .pdf version. 5/31/17 - Microsoft version and the .pdf version, for the Agenda and the CR Update document, have been posted on the AB 1296 website for the 5/31/17 meeting.
2018-01-12 | n/a | CH Project | All stakeholders to provide final comments to the 2019 Initiatives list by COB 1/19/18. | Stakeholders | CalHEERS / DHCS / Covered CA | 2018-01-19 | Closed
2018-01-12 | State Inmate | Stakeholder | Stakeholder requested further discussion and understand of the State Inmate CR (#82978). DHCS will add to the next CFSW or schedule separate meeting. | DHCS | DHCS | TBD | Completed & Closed | 09/11/18- currently this action item is being tracked on the CFSW action item log.
2018-01-12 | Horizontal Integration | Stakeholder | Stakeholder requested DHCS could consider horizontal integration as a future initiative | DHCS | DHCS | TBD | Completed & Closed | 4/26/19 - DHCS and CC added a line item to the 2020 Initiatives List "Explore Horizontal Integrratoin Improvements". DHCS, Covered CA, and CalHEERS Project will explore the capacity and feasibility during 2020 of adding this initiatives.
2018-08-30 | Release Notes Glossary | Stakeholder | Unplanned Pregnant Woman (UPW) - R18.6; R18.9 glossaries contain this acronym that doesn’t have an explanation. CH to take this item back, review, and provide the definition of the UPW if applicable/used in the document. | CalHEERS | Chris (CalHEERS) | TBD | Completed & Closed | 5/3/19 - CalHEERS provided clarity/correction during the meeting that UPW is Unmarried Pregnant Woman and not Unplanned Pregnant Woman.
2018-08-30 | IRS website link | Stakeholder | Alicia Kauk informed the group regarding a broken link on the IRS website. The expectation is that consumers are informed and guidance to the county is issued. Alicia will share the link webpage via the AB1296 inbox (email received on 09/10). CalHEERS and DHCS & CC will follow up with Accenture (who is the federal liaison) and work on more facts findings with the internal team | CalHEERS and DHCS & CC | CalHEERS/ DHCS/ CC | TBD | Completed & Closed | 1/14/19 - the IRS 2018 link has been updated with the new tax year. This link is an ever-green link that does not need to be changed. 2/6/19 - DHCS, Covered CA, and advocates discussed the best ways to support applicants and beneficiaries. The agreement reached was for DHCS to publish an ACWDL that includes a table from an IRS publication. DHCS expects to publish the ACWDL within the next few weeks. Eligibility workers are informed to share a IRS link and publication with consumers to assist with determining whether or not they are required to file taxes.
2018-08-30 | DIVS | Stakeholder | DIVS - how many documents are received by fax | Covered CA | CC | TBD | Completed & Closed | 5/3/19 - CC/Trisha provide count of 5,140 faxes are received per month. 9/11/18 - CC receives from 100-150 faxes per day total. CC will be able to determine what portion of these are DIVS documents after the implementation of DIVS mail/fax in the October R18.9 release.
2018-12-12 | List of Notices | Stakeholder | Stakeholders requested a list of CalHEERS generated consumer notices. | Covered CA | CC | 2019-01-11 | Completed & Closed | 3/28/19 - The list of consumer friendly document names for CalHEERS notices were sent on 3/28 to the key advocate team members.
2019-01-11 | R18.12 | Stakeholder | Cori R. requested a screenshot of the "My Account/Application" page to see the updates that have been made. | CalHEERS | Chris (CalHEERS) | TBD | Completed & Closed | Screen shots provided to Cori & Alicia K. on 2/6/19.
2019-01-11 | General | DHCS, CC, & CalHEERS | As part of AB 1296 Agenda item VI, DHCS/CC/CalHEERS requested feedback from Stakeholders regarding the CalHEERS Functionality & Progress since the system went live. Representing the key advocate team, Cori R. provided verbal feedback and will follow up and provide in writing. | Stakeholders | Stakeholders (Cori R.) | By 2nd 2019 AB 1296 Meeting | Completed & Closed | 5/1/19 - DHCS, CC, and CalHEERS received the letter from key advocate groups providing feedback on CalHEERS' functionality and progress.
2019-01-11 | 2020 Initiatives | DHCS, CC, & CalHEERS | DHCS/CC/CalHEERS will send responses to the stakeholder feedback (received on 1/2/19) on the 2020 CalHEERS Initiatives | DHCS, CC, & CalHEERS | DHCS, CC, & CalHEERS | 2019-01-22 | Completed & Closed | 1/23/19 - Adjusted deadline date for the responses to 1/24/19.
2019-01-11 | 2020 Initiatives | DHCS, CC, & CalHEERS | All stakeholders to review & provide 2nd round of feedback to DHCS/CC/CalHEERS' responses to the initial final comments to the 2019 Initiatives list by COB 1/19/18. | Stakeholders | Stakeholders (Cori R.) | 2019-02-02 | Completed & Closed | 1/23/19 - Adjusted deadline date for stakeholder feedback to 2/5/19.
2019-01-11 | 2020 Initiatives | DHCS, CC, & CalHEERS | DHCS/CC/CalHEERS will send 2nd round of responses to the stakeholder feedback and finalize the 2020 CalHEERS Initiatives. | DHCS, CC, & CalHEERS | DHCS, CC, & CalHEERS | 2019-03-01 | Completed & Closed | Finalized 2020 Initiatives List on 3/19/2019
2019-01-11 | Income & Deductions | Stakeholder | Alicia K. requested an updated Income & Deductions Chart, which was released with MEDIL 19-03. | DHCS | DHCS | 2019-05-03 | Completed & Closed | 4/29/19 - MEDIL 19-03 released January 14, 2019. Updated Income & Deductions Chart has been sent to requestor.
2019-01-11 | Income & Deductions | Stakeholder | Alicia K. requested updated list of consumer-friendly document names for CalHEERS notices. | Covered CA | Covered CA | 2019-05-03 | Completed & Closed | 3/28/19 - The list of consumer friendly document names for CalHEERS notices were sent on 3/28 to the key advocate team members. Note: This is similar request and action item on 12/12/18.
2019-01-11 | Income & Deductions | Stakeholder | For future IV&V Summaries, DHCS, Covered CA, and CalHEERS will discuss the strategy on how to build upon the IV&V reporting calendar and complete a roll up view for future IV&V updates. | CalHEERS / DHCS / Covered CA | CalHEERS / DHCS / Covered CA | TBD | Closed | 01/15/20 - CalHEERS, DHCS, and Covered CA have closed this action item. IV&V summary reports are internal reports and typically not shared externally. 7/24/19 - CalHEERS, DHCS, and Covered CA will continue to explore the opportunities in future meetings to share the IV&V reports 8/24/17 - CalHEERS, DHCS, and Covered CA will continue to explore the opportunities in future meetings to share the IV&V reports. 5/31/17 - CalHEERS, DHCS, and Covered CA will discuss the strategy in a future date.
2019-01-11 | Income & Deductions | Stakeholder | Cori R. asked whether the materials for applications assistors have been updated to reflect the new tax filing thresholds. | Covered CA | CC (Valerie York) | TBD | Complete | 5/3/19 - CC continue to work the material and will be providing once materials are finalize. 7/19/19 - Talking Points provided through HCA group in June 2019
2019-01-11 | Income & Deductions | Stakeholder | Alicia K. requested screenshots for the new dynamically displayed language for a pop-up on the "Are you planning to file taxes" page. | Covered CA | CC (Valerie York) | 2019-07-30 | Complete | 12/26/19 - Complete per 9/16/19 email to advocates from Covered CA. 5/3/19 - CC and DHCS have added a UCD user story to the backlog to dynamically display language on the page when a user marks that they are not planning to file taxes. Once the user story is being designed, CC will provide. 7/19/19 - No update at this time
2019-01-11 | Income & Deductions | Stakeholder | Cori R. requested follow up discussion/responses to the advocate feedback on the Bounce Back ACWDL (MCED-5147) | DHCS | DHCS/ Theresa H. | 2019-07-30 | Complete | 5/3/19 - Theresa to send email to Cori and set up meeting to walkthrough. 7/19/19- . Reponses were provided to Cori on 5/6/19 and there were no additional questions/follow up.
2019-01-11 | Notices | Stakeholder | Alicia K. requested information on the changes that were made to R19.9 notices. CC/Emma indicated changes were very minor. | Covered CA | CC (Emma Z.) | 2019-07-30 | Complete | 5/3/19 - CC/Emma to send snippets to Alicia. 7/19/19- Information was provided to advocates on 5/3/19.
2019-01-11 | Get Insured | Stakeholder | Alicia K. requested information as to whether or not the GI PCP Selection Module will differentiate between PCPs and gynecological PCPs | Covered CA | Covered CA | 2019-05-03 | Closed | 5.21.20:CCA’s PCP selection will only allow for one provider to be selected, which will be a Primary Care type. Gynecologist will not be available for selection as they are not Primary Care providers. Consumers will continue to select their specialist providers through their carrier once enrolled. 12/13/19: At the AB 1296 meeting in December, Covered CA shared that when this initiative goes into design, they will reach out and provide interface information. 7/24/19 – This requires an interface with PCP provider data. The details will be finalized during the design session.
2020-05-22 | Pandemic Unemployment Compensation | Stakeholder | Share how many individuals will be redetermined by DHCS that potentially entered in Pandemic Unemployment Compensation income into CalHEERS. | DHCS | DHCS | 2020-06-30 | Closed | 5/29/20: DHCS (PDB) is obtainng this information and will be sharing with Alicia and Coriby early June. 6/18/20 Update: Numbers were reported in COVID meeting with advocates and to Alycia and Cori directly on a call

## 2021 Initiatives Closed Items
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
Date Logged | Initiative # | Initiative Name | Requestor | Action Item | State Organization | Owner | Status | Notes
2020-02-11 | 2 | State Subsidy California 3895s | Stakeholder | Covered CA to send form and messaging to Advocates. | Covered CA | Karen Avakian | Closed | 3.12.20: Covered California shared the draft version of the cover letter with advocates on 3/11/20. 2.24.20: Covered CA will begin sharing the proposed language as soon as we can. FTB is planning to finalize and share the form sometime around the end of March or early April.
2020-02-11 | 3 | Docs and Correspondence | Stakeholder | CalHEERS will develop and present updated view at the May 2020 AB 1296 meeting. | CalHEERS | CH Project | Closed | Presentation at May 2020 AB 1296 Meeting
2020-02-11 | 4 | MAGI Medi-Cal to Covered CA Eligibility Determinations Improvements | Stakeholder | Advocates request the initiative to be written in plain language and identify that this is specific to MAGI Medi-Cal to Covered CA. In addition, Advocates request that #46 be combined to this effort. New Question regarding possible loss of MEC issue. | Covered CA/CalHEERS | William Wall | Closed | 4.16.20 DHCS researched MEC issue and confirmed this is not occuring in production. 3.12.20 Description update provided.
2020-02-11 | 28 | NOD 62 (Federal) and Form 1095s | Stakeholder | Covered CA will begin sharing the proposed edits as soon as we can. | Covered CA | Karen Avakian | Closed | 5/20/20: The draft language was previously provided to advocates and they have responded with their feedback which has been incorporated into the final versions.
[begin strikeout]2/11/2020[end strikeout] | [begin strikeout]Added Topic[end strikeout] | [begin strikeout]Added Action Item: Prospective Health Plan Enrollment Date[end strikeout] | [begin strikeout]Stakeholder[end strikeout] | [begin strikeout]Lucy Q. and Lynn K. to provide screen shots of enrollment page. Page does not allow consumer to enter prospective date for health plan enrollment.[end strikeout] | [begin strikeout]Covered CA[end strikeout] | [begin strikeout]Lucy Q. & Lynn K.[end strikeout] | Closed | Moved this to Advocate Request to research for possible change request.
[begin strikeout]2/11/2020[end strikeout] | [begin strikeout]Added Topic[end strikeout] | [begin strikeout]Added: Suppression Health Plan for FPL 138%[end strikeout] | [begin strikeout]Stakeholder[end strikeout] | [begin strikeout]Cori R. and Alicia E. would like to discuss the suppression of health plan for 138 % FPL.[end strikeout] | [begin strikeout]Covered CA[end strikeout] | [begin strikeout]Karen Avakian[end strikeout] | Closed | Covered CA addressed this in a separate forum.
2020-02-11 | 30 | SB 1341 AB 617 - Notice Improvements | Stakeholder | Covered CA to set up meeting with DHCS and advocates to discuss the scope of this initiative. | Covered CA | Karen Avakian | Closed | Covered CA met with Advocates regarding this request.