## 2022-2023 Roadmap
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
CalHEERS
2022 - 2023 CRs / Initiatives
CR # | TITLE | BRIEF DESCRIPTION | RELEASE
171267 | Notices Updates for R22.12 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 22.12
95184 | SEP Dropdowns and Workflow | The intended outcome of this CR is to update and add to the available SEP reasons, modify the business rules for the existing and new SEP reasons and Eligibility Effective Date Category, and dynamically display the SEP reasons in the dropdown list. The changes include adding a new Eligibility Effective Date Category ‘Loss of Coverage (MEC)’, updating the Eligibility Effective Dating rules for the SEP functionality, adding a new detected SEP reason 'APTC - Detected low FPL' which can be detected at intake or RAC, it will be sent to GI when it is the most advantageous, as well as modifying the portal display accordingly. | 22.2
156600 | Changes to Spanish Version on the CalHEERS Portal | The Spanish Portal of CalHEERS application will be updated to provide consumers with clear understanding of data fields and instructions during the application process and during any subsequent changes to their application. This effort will address all Spanish Translations for the HBX consumer facing screens including field text, ‘help screen’, ‘question icon’ and dropdown values on the Spanish version of the portal. | 22.2
159158 | Older Adult Expansion. Expansion of full scope Medi-Cal for individuals 50 years of age and older regardless of citizenship or immigration status | Older Adult Expansion change will allow eligible adults who are aged 50 years and older to receive full-scope MAGI Medi-Cal benefits irrespective of their citizenship or immigration status. This policy is effective from 05/01/2022 and all existing eligible cases meeting the age and citizenship/immigration criteria will be re-determined for full scope MAGI Medi-Cal benefits via SAWS. | 22.2
164426 | Implement “Verify Current Income” Service for FDSH e-verification of Income | This CR provides the ability to leverage “the work number” service, which is provided by Equifax via the Federal Data Services Hub, to increase the speed and accuracy of verifying a user’s attested income and employment information. The current verification process uses IRS or FTB data which utilizes prior year information, while “Verify Current Income” service operates near real-time data. | 22.2
168267 | Implement additional language preferences per MEDS update | CalHEERS is implementing the capability to support two additional spoken and written language preferences of Punjabi and Hindi in CalHEERS system. Updates include being able to capture these additional language preferences on CalHEERS and SAWS Access Channels, and sending these new language preferences to interface partners such as MEDS, GetInsured and SalesForce. | 22.2
169188 | Address validation and standardization | With this CR, we will accomplish following changes: 1. Address validation service for CalHEERS portal, flexi app and agent/agency account creation updated to SmartyStreets US Street Address API; 2. CalHEERS portal will support 50 characters in Address Line 1 and 2 to be in sync with SAWS address field character limitation; 3. New address validation module and banner texts to improve address validation and suggestion; 4. Validate FIPS county code received in SAWS EDR using SmartyStreets US Street Address API; 5. Trigger BV 128 when the Zip Code provided by SAWS cannot be validated using SmartyStreets API and not listed in ZIP code to FIPS County Code mapping table; 6. Send Zip+4 to MEDS. | 22.2
171264 | Notices Updates for R22.2 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 22.2
171373 | BREfS Initiative #10: CalHEERS Application Life Cycle | The Application Life Cycle initiative will allow MAGI Medi-Cal applications to align with the existing SAWS application lifecycle i.e. reapplication scenarios. This will help align the business processes across systems. | 22.2
171387 | Case Linkage - Phase 1 | The Case Linkage - Phase I CR aims to provide process improvements and resolve existing issues related to case linkage and person linkage between CalHEERS and SAWS cases through updates to eHIT transactions (EDR, Disposition, CancelDER, COR Reassignment Enablement Batch) and a new Search transaction between CalHEERS and SAWS. | 22.2
173134 | Small MCAP design and code enhancements to improve the current design and functionality of CalHEERS | The purpose of this CR is to implement small MCAP enhancements: 1. CalHEERS will send the EERC: PS ‘QHP Pregnancy Hold – Has elected to switch' to SAWS via DER-U when a consumer elects to switch from QHP to MAGI Medi-Cal while in QHP Pregnancy Hold. CalHEERS will send the EERC: MS ‘MCAP Pregnancy Hold ended – Consumer elected to switch to MAGI MC' to SAWS via DER-U when a consumer elects to switch from MCAP to MAGI Medi-Cal while in MCAP Pregnancy Hold. 2. CalHEERS will send HX20-ESAC2 update transaction to MEDS when a consumer transitions from MCAP to CCHIP or vice versa. 3. CalHEERS will display the MCAP phone number on the Account Home page for consumers Pending for MCAP. | 22.2
177906 | Allow Consumers Unlimited Plan Changes During SEP Window | Allowing a consumer to update their plan selection for the entire duration of their special enrollment period (SEP) window following their Qualifying Life Event (QLE) as well as the duration of open enrollment (OEP). There will be no limitation on number of times that a consumer can change their plan within the OEP and SEP windows. If the consumer reports a change (RAC) while the SEP window is still open, the system shall automatically choose the QLE with the more beneficial SEP window (the one that ends later). The consumer will now see the “Change Plan” option on the Account Home Page in 2 areas as well as on the Eligibility Results Summary Page in 2 areas once plan selection has been completed. | 22.2
179136 | Enroller Portal Alerts - Phase II | This CR adds more notifications to the Enroller's Notification excel sheet which was a part of Phase I CR 170125. Also gives the SCR admin a way to retrieve enroller's notification through salesforce and updates the BOB to add column "Consent Valid Through Coverage Year Report" and remove 1. Consent Received Date 2. Consent Duration. | 22.2
179749 | Enable Choose Plan for GI Overrides | When shopping window is opened via GI override functionality, choose plan button should be enabled on Eligibility summary page and Account Home page. | 22.2
182474 | Provide 12 months postpartum coverage to all MAGI Medi-Cal and MCAP aid codes when the individual has reported a pregnancy | Effective 04/01/2022, CalHEERS system will be granting pregnant individuals under MAGI Medi-Cal and MCAP program with an extended postpartum period of 365 days instead of current 60 days. CalHEERS system will be extending the postpartum for pregnant individuals under MAGI Medi-Cal program irrespective of the aid code determined. CalHEERS will be deriving a new one-time staging batch which will extend the postpartum period for all existing MCAP cases. Postpartum period for all existing MAGI Medi-Cal cases will be extended via the SAWS. System functionality includes the following: 1. Include language in the CoveredCA portal to advise the applicant of the length of the postpartum coverage. 2. Configure and send the postpartum period (number of days) and the postpartum end dated to SAWS on the E-Hit transactions when eligibility is determined. 3. Display the postpartum end date on the Budget worksheet when eligibility is determined. 4. Apply the discontinuance rules for individuals in postpartum period only if the following specific Negative Action reasons are received: a. Written Withdrawal b. Deceased c. California Residency d. Receives SSI e. On Aid in Another Case | 22.2
186995 | Update Portal Language and Links | With this CR, we will accomplish following changes: 1. English and Spanish tooltip/hover text language and links updated for "Minimum Value Standards", "Affordability Standards" and "Employer Coverage" in Consumer and Flexible-Application view; 2. The hover text language related to the Affordable Care Act and links updated for all flows including intake, RAC and Renewal; 3. Spanish translation text of error messages for incorrect Authentication Code updated for Consumer Delegation page | 22.2
188855 | BPM Workflow Improvements | BPM Workflow Improvements is a collaborative work with Covered California to deliver enhancements of requirements identified during BPM Phase 3. These changes will be delivered using an incremental delivery approach, which will include demos of the features developed within each sprint. | 22.2
160531 | Medi-Cal Transition Auto-Enrollment per SB260 Part I | Implementation of the following logic to auto enroll consumers who are transitioning from MAGI Medi-Cal/MCAP/CCHIP to APTC into Covered CA plans. The following enhancements will be added to assist the auto enrolled population: -Updated messaging and direction for consumers to link their case to a new CalHEERS account and access their auto enrolled plan details -The ability to Opt In/Opt Out of their auto enrolled plan through CalHEERS Portal or IVR -Downstream processing and communication to GI and carriers based on consumer Opt In/Opt Out confirmation | 22.6
171265 | Notices Updates for R22.6 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 22.6
174936 | Addition of federally recognized tribes in CalHEERS | With this CR, we will accomplish following objectives: 1. Update tribe names in eHIT and the CalHEERS database to match with the federal list of tribes; 2. Add tribes to eHIT and/or the CalHEERS database which are currently in the federal list but not in eHIT and/or the CalHEERS database; 3. End date tribes that are no longer federally recognized, move individuals from the no longer recognized tribes to “Tribe Not Listed”, and add a case note to inform admins of the reason for the change in tribe name to “Tribe Not Listed"; 4. Add VA and IN in the State dropdown for AI/AN tribe. | 22.6
181476 | Case Linkage - Phase II | This CR provides the functionality for a user to reactivate an inactivated individual from the CalHEERS Portal and Flexi App. | 22.6
188570 | Shop & Compare and GI Updates for Loss of Coverage | The purpose of this CR is: a) To align Non-Hyde Abortion Premium logic in Shop and Compare to match actual determination in portal. b) Align GI enrollment date | 22.6
189423 | Add a Carrier Link to Enrollment Dashboard | A new button will be implemented to redirect consumers, with a $0 Net Premium, to carrier websites to select a Primary Care Provider. | 22.6
198728 | Remove any reference to MCAP, CCHIP, and OTLICP premiums | All MCAP, CCHIP and OTLICP notices and portal messaging needs to omit any language in reference to premiums and contributions. This change needs to be configurable in the event that premiums are reinstated in the future. | 22.6
199518 | 20% Reasonable Compatibility Threshold Increase for MAGI Medi-Cal | This initiative would require CalHEERS application to add an additional 20% Reasonable Compatibility threshold to the existing income verifications for MAGI Medi-Cal/MCAP/CCHIP. The 20% reasonable compatibility threshold will be configured such that it can be turned on or off. | 22.6
194344 | Include Verify Current Income in RRV | The purpose of the CR is to proactively retrieve VCI Income from the RRV composite service and use the verification data during the passive renewal process. This will help to minimize online traffic and potential delays during renewal processing. As a part of this CR, RRV Batches will be updated to include VCI Service. CalHEERS will also populate the VCI-RRV response in DER-U when an updated response is received from this service. | 22.7
121903 | Document Image Conversion tool | This CR provides functionality in CalHEERS to convert all user uploaded documents related to verification / eligibility to PDF in order to standardize a single file format to be stored in CalHEERS. | 22.9
171266 | Notices Updates for R22.9 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 22.9
186107 | CalWIN Conversion to CalSAWS Wave 1 (Placer, Contra Costa and Yolo) | This initiative is the first of six waves to support the CalWIN to CalSAWS Migration for Placer, Contra Costa and Yolo counties. | 22.9
188309 | Updates to Terminate case, Duplicate case closure and CancelDER functionalities | The following functional changes are requested in CR 188309: Terminate Applications: - When a case is terminated the case status will be updated to "INACTIVE" -When an admin submits case for termination, the Case Transaction History Screen will have a record "Case Terminated" If Cases Closed as Duplicate/ Cancel DER is received from SAWS: - Case Transaction History page will have a record "Duplicate Case Closure" -all individuals on a case will be discontinued for the current benefit year at the end of the current month - if the case has been renewed, eligibility will be all individuals for the future benefit year effective 1/1, and Account Transfer will be sent for current and future benefit years | 22.9
189274 | Update Incarceration Functionality for MAGI Medi-Cal | This CR's goal is to ignore the incarceration verification and admin fail for MAGI Medi-Cal Individuals. Therefore, individuals will now be eligible if otherwise eligible for MAGI Medi-Cal even if they have an outstanding/Pending Incarceration Verification. A new Negative Action will be added to allow for the discontinuance of MAGI Medi-Cal individuals due to incarceration. | 22.9
190956 | State-Level Cost Sharing Reduction program | As per the 2021-2022 State Budget (AB 128) and Health Omnibus trailer bill (AB 133), funds have been allocated to be used for cost sharing reductions under affordability programs operated by Covered California. State level CSR functionality should be implemented from plan year 2023 onwards. The existing Federal CSR program and the new State CSR program should be made configurable and Covered CA should be able to decide which CSR program would be used for eligibility determination in a benefit year. Different FPL levels would be used for the State CSR determination. CalHEERS shall update notices to appropriately notify individuals about the new State Level CSR program. Reports need to be generated for households eligible to the State CSR program. Shop and Compare shall determine eligibility to the appropriate cost sharing reduction program based on the configuration for a particular benefit year. | 22.9
191292 | 2023 Renewals | Annual renewals related system enhancements | 22.9
197324 | ARPA Postpartum Coverage Extension for all MAGI Medi-Cal and MCAP Programs - Phase II | Exempted Negative actions applied during the Postpartum period continue to be exempt from discontinuance after the postpartum periods ends. The latest pregnancy information should be sent to SAWS in the DER transaction until the end of the postpartum period. | 22.9
197806 | Security Enhancements for Portal Pages | CalHEERS will implement security enhancements to protect consumer PII. CalHEERS portal can be improved to ensure that the consumers have a more secure CalHEERS account and the PII data is protected | 22.9
200351 | Notices CR for 23.12 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.12
114946 | Consumer Document Upload Functionality and Admin Task Management | This CR is split from CR 99895 and includes consumer document upload functionality requirements and task management as a result of that upload functionality. | 23.2
147420 | Administrator Search Enhancements | This CR will begin the redesign of the Admin CalHEERS portal search screen to improve usability and provide more details for our admin users. With this change, CalHEERS will introduce enhanced case searching functionality. | 23.2
173678 | Medicare Coverage Dates | CalHEERS should be able to persist and read the partial Medicare coverage details from the Medicare response for the year and then evaluate consumers eligible for subsidy only for months that are not covered by Medicare. If the response indicates a Medicare Coverage End Date in the future, system should be able to make a correct determination of whether it should count as a Medicare covered month. CalHEERS should have the functionality to not read ALL partial coverage year scenarios as not covered by Medicare. | 23.2
186216 | CalWIN Conversion to CalSAWS Wave 2 (Santa Clara, Tulare) | Santa Clara and Tulare will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 02/2023. | 23.2
186218 | CalWIN Conversion to CalSAWS Wave 3 (Orange, Santa Barbara and Ventura) | Orange, Santa Barbara and Ventura will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 04/2023. | 23.2
190570 | 2023 Annual FPL Updates | The purpose of this CR is to track the Annual FPL Updates and continue to streamline and improve operational efficiencies Business would like to update the annual FPL values dynamically, to make this annual process more efficient. | 23.2
200349 | Notices CR for 23.2 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.2
TBD | Chat Bot Integration into CalHEERS | Integrates CiCi (.com chat bot) with CalHEERS | 23.2
189474 | Plan Choice and Assister Portal Project (PCAP) | Replace the existing COTS product(s) with a custom solution that is integrated with the HBEX custom solution to produce custom software solution or a combination of a custom/Salesforce solution for the CalHEERS Eligibility and Enrollment functionality. Note that 6 child CRs were created in RTC to support the initiative from an administration perspective: CR 193111 - Plan Choice and Assister Portal Project (PCAP) - Plan Management CR 193114 - Plan Choice and Assister Portal Project (PCAP) - Enrollment & Shopping CR 193115 - Plan Choice and Assister Portal Project (PCAP) - EDI & Enrollment Batches CR 193140 - Plan Choice and Assister Portal Project (PCAP) - Agent & CEC Portal CR 193143 - Plan Choice and Assister Portal Project (PCAP) - Issuer Portal CR 193144 - Plan Choice and Assister Portal Project (PCAP) - Admin Self-Service CR 193145 - Plan Choice and Assister Portal Project (PCAP) - Policy Based Payments & Renewal Batches | 23.4
165890 | ROP Batch - Phase II | In Release 21.2, Phase I will be released. This CR is a placeholder to allow for any adjustments that may be needed to the system to ensure the efficient operation of the ROP Batch post that release. | 23.6
186221 | CalWIN Conversion to CalSAWS Wave 4 (San Diego, San Mateo, Santa Cruz and Solano) | San Diego, San Mateo, Santa Cruz and Solano will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 06/2023. | 23.6
186317 | CalWIN Conversion to CalSAWS Wave 5 (Alameda, Fresno and Sonoma) | Alameda, Fresno and Sonoma will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 04/2023. | 23.6
190310 | Supplemental Notices Insert and Notices Hold Release | Covered CA would like to have the option of automating a supplemental notice insert (content previously known as buck slip) with a notice, so that the generated pdf has the supplemental notice insert and it can be scanned as a whole notice and uploaded to the consumer account. Covered CA would also like to have the supplemental insert in all the supported languages with the capability to handle full color/gray scale, bold, italics, underline, special characters, charts, tables and images and printed on a single or double page (half, third of a sheet, full sheet) with the option of selecting the positioning of the supplemental notice insert in the notice package. Covered CA would like to expand the functionality of an Admin Notice (NOD00), so that the admin notice can be generated in all the supported languages with the capability to handle full color/gray scale, bold, italics, underline, special characters, charts, tables and images. It should also include the short version of the babel page and the non-discrimination 1557 language. Covered CA would also like to hold/release a notice through an automated process that can be easily managed and tracked by the team. | 23.6
200350 | Notices CR for 23.6 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.6
40149 | Automation of the Application Missing Information Notice (NOD16) | The objective of this initiative is to allow admin roles to skip required fields and automatically send the consumer notification of missing information. | 23.9
61104 | Implement Plan Dependent Rules | Update CalHEERS to implement the enforcement of plan dependent rules. CalHEERS enrollment grouping rules should include plan dependency definitions, by only allowing Married spouses, Registered domestic partners, Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners, Disabled adult children of any age (including 26 or above) and Siblings under the age of 26 to enroll in the same Covered CA plan. CalHEERS should also prevent enrollment of over-age dependents unless they meet the “disabled child” exception. | 23.9
96957 | Update CalHEERS to include downstream processing when an Individual is removed from a case | Provide messaging – Remove a member The objective of this initiative is to ensure downstream processes occur when a consumer requests to remove a household member from a case in CalHEERS. | 23.9
166033 | Prospective Premiums for Renewals | The intended outcome is to better inform consumers about what their next year's APTC and premium amounts will be if they keep their same plan. | 23.9
180018 | Spanish URLs for CalHEERS Portal Login and Shop & Compare | Covered CA is seeing a high drop rate of Spanish Consumers ending their sessions after landing on the English version of CalHEERS Portal Login (https://apply.coveredca.com/apspahbx/ahbx.portal) and Shop & Compare (https://apply.coveredca.com/lw-shopandcompare/) based on analyzing the stats collected from Google Analytics. Covered CA has determined that most Spanish Consumers are clicking on URLs provided by Covered CA Marketing campaigns and Covered CA partners. Covered CA would like dedicated Spanish URLs to direct Spanish Consumers to CalHEERS Portal Login and Shop & Compare and automatically select Spanish language. Spanish Consumers will land on CalHEERS Portal Login and Shop and Compare pages in Spanish when Consumer clicks on hyperlink provided by Covered CA Marketing campaigns and Covered CA Partners. | 23.9
186319 | CalWIN Conversion to CalSAWS Wave 6 (Sacramento, San Luis Obispo and San Francisco) | Sacramento, San Luis Obispo and San Francisco will be migrated to CalSAWS (LRS designation of consortia in CalHEERS) in 10/2023. | 23.9
200352 | 2024 Renewals | Annual renewals related system enhancements | 23.9
200353 | Notices CR for 23.9 | This CR is created to capture and consolidate notice impacting business requirements identified for CR planned in the release. Sponsors may also include stand-alone BRs to add/enhance notices. | 23.9
TBD | Integrate Survey After Plan Added to Cart | Adds a consumer survey to CalHEERS post plan selection | 23.9
TBD | BREfS #7 - Carry Forward | This initiative will enhance and streamline the existing Carry Forward process by reducing the number of steps that eligibility workers are required to take in the current system. | 23.9
123319 | 2022 Annual FPL Updates | The purpose of this CR is to create functionality for the Annual FPL Updates to be made independently of a release. Business would like to update the annual FPL values dynamically, without requiring a production release to make this annual process more efficient. | 22.2.1

## 2024+ Pipeline
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
CalHEERS
Pipeline CRs / Initiatives
CR # | TITLE | BRIEF DESCRIPTION | RELEASE
183100 | SEP Dropdown and Workflow - Phase II | Problem Statement: The SEP reasons in the portal is not a comprehensive list that adheres to the federal regulations. The page does not have helpful information and causes confusion to the consumers in the Intake/RAC flow. Intended Outcome: The SEP reasons in the portal needs to be more intuitive and more helpful to the users: 1. Update and add to the available SEP reasons 2. Update and add to the business rules for each existing and new SEP reason 3. Dynamically display the SEP reasons in the drop down list based on the user role and application mode 4. Update the SEP page language 5. Allow users to capture multiple SEP reasons. System to determine the most advantageous SEP reason. 6. Capture SEP reasons at the household vs individual level. 7. Update eHIT/SAWS accordingly | 24.2
189273 | Implement Eligibility Functionality for Family Planning, Access, Care and Treatment (Family PACT) Program in CalHEERS | CalHEERS shall add the Family PACT application and eligibility process to the CalHEERS Portal and BRE, automate integration with MEDS, automate referrals for other IAP programs, and provide appropriate notices and messaging to Family PACT clients and Family PACT providers. Family PACT program aid code 8H is not considered MEC and shall not impact current CalHEERS functionality for determining eligibility for IAP programs. | 2023 TBD
82920 | BREfS #9 Verifications Only Service and Separation of Verifications by Source (previously BREfS - Phase D) | The intended outcome of this change is to modify both the CalHEERS portal and the eHIT architecture to add a separate Verifications Only service, while continuing to maintain the existing functionality described above for the combined VIED and BRE service. | 2024 Q1
118769 | SAWS Integration with DIVS Solution | The purpose of this initiative is to incorporate the eHIT changes to align with the integration of the document imaging verification solution. | 2024 Q1
128730 | Automation of Termination Reason Codes due to Fraud and Medi-Cal Eligibility | The objective of this initiative is to automate reason codes in 835 File Transactions between CalHEERS and Qualified Health Plans (QHP) that are conducted manually currently. | 2024 Q1
151332 | MAGI Medi-Cal Income Budget Periods | This initiative enhances the use of three budget periods to properly align with State law and Federal regulations and the budget period options selected in the SPA. As part of this initiative, the Projected Annual Income and Reasonably Predictable Future Income budget periods will be separated to allow for better alignment with current policy. | 2024 Q1
TBD | Alternative Formats – Accessibility Question | The purpose of this initiative is to add a question to CalHEERS Single Streamline Application for the applicant or representative to indicate any alternative format preferences. This initiative must align with all partner system enhancements for implementation. | 2024 Q1
45901 | SB 1341 AB 617 - BREfS Phase B | SB 1341 AB 617 - Notice Improvements - The objective of this initiative is to align CalHEERS with Senate Bill 1341 and Assembly Bill 617 and consolidate and send notices for Mixed Households in SAWS. | 2024 Q2
TBD | 90-Day Cure Period | This initiative will automate and streamline reinstatement of Medi-Cal eligibility in CalHEERS by SAWS when additional information needed to complete a redetermination is received within 90 days after discontinuance. This 90-day timeframe is referred to as the “cure period”. This initiative will help align the business processes across systems, and it may be merged with the broader BREfS: Application Life Cycle initiative. | 2024 Q2
TBD | Individual Level Eligibility | This initiative is intended to enhance and streamline the individual level eligibility functionality in CalHEERS. | 2024 Q2
85672 | Medi-Cal Plan Selection | The objective of this initiative is to provide the ability for MAGI Medi-Cal consumers to select a plan within CalHEERS. | 2024 Q3
151861 | Change in MEC Value for Aid Code 01 | Effective November 2019, refugees eligible for Medi-Cal aid code 01 are not entitled to Refugee Medical Assistance (RMA) benefits. Because aid code 01 will no longer include RMA benefits, it must NOT be considered Minimal Essential Coverage (MEC) in CalHEERS when the removal of RMA from aid code 01 takes effect. CalHEERS shall update the MEC table value for aid code 01 from TRUE to FALSE. Impacts to SAWS/Counties: SAWS will need to make noticing updates and potentially other changes per the pending ACWDL. | 2024 Q3
173135 | Enhance eHIT to Transmit Verification Documents Uploaded in CalHEERS to SAWS | Problem Statement: Consumers have the ability to upload outstanding verification documents in the CalHEERS portal. Currently the CalHEERS system does not notify counties/SAWS that Medi-Cal recipients have uploaded verification documents in the CalHEERS portal. In addition, the verification document is not transmitted to SAWS for verification by county eligibility workers. This Change Request will provide the functionality for CalHEERS to notify and send verification document/s to SAWS for county eligibility workers to complete verifications. Intended Outcome: Improved experience for business partners/SAWS. | 2024 Q3
TBD | Consumer Protection Programs | The objective of this initiative is to determine eligibility for the Consumer Protection Programs (CPPs) in the event a consumer lose eligibility in their coverage group. | 2024 Q3
TBD | Explore Horizontal Integration Improvements | Explore Horizontal Integration Improvements | 2024 Q3
122183 | Infants Initiative | The objective of this initiative is to enhance functionality for Medi-Cal Deemed Infants, provide ability to add Medi-Cal Access Program infants (MCAIP) and renewal functionality in CalHEERS | 2024 TBD
125938 | EDD Interface - Employer Address Information | The objective of this initiative is to enhance the EDD interface to collect employer addresses. This will reduce the need for consumers to enter employer contact information. This will ensure CCA has accurate information to send the required employer notifications. | 2024 TBD
132464 | CCHIP Enhancements | To enhance current CCHIP eligibility and renewal functionality in CalHEERS. Adding Pending Eligibility determinations, resulting in update changes to noticing and CCHIP daily extract file. What: The purpose of these changes are to align CCHIP eligibility with the CMS MAGI Medicaid & CHIP Electronic Verification Plan Who: These fixes affect eligibility for CCHIP beneficiaries. Where: CalHEERS currently does not determine a CCHIP child as pending eligible when certain electronic verifications are not reasonably compatible. Conditionally eligible outcomes are not consistent with the approved CMS MAGI Medicaid & CHIP Electronic Verification Plan. Why: If the requested functionality is not added, CCHIP eligibility will not be in compliance with CMS MAGI Medicaid & CHIP Electronic Verification Plan. | 2024 TBD
161090 | Value Based Insurance Design | Covered California would like to implement a Value Based Insurance Design pilot in select regions. Consumers in select regions will be enrolled in VBID plan designs. All consumers in the region will participate. There will be opportunity to opt in or out of this pilot. | 2024 TBD
170935 | Multiple Primary Tax Filers on the same case/application | Problem Statement: Currently, CalHEERS allows only one primary tax filer on a case/application. CalHEERS does not have the ability to calculate separate APTC amounts for multiple primary tax filer households on one case and also to enroll multiple tax households in one plan. Intended Outcome: Update CalHEERS to allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application/enrollment. Update the system to allow multiple different tax households with multiple different APTC amounts for one enrollment. Update the system to prevent any surplus APTC of one APTC tax household from being applied to another APTC tax household (even if both consumers are enrolled in the same plan). Update the system to generate multiple 1095s for multiple tax households that are enrolled on a single enrollment/plan. | 2024 TBD
183098 | Placeholder for Federal Annual Updates | Placeholder for automation improvements / reminder to improve efficiencies, whether process or system efficiencies | 2024 TBD
183209 | Eligibility Notice Generation Enhancement – Phase 2 | Phase 2: The purpose of this initiative is to enhance the CalNOD01 noticing system that lives within the business rules engine that will have the ability to effectively, efficiently, and accurately notice consumers about their eligibility determination. | 2024 TBD
TBD | BREfS #5 High Impact Business Validations | This initiative will first require the analysis of the high impact eHIT Business Validations (BVs) to identify potentially redundant or antiquated BVs. Updates to the identified BVs would improve the accuracy and speed of automated eligibility determination results. | 2024 TBD
TBD | BREfS #8 eHIT Enhancement of Data Overlay | This initiative will enable CalHEERS to process eHIT eligibility requests from SAWS without impacting exchange programs by overlaying required data elements. | 2024 TBD
TBD | Eligibility Results Page Phase II | TBD | TBD
165044 | Changing Shop & Compare Defaults to Reduce Choice Errors for Silver 87- and Silver 94-eligible consumers | The intended outcomes will be (1) a substantial reduction in CSR choice errors and (2) enhanced tracking for data analysis. | 2024 Q3
158891 | Create/Assign CalHEERS Unique Person Identifier | The Create/Assign CalHEERS Unique Person Identifier CR aims to create a new CalHEERS Unique Identifier (CUI) that is assigned to all individuals on CalHEERS. Using CUI, CalHEERS will be able to map an individual who has been added multiple times to multiple cases on CalHEERS to a single unique identifier for that individual. | TBD
88353 | Implementation of GI PCP Selection Module and Provider Map | The objective of this initiative is to add functionality to the existing Provider Directory for physicians designated as Primary Care Providers (PCPs). The new functionalities are part of the GI PCP Module: 1) PCP Assignment for QHP 2 ) Network Density Tools: This feature will allows consumers to search an area where they desire coverage and determine in real-time how many providers are active in an area for a health plan issuer. | 2024 Q3