## 2020 Release Roadmap
Press TAB to move to input areas. Press UP or DOWN arrow in column A to read through the document.
RELEASE | CR # | TITLE | REQUESTOR | BRIEF DESCRIPTION | STATUS UPDATES for 08/25/20 AB 1296 MEETING
20.2 | 147416 | Tax Information: Tax Messaging Updates – User Centered Design Updates (UCD) | CalHEERS State | Tax Information: Tax Messaging Updates – User Centered Design Updates (UCD) | Implemented 20.2
20.2 | 138728 | Implementation of changes to income and deductions as a result of the Tax Cuts and Jobs Act 2017 | DHCS | Implementation of changes to income and deductions as a result of the Tax Cuts and Jobs Act 2017 - The objective of this initiative is to enhance previously implemented changes to align with the Tax Cuts and Jobs Act of 2017 to bring the CalHEERS application fully in compliance with the Act. The Tax Cuts and Jobs Act 2017 changed the treatment of alimony as income and deductions for all programs based on the MAGI methodology. As a result of the act, alimony is no longer used in the eligibility determination as income or a deduction when the separation or divorce agreement or modification were made on or after 01/01/2019. This CR aligned functionality with the tax law when alimony is paid or received. DHCS is currently completing UAT for this CR | Implemented 20.2
20.2 | 148955 | Account Home - User Centered Design Updates (UCD) | CalHEERS State | Account Home - User Centered Design Updates (UCD) | Implemented 20.2
20.2 | 145429 | State Subsidy Income Verification Updates | Covered CA | State Subsidy Income Verification Updates - This CR will implement an income verification that will be used in determining eligibility to the California Premium Subsidy Program. Income information received from the IRS, FTB, EDD, and SSA will be used to verify attested income. The use of information from the IRS in the income verification for California Premium Subsidy Program will be configurable and will be turned off. | Implemented 20.2
20.2 | 147053 | 2020 20.2 Notice Change Request | CalHEERS State | 2020 20.2 Notice Change Request - The objective of this initiative is to update notice language to align with changes made this release within CalHEERS. | Implemented 20.2
20.2 | 147418 | Documents and Correspondence - Functional Design - UI Updates (UCD) | Accenture | Documents and Correspondence - Functional Design - UI Updates (UCD) - The objective of this initiative is to update the Document & Correspondence pages to improve the user experience. | Implemented 20.2
20.2-20.4 | 146608 | Non-Warranty Close-Out | CalHEERS State | Non Warranty Defects Closeout | Implemented 20.3
20.3 | 145800 | Annual FPL Updates | DHCS | The purpose of this Annual FPL update is to implement the FPLs released by the Federal Register in January each year into CalHEERS. | Implemented 20.3
20.5 | 161368 | NEW: Update the treatment of UIB Income (COVID) for Emergency Increase in Unemployment Assistance | DHCS | 1. Enhance the current unemployment income collection page to add a new field to obtain the amount of the Federal Pandemic Unemployment Compensation. The amount of income entered into the Federal Pandemic Unemployment Compensation field would not be used in the eligibility determination for Medi-Cal (will defer to Covered CA on their treatment of this field). Similarly, when this income type was received from the SAWS EDR, the income should be handled in the same way. This income should pass between SAWS and CalHEERS to ensure correct eligibility for all IAPs. There would be no additional changes to noticing or the eligibility results page as a result of this enhancement. 2. Use the existing unemployment field and allow the Federal Pandemic Unemployment Compensation of $600 a week be automatically subtracted from the amount the consumer entered into the data field for Medi-Cal eligibility determinations. Covered California programs would continue to use the amount entered. This option would not require | Implemented 20.5
20.6 | 151996 | 2020 20.6 Notice Change Request | Covered CA | 2020 20.6 Notice Change Request - The objective of this initiative is to update notice language to align with changes made this release within CalHEERS. | Implemented 20.6
20.6 | 150743 | Provide Certified Enrollers Ability to View Enrollment Information Details | Covered CA | Provide Certified Enrollers Ability to View Enrollment Information Details - The goal of this CR is to provide Certified Enrollers with read-only access to the additional enrollment information currently available only to Service Center Representatives. This includes the panels containing Enrollee data, Enrollment History on the Enrollment Details Page and access to the Enrollment - Premium History Page. | Implemented 20.6
20.6 | 150741 | Display Enroller Delegation History | Covered CA | Display Enroller Delegation History - The goal of this CR is to display the Enroller delegation history of a household case/enrollment ID to the Service Center Representatives, Agency Managers, Certified Enrollment Counselors, Consumers, and the Issuer Representatives. | Implemented 20.6
20.6 | 144196 | Update the Issuer Portal to include Agent information | Covered CA | Update the Issuer Portal to include Agent information - The intent of this initiative is to enable authorized Carrier Representatives to access the Issuer Portal and view the broker delegation information for each month of an enrollment. | Implemented 20.6
20.6 | 138709 | Duplicate Application Logic Applied Within Single Streamlined Application | Covered CA | Duplicate Application Logic Applied Within Single Streamlined Application - Implements duplicate mapping logic currently available at account creation into the Single Streamlined application to better prevent duplicate cases from being created. | Implemented 20.6
20.6 | 153970 | Married Filing Jointly Spouse and Out of State | DHCS | Married Filing Jointly Spouse and Out of State This CR implements the requirement for individuals who self-attest to filing taxes as 'Married Filing Jointly' to include the individual they are filing with on the application. The following additional functional changes are included in this CR to support this requirement: -Allowing individuals included on the case to report an out of state address or indicate someone is residing out of the country. -Allowing an individual to indicate the other person on the case who they are filing a joint tax return with. This CR will also enhance the household composition logic for unmarried individuals who self-attest to filing taxes as 'Married Filing Jointly'. | Implemented 20.6
20.9 | 158675 | NEW BREfS #4: Enhance existing verification | DHCS | This initiative will enhance eHIT response from CalHEERS to SAWS to include existing verification data. This will allow a County Eligibility Worker to retrieve this data without logging in to the CalHEERS portal. There will be no impact to eligibility or the database. The data is already available in the system. After the schema update is made, SAWS can implement when ready. | CR is on track for 20.9 implementation
20.9 | 158676 | NEW BREfS # 6: Checking enrollment status for Consumers Transitioning from CovCA Programs to MAGI Medi-Cal | DHCS | When consumers report a change, this initiative will check enrollment status for exchange eligibility consumers and if not enrolled, allow them to be moved to MAGI Medi-Cal without Carry Forward. This will streamline the process for consumers needing access to care. | CR is on track for 20.9 implementation
20.9 | 155515 | CA State Subsidy Changes for Year 2 | Covered CA | CA State Subsidy Changes for Year 2 - The purpose of this initiative is to implement changes for the second year of the State Subsidy Program for benefit year 2021. | CR is on track for 20.9 implementation
20.9 | 156486 | 2020 20.9 Notice Change Request | Covered CA | 2020 20.9 Notice Change Request - The objective of this initiative is to update notice language to align with changes made this release within CalHEERS. | CR is on track for 20.9 implementation
20.9 | 142436 | GI Enrollment Enhancements (Update may not apply hover text, add sort feature for selected providers, and add “back to preferences” link to the plan tile) | Covered CA | GI Enrollment Enhancements (Update "may not apply" hover text, add sort feature for selected providers, and add “back to preferences” link to the plan tile) - Multiple benefit display enhancements requested by the Plan Management Division. | CR is on track for 20.9 implementation
[begin strikeout]20.9[end strikeout] 2022 | 151332 | MAGI Medi-Cal Income Budget Periods | DHCS | MAGI Medi-Cal Income Budget Periods - This initiative enhances the use of three budget periods to properly align with State law and Federal regulations and the budget period options selected in the SPA. As part of this initiative, the Projected Annual Income and Reasonably Predictable Future Income budget periods will be separated to allow for better alignment with current policy. | CR has been reprioritized for 2022 implementation
20.9 | 146748 | 2021 Renewals CR | Covered CA | 2021 Renewals CR - This is the annual CR to update the required contribution tables and may include automations of existing manual processes or small updates to program rules | CR is on track for 20.9 implementation
20.9 | 149502 | Former Foster Youth: Hide Verifications for Former Foster Youth (UCD) | CalHEERS State | Former Foster Youth: Hide Verifications for Former Foster Youth (UCD) - The objective of this initiative is to improve the upload document experience for Former Foster Youth. | CR is on track for 20.9 implementation
20.12 | 139571 | State Subsidy California 3895s | Covered CA | State Subsidy California 3895s - This CR will generate State 3895 forms mirroring the Federal 1095-A forms sent to consumers and will set up an annual process of integration with the Franchise Tax Board (FTB). | CR is on track for 20.12 implementation
[begin strikeout]20.9[end strikeout] 21.2 | 159613 | MAGI Medi-Cal to Covered California Eligibility Determinations Improvements (IAP) | CalHEERS State | Revised: The objective of this initiative is to improve the eligibility determinations for consumers discontinued from MAGI Medi-Cal and possibly eligible for Covered California. Since the passing of Senate Bill (SB) 26, Covered California and DHCS have renamed this initiative to better reflect the updated objectives of this change. This will serve as a foundation to ensure proper and accurate auto-enrollment beginning 7/2021 as specified in SB260. Currently CalHEERS provides Covered California eligibility of consumers moving from MAGI Medi-Cal to Non-MAGI Medical programs. Consumers who are eligible to Non-MAGI Medi-Cal with a zero share-of-cost should not have enrollment in Covered California. These improvements would ensure consumers eligible for Non-MAGI Medi-Cal with zero share-of-cost would not be auto-enrolled when SB260 CR is put in place. | CR has been reprioritized for 21.2 implementation
[begin strikeout]20.9[end strikeout] 21.9 | 147420 | Admin: Super Search – User Centered Design Updates (UCD) | CalHEERS State | Administrator Search Enhancements – User Centered Design Updates (UCD) - | CR has been reprioritized for 21.9 implementation
[begin strikeout]20.9[end strikeout] 21.2 | [begin strikeout] 109748 [end strikeout] | Redefined and To Be Implemented in 2021. See 2021 Initiatives List for full details. [begin strikeout] Eligibility Preview/Standby (BREfS - Phase C Part 4) [end strikeout] | DHCS | [begin strikeout] Eligibility Preview/Standby (BREfS - Phase C Part 4) - The objective of this initiative is to modify the eHIT architecture to add a CalHEERS Eligibility Preview for CEWs in SAWS and may also provide the preview capability via the CalHEERS portal for use by Covered CA SCRs and designated state staff for state managed programs in CalHEERS. [end strikeout] | [begin strikeout] CR is currently in Collaborative Design Sessions. [end strikeout] CR is planned for 2021 Implementation.
[begin strikeout]20.9[end strikeout] 21.2 | [begin strikeout] 109749 [end strikeout] | Redefined and To Be Implemented in 2021. See 2021 Initiatives List for full details. [begin strikeout] Next day eligibility determination/remediation (BREfS - Phase C Part 3) [begin strikeout] | DHCS | [begin strikeout] Next day eligibility determination/remediation (BREfS - Phase C Part 3) - The objective of this initiative is to allow CEWs remediation of CalHEERS eligibility determinations to occur via eHIT after eligibility was finalized the day prior. This remediation will be subject to existing county case management processes for effectuating correct Medi-Cal eligibility in SAWS. This initiative could also provide the next day remediation capability via the CalHEERS portal for use by Covered CA SCRs and designated state staff for state managed programs in CalHEERS. [end strikeout] | [begin strikeout] CR is currently in Collaborative Design Sessions. [end strikeout] CR is planned for 2021 Implementation.
[begin strikeout]20.9[end strikeout] 21.2 | [begin strikeout] 109747 [end strikeout] | Redefined and To Be Implemented in 2021. See 2021 Initiatives List for full details. [begin strikeout] Override eligibility determination functionality (BREfS - Phase C Part 2) [end strikeout] | DHCS | [begin strikeout]Override eligibility determination functionality (BREfS - Phase C Part 2) - The purpose of this initiative is to enable CEWs to override CalHEERS eligibility determinations via eHIT, which will be subject to existing county case management processes for effectuating correct Medi-Cal eligibility in SAWS. This initiative could also provide the override capability via the CalHEERS portal for use by Covered CA SCRs and designated state staff for state managed programs in CalHEERS. [end strikeout] | [begin strikeout]CR is currently in Collaborative Design Sessions. [end strikeout] CR is planned for 2021 Implementation.
[begin strikeout]2020 Q4[end strikeout] 20.9 | TBD | Rewrite NOD12 and Reduce number of NOD12 | Covered CA | Rewrite NOD12 and Reduce number of NOD12 - Initiative was included in CR 156486 20.9 Notice Change Request | CR is on track for 20.9 implementation
TBD [begin strikeout]2020 Q4[end strikeout] | 95184 | SEP Dropdowns and Workflow | Covered CA | SEP Dropdowns and Workflow - The objective of this initiative is to update the SEP reasons in the online application and also update eHIT/SAWS accordingly. | CR is currently under review for prioritization in 2022.
[begin strikeout]2020 Q4[end strikeout] 20.9 20.12 | TBD 166029 | NOD62 (Federal) and Form 1095s | Covered CA | NOD62 (Federal) and Form 1095s - | CR is on track for [begin strikeout]20.9[end strokeout] 20.12 implementation

## Sponsor Priority List (hidden)
SPONSOR PRIORITY LIST - | [5 empty] | KT Artifacts
CR Number | Summary | Requested Release | Sponsor Type | CovCA Priority | DHCS Priority2 | ICR/Policy Form | Rqmts | Collab Design
142899 | Married Filing Jointly Spouse and Ouut of State Requirements | 2020 Q2 | Shared | 2 | 1 | Yes | Yes | Yes
124914 | IAP Transition Enhancements | 2020 Q2 | Shared | 2 | 2 | Yes | No | Yes
142238 | Non-Warranty SIRS for 2020 Q2 | 2020 Q2 | Shared | 1 | 1 | No | Yes | No
138709 | Duplicate Prevention Logic | 2020 Q2 | Shared | 1 |  | Yes | Yes | No
119303 | Technical Updates to Separate Eligiblity and Verification Processing | 2020/2021 | Shared | 3 | 1 | No | Yes | No
118769 | SAWS Integration with DIVS Solution | 2020/2021 | Shared | -- | -- | No | Yes | No
109749 | Nex day eligiblity determination/remediation (BREfS - Phase C Part 3) | 2020/2021 | Shared | 3 | 3 | No | No | No
96957 | Update CalHEERS to include downstream processing when an individual is removed from a case | 2020/2021 | Shared | 2 | 1 | Yes | No | No
122247 | CalHEERS Web Service Update to Support IVR Flow for Multiple Enrollments | 2020/2021 | Shared | 1 | 3 | Yes | Yes | No
123319 | Auomate and Streamline the Annual FPL Updates | 2020/2021 | Shared | 0 | 0 | Yes | No | No
109747 | Override eligibility determination functionality (BREfS - Phase C Part 2) | 2020/2021 | Shared | 3 | 2 | Yes | Yes | Yes
82920 | Verifications Only Service and Separation of Verifications by Source (BREfS - Phase D | 2020/2021 | Shared | 2 | 0 | Yes | Yes | No
124261 | Build OPA-based CalNOD01 Noticiing System and update CalNOD01 triggering conditions | 2020/2021 | Shared | 2 | 3 | Yes | Yes | No
TBD | 2021 Renewals CR | 2020 Q3 | Shared | 2 | -- | No | No | No
80400 | Create Landing Page for Non-CalHEERS Portal Application Users | 2020 Q1 | Shared | -- | -- | No | No | No
139051 | CalHEERS Verification Catching Functionality Update | 2020/2021 | Shared | 1 | 1 | No | No | No
96507 | Build new FTB Web Interface to replace the SFTP OAG | 2020 Q1 | Shared | 3 | -- | No | No | No
123978 | Testing Environment Updates - Update to Batch Jobs | 2020 Q2 | Shared | -- | -- | No | Yes | No
142487 | State Subsidy New FTB Interface | 2020 Q2 | Covered CA | 1 | n/a | Yes | Yes | No
95184 | SEP Dropdowns and Workflow | 2020 Q2 | Covered CA | 2 | n/a | Yes | Yes | No
116230 | Apply APTC Increase in Month of Change for Members Added via Birth or Adoption | 2020 Q2 | Covered CA | 3 | n/a | Yes | Yes | No
125989 | Reporting for CR 92295 - Verify Lawful Presence and for CR 92298 SSA Disability Verification | 2020 Q2 | Covered CA | 3 | n/a | No | Yes | No
128730 | Automation of Termination Reason Codes due to Fraud and Medi-Cal Eligibility | 2020 Q2 | Covered CA | 3 | n/a | Yes | Yes | No
98640 | BPM Workflow Additions and Modifications | 2020 Q2 | Covered CA | 3 | n/a | Yes | Yes | No
124707 | ROP Batch Configuration | 2020 Q2 | Covered CA | 1 | n/a | Yes | No | No
140479 | Data Exchange from CalHEERS to Salesforce Service Cloud | 2020 Q2 | Covered CA | 1 | n/a | No | Yes | No
TBD | Enroller view of enrollment details (GI only change) | 2020 Q1 | Covered CA | 1 | n/a | No | No | No
144196 | Agent info in the Issuer Portal (GI only change) | 2020 Q1 | Covered CA | 1 | n/a | No | Yes | No
138977 | Provider Data Management Tool | 2020 Q2 | Covered CA | 1 | n/a | Yes | Yes | No
139192 | Race/Ethnicity Mapping to Account Transfer Interface | 2020 Q2 | Covered CA | 1 | n/a | No | No | No
119171 | Account Transfer Final Phase | 2020 Q2 | Covered CA | 2 | n/a | Yes | No | No
150280 | GI Enhancements - Streamline or enhance enrollment process and/or Customer Admin Portal in Get Insured | 2020 Q2 | Covered CA | 1 | n/a | No | No | No
TBD | REM 3.0 Financial Reconciliation | 2020 Q2 | Covered CA | 1 | n/a | No | No | No
139503 | Move Plan Management to Cloud to Support Shop and Compare Functionality | 2020 Q3 | Covered CA | -- | n/a | Yes | Yes | No
44000 | Semiannual examination of data sources for enrollees in APTC or CSR | 2020 Q3 | Covered CA | 2 | n/a | Yes | Yes | No
45901 | SB 1341 AB 617 - BREfS Phase B | 2020 Q3 | Covered CA | 3 | n/a | No | No | No
TBD | Suppress NOD01 that have no eligibility changes | 2020 Q3 | Covered CA | -- | n/a | No | No | No
TBD | Rewrite NOD12 and Reduce number of NOD12 | 2020 Q3 | Covered CA | -- | n/a | No | No | No
TBD | Display of Agent Delegation History | 2020 Q3 | Covered CA | 2 | n/a | No | No | No
144858 | Generate EDI 834 transations to Carriers for Agent data changes | 2020 Q3 | Covered CA | 2 | n/a | Yes | Yes | No
142436 | GI Enrollment Enhancements (Update may not apply hover text, add sort feature for selected providers, and add “back to preferences” link to the plan tile) | 2020 Q3 | Covered CA | 2 | n/a | Yes | Yes | No
139571 | State Subsidy California 1095s | 2020 Q4 | Covered CA | 2 | n/a | Yes | Yes | No
TBD | NOD62 (Federal) and Form 1095s | 2020 Q4 | Covered CA | 2 | n/a | No | No | No
TBD | New State Notice and Form 1095s | 2020 Q4 | Covered CA | 2 | n/a | No | No | No
61104 | Allow RDPs and Children under the age of 26 on same plan with parents and implement Plan Dependent Rules | 2021 Q2 | Covered CA | 3 | n/a | Yes | Yes | No
70500 | Advance Availability of RAC (Permanent Move, Release from incarceration, MEC) | 2021 Q2 | Covered CA | 3 | n/a | Yes | Yes | No
139572 | Failure to Reconcile (FTR) for State Subsidy | 2021 Q3 | Covered CA | 3 | n/a | Yes | Yes | No
139575 | Notice Change Request - Including State Subsidy FTR Notice | 2021 Q3 | Covered CA | 3 | n/a | Yes | Yes | No
88353 | Implementation of GI PCP Selection Module and Provider Map | 2020/2021 | Covered CA | -- | n/a | Yes | No | No
90057 | Operationalize Ability to Add Case Notes from Novitex Move Update Report | 2020/2021 | Covered CA | -- | n/a | Yes | Yes | No
TBD | NOD01 Eligibility Table | 2020/2021 | Covered CA | 2 | n/a | No | No | No
TBD | GA360/BigQuery Custom Reports | 2020/2021 | Covered CA | 3 | n/a | No | No | No
125997 | County of Responsibility/Case Linkage Updates | 2020 Q2 | DHCS | n/a | 1 | Yes | No | No
122183 | Add Medi-Cal Deemed Infant and Medi-Cal Access Infant Program Functionality | 2020/2021 | DHCS | n/a | 1 | Yes | Yes | No
144390 | CalHEERS MEDS Reconciliation File Enhancements | 2020/2021 | DHCS | n/a | 2 | Yes | Yes | No
108101 | CalHEERS-SAWS Reconciliation | 2020/2021 | DHCS | n/a | 0 | No | No | No
123318 | Upgrade Adobe Live Cycle ES4 to Adobe Experience Manager | 2020 Q1 | CalHEERS | n/a | n/a | No | No | No

## Lookup Compare (hidden)
Sponsor Type
Shared
Covered CA | 24 Mo RTC Extract | 9/9 Sponsors | From 24 Mo RTC Extract | From Sponsor 9/9 List
DHCS | 3387 |  | missing from sponsor list
CalHEERS | 4180 |  | missing from sponsor list
| 4589 |  | missing from sponsor list
| 9558 | 124914 | missing from sponsor list | not in RTC
| 28865 | 142238 | missing from sponsor list | not in RTC
| 29679 |  | missing from sponsor list
| 40149 |  | missing from sponsor list
| 42017 |  | missing from sponsor list
| 44000 |  | missing from sponsor list
| 45901 |  | missing from sponsor list
| 60323 |  | missing from sponsor list
| 61104 |  | missing from sponsor list
| 65721 | 109749 | missing from sponsor list | not in RTC
| 70500 |  | missing from sponsor list
| 70678 |  | missing from sponsor list
| 73879 |  | missing from sponsor list
| 80400 |  | missing from sponsor list
| 82920 |  | missing from sponsor list
| 85672 |  | missing from sponsor list
| 88353 |  | missing from sponsor list
| 88757 |  | missing from sponsor list
| 90057 |  | missing from sponsor list
| 92297 | 118769 | missing from sponsor list | not in RTC
| 95184 |  | missing from sponsor list
| 95607 |  | missing from sponsor list
| 96957 |  | missing from sponsor list
| 98640 |  | missing from sponsor list
| 108099 |  | missing from sponsor list
| 108101 |  | missing from sponsor list
| 109747 |  | missing from sponsor list
| 109748 |  | missing from sponsor list
| 109749 |  | missing from sponsor list
| 109750 |  | missing from sponsor list
| 114727 |  | missing from sponsor list
| 114946 |  | missing from sponsor list
| 115536 |  | missing from sponsor list
| 116230 |  | missing from sponsor list
| 118577 |  | missing from sponsor list
| 118769 |  | missing from sponsor list
| 119171 |  | missing from sponsor list
| 119303 |  | missing from sponsor list
| 121729 |  | missing from sponsor list
| 121903 | 122247 | missing from sponsor list | not in RTC
| 122064 |  | missing from sponsor list
| 122183 |  | missing from sponsor list
| 122247 |  | missing from sponsor list
| 122469 |  | missing from sponsor list
| 123318 |  | missing from sponsor list
| 123319 |  | missing from sponsor list
| 123978 |  | missing from sponsor list
| 124261 |  | missing from sponsor list
| 124370 |  | missing from sponsor list
| 124707 |  | missing from sponsor list
| 124914 |  | missing from sponsor list
| 125259 | 96957 | missing from sponsor list | not in RTC
| 125938 |  | missing from sponsor list
| 125989 |  | missing from sponsor list
| 125997 | 123318 | missing from sponsor list | not in RTC
| 128730 | 108101 | missing from sponsor list | not in RTC
| 131435 | 144390 | missing from sponsor list | not in RTC
| 131752 | 142899 | missing from sponsor list | not in RTC
| 134753 | 122183 | missing from sponsor list | not in RTC
| 135107 | 125997 | missing from sponsor list | not in RTC
| 135188 | 138709 | missing from sponsor list | not in RTC
| 135547 | TBD | missing from sponsor list | not in RTC
| 138709 | TBD | missing from sponsor list | not in RTC
| 138977 | 90057 | missing from sponsor list | not in RTC
| 139051 | 88353 | missing from sponsor list | not in RTC
| 139192 | 139575 | missing from sponsor list | not in RTC
| 139503 | 139572 | missing from sponsor list | not in RTC
| 139571 | 70500 | missing from sponsor list | not in RTC
| 139572 | 61104 | missing from sponsor list | not in RTC
| 139575 | TBD | missing from sponsor list | not in RTC
| 139596 | TBD | missing from sponsor list | not in RTC
| 140479 | 139571 | missing from sponsor list | not in RTC
| 142238 | 142436 | missing from sponsor list | not in RTC
| 142436 | 144858 | missing from sponsor list | not in RTC
| 142487 | TBD | missing from sponsor list | not in RTC
| 142489 | TBD | missing from sponsor list | not in RTC
| 142899 | TBD | missing from sponsor list | not in RTC
| 144196 | 45901 | missing from sponsor list | not in RTC
| 144390 | 44000 | missing from sponsor list | not in RTC
| 144858 | 139503 | missing from sponsor list | not in RTC
| 145429 | TBD | missing from sponsor list | not in RTC
| 146608 | 150280 | missing from sponsor list | not in RTC
| 146748 | 119171 | missing from sponsor list | not in RTC
| 147053 | 139192 | missing from sponsor list | not in RTC
| 147322 | 138977 | missing from sponsor list | not in RTC
| 147415 | 144196 | missing from sponsor list | not in RTC
| 147417 | TBD | missing from sponsor list | not in RTC
| 147420 | 140479 | missing from sponsor list | not in RTC
| 147495 | 124707 | missing from sponsor list | not in RTC
| 147518 | 98640 | missing from sponsor list | not in RTC
| 148743 | 128730 | missing from sponsor list | not in RTC
| 148955 | 125989 | missing from sponsor list | not in RTC
| 149328 | 119303 | missing from sponsor list | not in RTC
| 149502 | 116230 | missing from sponsor list | not in RTC
| 149915 | 95184 | missing from sponsor list | not in RTC
| 150102 | 123319 | missing from sponsor list | not in RTC
| 150106 | 142487 | missing from sponsor list | not in RTC
| 150280 | 123978 | missing from sponsor list | not in RTC
| 150618 | 95607 | missing from sponsor list | not in RTC
| 150740 | 139051 | missing from sponsor list | not in RTC
| 150741 | 80400 | missing from sponsor list | not in RTC
| 150743 | TBD | missing from sponsor list | not in RTC
| 151332 | 124261 | missing from sponsor list | not in RTC
| 151488 | 82920 | missing from sponsor list | not in RTC
| 151843 | 109747 | missing from sponsor list | not in RTC